| I | Central Secretariat Library (CSL) including Secretariat Social Service |  | 12.30 | 2.86 | Providing information for research and reference to policy planners, academicians, research scholars etc. Modernization of office undertaking training and similar programmes for cultural organizations. | Added 2562 books including 1502 textbooks and also 3897 books were purchased in Hindi and other Regional languages. About 150 State Government publications have also been added to the collection. To undertake modernization of the office accommodation for efficient functioning of the Ministry orders were placed for modernization of 5 rooms in the Ministry. In addition to it, 35 computers with printers, 8 photocopiers and 11 fax machines were purchased for use of officers and staff of the Ministry. | CSL: 0.94 Sectt & Admn. 6.40 | CSL: 1.07 Sectt & Admn: 0.15 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| II | Zonal Cultural Centre | To aim of projecting culture kinships, which transcend territorial boundaries and to arouse and deepen awareness of local culture. | -- | 15.00 |  |  | - | 9.35 | Includes 30% provision towards pro-women, and 20% provision for ST allocation. |
| (i) | National Culture Exchange Programme | Exchange of artists, Musicians, performers, & sculptors etc. between different regions within the country for the promotion of rich cultural heritage of India |  |  | About 1100 programmes would be organized benefiting a large number of artists | 500 programmes organized benefiting a large number of artists till 31.12.2006. |  |  |  |
| (ii) | Documentation | Documentation of various folk & tribal art forms particularly the vanishing art forms for their proper preservation |  |  | Various folk & tribal art forms, great masters of member states will be documented as per advice of Programme Committee and research oriented projects would be taken in hand for publication | 43 documentation works have been taken up till 31.12.2006. |  |  |  |
| (iii) | Lok Tarang Folk Dance Festival 2007 | This festival is organized for Republic Day Celebrations during January each year for the promotion of our rich cultural heritage & national integration |  |  | This festival provides a unique performance opportunity for the folk artists from various parts of country at the national level. Besides this a large number of school children participate in R.D. Parade | This festival is to be held in the month of January 2007. |  |  |  |
| (iv) | Kurukshetra Utsav | Celebrated on the occasion of Geeta Jayanti Samaroh at Kurukshetra-a Sacred place related to Mahabharta |  |  | Very suitable occasion for the promotion of Indian art & culture. Classical & folk artists perform benefiting large number of people. Besides this a large number of craft persons are given opportunity to display & sell their products | Organized successfully from 22.11.2006 to 1.12.2006. Renowned artistes and more than 2 lakh visitors participated. |  |  |  |
| (v) | Guru Shishya Parampara | For the promotion & preservation of our Fast vanishing art Forms |  |  | Not only Gurus but shishyas are also benefited. About 100 gurus with 500 shishyas are likely to be benefited during the year. Art forms are decided in Consultation with State Governments from time to time. | 148 Gurus and 849 shishyas benefited under the scheme. |  |  |  |
| (vi) | Theatre Rejuvenation | Providing an opportunity to the theatre artists to stage plays & other theatre activities. Also interacting with each other on the Common platform |  |  | About 350 theatre groups would stage their plays and more than 1000 artists and a large number of people would be benefited in promoting the theatre. Workshops to promote theatrical skills will also be held. | Under this programme, 87 plays were staged. |  |  |  |
| (vii) | Crafts Mela | For promotion of craftspersons to demonstrate their skills & to sell their artifacts |  |  | About 1150 craftpersons from various parts of the country would participate attracting large number of people | About 1000 persons participated in craft mela. |  |  |  |
| (viii) | Young Talent Scheme | To recognize & encourage young Talented artists in various folk Art forms |  |  | About 120 folk art forms would be selected & competitions would be held involving sufficient number of upcoming artists & public. | 74 scholarships awarded till 31.12.2006. |  |  |  |
| (ix) | Shilpgram | Shilpgrams established by ZCCs are playing very significant role for the promotion & preservation of Indian Art & Culture & providing platform to the talented artisans. The main objective is to boost the activities in Shilpgram/Kalagram |  |  | A large number of artists & artisans are benefited. A large number of people are made aware of our rich cultural heritage. | A large number of artisans benefited. |  |  |  |
| (x) | International Folk Dance Festival | The Indian resurgence as a major player in Indian Polity & economy has cast upon as the responsibility of preserving & promoting folk art forms which are a store house of our cultural heritage and which face threat from the modernization process under way. This threat to folk is being all the countries and thus it behoves our stature to take a lead role amongst the Asian countries to take effective steps toward preservation and growth of folk art and traditions. |  |  | The International Folk Festival of India will have three major components – folk music and dance performance, exhibition – cum – sale of traditional handicrafts and handlooms and a one-day international seminar on “Globalization and the withering of Folk Traditions.”It is proposed to invite approx.15 countries, mostly from Asia, to participate in this festival. For the Music and Dance performance each country would be allowed sixteen participants while for the handicraft exhibition each country would be allowed | This festival could not be held due to administrative reasons. |  |  |  |
|  |  |  |  |  | 5 participants. A total of 315 participants from abroad and approximately a matching number from India are expected to take part in the festival. |  |  |  |  |
| (xi) | Festival of the North East | The objective of the proposed festival of the North East is to help the people in general and artists from the North East in particular to have a closer interaction with the rest of the country. |  |  | Around 500 artistes from North East including folk artistes, musicians, film & literary personalities etc. will be performing in a series of programs to be organized in Delhi . | The North East Festival is to be held on 18-25 February 2007 at Hyderabad.. |  |  |  |
| III | Sangeet Natak Academi, New Delhi | The Academy devotes to the furtherance of the performing arts of India, and seeks to achieve this by arranging performances by renowned veterans as well as by talented artists of the younger generations through training programmes, award of scholarships and documentations. | 5.40 | 9.00 |  |  | 3.78 | 6.41 |  |
| (i) | Organizing, Music, Dance & Theatre Festivals Seminar, Workshop on Music, Dance and Theatre | To preserve, promote and develop performing arts traditions in live practice on regional and national levels and support exchange of ideas, concepts and techniques nationwide. |  |  | National: 1. Lok Utsav - national festival of folk and traditional arts 2. Vande Mataram - National festival of Music 3. National Choreography festival 4. Theatre Festival and Seminar 5. National Festival of Andhra Dance Tradition and Seminar 6. Rang Sangam Festival of Theatre 7. Nritya Sangam Festival of Dance 8. Sangeet Sangam Festival of Music 9 Sangeet Sangam | . Some of the events viz. Lok Utsav, . Vande Mataram, National Choreography festival, Theatre Festival, National Festival of Andhra Dance Tradition, Sangeet Sangam, Sangeet Sangam and Seminar on Art Criticism postponed for the next Financial year, due to less allocation of funds for the current financial year The Festival of Theatre Rang Sangam held during the year also Nritya Sangam Festival of Danceorganised. |  |  |  |
|  |  |  |  |  | 10. Seminar on Art Criticism 11. Traditional Theatre Festival & Seminar Regional: 1. Brhaddesi Music Festival & Seminar of Central Zone 2. Festival & Seminar of Buddhist traditions of North East 3. Regional level celebration of Music Day, Dance Day & Theatre Day 4. Two regional seminars on folklore. | Brhaddesi Music Festival to be organized in March, 2007 at Varanasi. Theatre day to be achieved.Music and Dance day celebrated. Two Regional Seminars on Folklore to be held in Feb/March, 2007. International Odissi Dance Festival held in Bhubneswar. Hornbill Festival held in Nagaland. Seminar on Tapas Sen held in Delhi. |  |  |  |
| (ii) | Sponsorship of Young Talents - Yuva Utsav | To identify and promote talented young artistes of the country in dance and music and to subsidies and create new audiences |  |  | Four Festivals of Young Musicians and four festival of young dancers in North, South, East and West Zone Two Festivals for North East | Two Festivals of Young Musicians and two festivals of young dancers and one young Dancers Festivals for North East were held. |  |  |  |
| (iii) | Assistance to Young Theatre Workers | To support experimental works by young theatre directors, production of new plays, Training for Young Theatre Workers, upgrading standards in different regions. |  |  | Workshops for Young Theatre Artists in - Central Zone - 3 States Master training to 55 best young directors of East Zone and North Zone 4 festivals of young theatre directors in four states | 30 days workshops held at Panchmarhi and Allahabad. Master training to young Directors could not be held. festivals of young theatre directors held at Surat another will be held in Rajasthan in Feb., 2007. |  |  |  |
| (iv) | Assistance to Playwrights in Indian Languages | To support the endeavors of potential playwrights. Encouragement to writers of new plays, Translate plays in various languages |  |  | One Playwrights workshop including 10 new playwrights | To be achieved in March, 2007. |  |  |  |
| (v) | Scheme of Assistance & Support to Contemporary Choreographers | To support a contemporary expression and idiom of Indian dance and new compositions of experimental music |  |  | One Workshop & Festival of Contemporary Choreographers/ Composers Financial assistance to 10 institutions and individuals | To be held in March, 2007 at Guwhati. To be achieved. |  |  |  |
| (vi) | SNA Awards & Fellowship Welfare & Financial Assistance to Fellows & Awardees of the Akademi | To recognize excellence and sustained contribution in performing arts and support eminent old artists |  |  | 33 Awards and 5 Fellowships Mediclaim insurance for 350 Awardees and Fellows | To be achieved in March, 2007 followed by a week long Festival of Music, Dance and Theater in Delhi. |  |  |  |
| (vii) | Training & Preservation of Traditional Performing Arts | To Support different forms of music, dance and theatre, encourage young members of the traditional artists, support to such forms, style, traditions, gharanas etc. that are threatened by change |  |  | Training programme including 100 artists | It is an ongoing training programme. Achieved. |  |  |  |
| (viii) | Grants to Cultural Institutions | support to voluntary initiative nationwide for common goals of promotion of arts |  |  | Over 500 cultural institutions will be supported with financial assistance | Grants to almost 485 cultural institutions released. |  |  |  |
| (ix) | Project Grant to Individuals for Research in Performing Arts Financial Assistance for Publication and Akademi Publication Studies in Tribal Culture | To promote scholarship and public awareness in the field of Indian dance, drama and music. |  |  | 15 Research Projects 4 Akademi journals, 4 Seminar Reports, two 4 books 6 News Bulletin in English 6 News Bulletin in Hindi Financial Assistance to about 20 authors and 20 journals | To be achieved in March, 2007. Achieved/ being achieved. Achieved/ being To be achieved. |  |  |  |
| (x) | Documentation, Archive Collection & Research Purchase of Raw Material,, Technical Equipment for Documentation Production & Dissemination of Archival Material Pertaining to Performing Arts | To preserve traditions through audio/video documentation and dissemination |  |  | Recording of 150 hrs of audio 150 hrs of video 7000 photographs |  |  |  |  |
| (xi) | Library & Audio Visual Library | To support study, research and dissemination of knowledge |  |  | Expansion of Library information system Addition of 300 books 150 periodicals | It is an ongoing programme. Achieved. |  |  |  |
| (xii) | Akademi Museum | Preservation of performing arts objects and support to makers of these objects |  |  | Over 600 instruments and equal number of puppets and masks are preserved | Postponed to next Financial year. |  |  |  |
| (xiii) | Inter-State Cultural Exchange Programme | National Integration through Cultural Exchanges |  |  | 15 Exchanges involving 30 States/UTs | Achieved for 10 Exchanges involving 20 States/UTs. Balance to be achieved in March, 2005. |  |  |  |
| IV | Lalit Kala Akademi | Promotion of visual and plastic arts | 3.87 | 5.00 |  | Propagation and popularization of interstate music, dance and drama | 1.94 | 2.05 |  |
| (i) | Promotional activities in the field of visual & plastic art. Art Development Com. Dissmn Outgoing Exh,. National Exh. Triennale Archives Lectures & Film Camps Library Cons & Restn. Grants to State Akademis. Regional Centres Scholarships | The main objectives of the Academy are to provide infrastructural facilities to the artist’s community for the development of art activities of the country especially in the field of contemporary art. |  |  | Exhibitions: (Resonance, National, Outgoing, Incoming & Regional Art) Delegates: visiting India from abroad Delegates: visited abroad. Camps & workshops: National Regional Scholarships: Fellowship: Memorial Lectures: Art Publications: Portfolios Journals (English) Journals (Hindi) Artist Directory Regional Hindi Journal Art Festival in North East | 15 exhibitions 5 delegates 13 visited abroad. Camps & workshops: National - 02 Regional -12 Scholarships: 40 Fellowship:02 Memorial Lectures:42 Art Publications: Portfolios - 05 Journals (English)-02 Journals (Hindi)-02 Artist Directory- 01 Regional Hindi Journal - Art Festival in North East-01 |  |  |  |
| V | Sahitya Akademi | To undertake publishing & promoting Indian literature | 3.60 | 8.50 |  |  | 1.80 | 5.86 |  |
| (i) | Upgradation of Libraries and Information Services | To provide readers/ intellectuals the complete range of books and update basic information about writers and literary activities in India at one place, make documentary tele films on eminent writers and scholars in the field of literature with modern archive unit of visuals. |  |  | Purchase of books in 24 languages. Subscription and New journals to be added. Upgradation of the Akademi’s web site and Hindi web site to be taken up. Ten Documentary films on writers will be made. | 3500 books were purchased, 50 literary journals subscribed, 650 members enrolled. Audio/ video tapes are being catalogued, six documentary films were made, 3 shows of documentary films made by the Akademi were oragnised. |  |  | NIL |
| (ii) | ### Publication Schemes | The scheme to full fill the basic objective of the Akademi dissemination of Indian Literature and making available to multilingual societies of Indian Literary masterpieces from other language into their own language, histories of literature, monographs on Indian Writers, translation of important Indian and foreign classics, anthologies of poetry, short-stories, one-act plays, literary essays etc. |  |  | It is proposed to publish around 300 books in all the 24 languages recognised by the Akademi. The publication of bi-monthly journals Samkaleen Bharatiya Sahitya (Hindi) and Indian Literature (English) and a half yearly journal Sanskrit Pratibha (Sanskrit) to continue. | 270 books were published in 24 languages recognized by the Akademi. The publication of bi-monthly journal, “Indian Literature (English)” and “Samakaaleena Bharatiya Sahitya” (Hindi) continued. The work on update version of six Encyclopaedia Indian Literature has been started. |  |  | NIL |
| (iii) | Modernisation and improvement of administrative functioning | To keep pace with the improved technology of the modern electronic age. |  |  | The computerisation in the Akademi will be upgraded. The accommodation at New Delhi, Mumbai, Kolkata, Chennai and Bangalore on hire will continue. The interior of the Regional Office Kolkata office premises being purchased from Municipal Corporation Kolkata will be done. | The process of computerization of various sections of the Akademi including regional offices continued. A few computers and other office equipment like photocopy machines etc. were purchased. |  |  | NIL |
| (iv) | Literary functions and programme | To celebrate centenaries of great writers, hold regional, national and international seminars, writers camps, workshops, symposiums etc., provide writers a forum for their periodical gathering by organizing meet the author, men and books, Kavi Sandhi, Asmita for women writers, Katha Sandhi, Kavya Bharati, Mulakat, Samvad, Kavya Sandhya and Antral etc. |  |  | Around 35 Seminars including international seminars, Literary Forums, Men and Books, Katha Sandhi, Kavi Sandhi, Avishkar, Meet the Author, Through My Window, Asmita, Mulakat, Samvad, Book Release Functions and Sur Sahitya etc. | Around 90 literary programmes including Meet the Author, Poets’ Meet, Mulakat, Katha Sandhi, Kavi Sandhi organized. Similarly, 40 regional, national and international seminars were organized. |  |  | NIL |
| (v) | Services to writers | To enable young and old writers in Indian language to visit other parts than their own, send Indian writers and host foreign writer delegation under Cultural Exchange Programmes, to give award to literary works which merit appreciation and encouragement in all 24 Indian languages recognized by the Akademi. |  |  | Around 50 young writers to avail the Travel Grant scheme of the Akademi. The Akademi will participate in different Cultural Exchange Programmes including new ones as per the decision of the Government of India or on reciprocal basis. The Annual Awards will be given to writers in 24 Indian languages recognized by the Akademi. To conduct meetings of the 24 language advisory boards besides other committees. | 50 young writers availed the benefit of Tribal Grant scheme of the Akademi. Writers’ delegation visited China, Germany, Syria and two foreign writers’ delegation were hosted in India. |  |  | NIL |
| (vi) | Promotion of sale of akademi publication, advertisement publicity and book exhibitions | To advertise Akademi publications through literary journals, organize and participate in book exhibitions at regional, national and international level. |  |  | The Akademi will participate in around 90 book exhibitions at National/ Regional/International (Lahore / Frankfurt) levels. The Akademi proposes the sales target around Rs.250 lakhs for the year 2006-07. The target is to be achieved by participating in various book exhibitions at national / regional levels. | Akademi participated in 80 books’ exhibitions which include Frankfurt Book Fair and Lahore Book Fair. |  |  | NIL |
| (vii) | ##### Translation schemes | To make arrangements for training of translators by conducting workshops, interlingual research and translation, prepare a register of translators and identify titles for translations and their publications into other Indian languages and into foreign languages. |  |  | The Translation Prizes in 24 languages recognised by the Akademi will continue. The Translation Centers at Bangalore and Kolkata are likely to publish more than ten books in regional languages and English. Besides publication by the Translation Center will continue by translating important books in various Indian languages and vise-versa. The Centers will conduct Translation Workshops in languages recognized by the Akademi as well as un-recognised languages to strengthen the translation activities. New Translation Centers will be launched in Western and Northern regions. | The translation centre has published 20 translations in different languages, 5 manuscripts are at final stage. Translation prizes to 22 translators were given in a function at Bhopal. 10 translations of Akademi award winning books were published. |  |  | NIL |
| VI | Festival of India | To organize major cultural festivals in selected foreign countries for achieving better understanding and cooperation | 4.00 | -- | To hold “India Week” in the Republic of Korea, to host “Days of Ukrainian Culture in India” on reciprocal basis, to organize Indian festival in Brazil and to present cultural events in Germany in connection with Frankfort Book fare. | For organization and inaugural cultural function in Frankfurt Book Fare in October 2006 funds to the tune of Rs.1.00 crore was released to National Book Trust, M/o HRD. Glimpses of India – Events were organized in October – November 2006 under India-Korea Cultural Exchange Programme. | 1.00 | - |  |
| VII | National School of Drama, New Delhi | Promote Theatre and to conduct theatre training programme | 4.10 | 9.00 |  |  | 3.37 | 7.42 |  |
| (i) | Theatre workshop and part time courses in regions and locally and other training courses for faculty and staff. | To benefit a vast majority of theatre enthusiasts in various states with diverse languages and cultural backgrounds and to create theatre awareness in them. |  |  | 38 theatre workshops to be conducted. | 12 collaborative / intensive theatre workshops organized. |  |  |  |
| (ii) | Organizing of course of training Children Theatre in Delhi and outside Delhi | To develop personality and give exposure to children in terms of their expressions and confidence. |  |  | 21 children theatre workshops to be conducted. | 20 theatre workshops and 8 collaborative workshops conducted. |  |  |  |
| (iii) | Organising of collaborative programme of traditional group in villages and theatre festival/ exhibition. | Providing 3-year Advanced Dramatic Training Course and to acquaint the students from theatre from existing in different regions of the country. |  |  | 5 collaborative programmes. 2 Festivals are to be conducted. 2 exhibitions are to be displayed. 35 contractual experts will be benefited. | 3 Theatre Workshop with traditional groups. 1 summer theatre workshop festival by Rep. Co. 2 theatre exhibition of plays. 15-performance by weekend theatre groups. 9 performance of ANSDA from Mumbai. |  |  |  |
| (iv) | Creating Theatre Educational and Documentation Museum, Theatre Archives Museum. | To demonstrate and document the important activities of the school such as student production, Repertory Co., TIE co., outside productions, lectures by eminent people. |  |  | Documentation of the all activities. | Documentation of activities undertaken. Equipment and consumable material purchased. |  |  |  |
| (v) | Promotion of Folk, Tribal Arts and Educational Tours | To finalise the students of the 1, 2, 3 year with the existing folk and tribal art relating to theaterical and music forms. |  |  | Performances of invited groups conveniently with the scheduled period. | Theatre workshops and performance with folk and tribal groups and one educational tour were undertaken. |  |  |  |
| (vi) | National Theatre Festival | To conduct 8th National Festival. |  |  | One national festival with Indian and foreign theatre groups to be held in January 2007 | The National Theatre Festival (9th BRM) and Satellite Festival to be organized by the school at New Delhi and Kolkata during the period 6th-20th January 2007. |  |  |  |
| ### VIII | ### National Gallery of Modern Art | ### To create an understanding and sensitivity among the Indian public ### towards visual and plastic arts in general and to promote the development of contemporary art in particular. | ### 1.60 | ### 4.00 |  |  | ### 1.19 | ### 2.32 |  |

|  | ### Upgradation, Modernisation and maintenance of museum | ### To promote development of contemporary art in the Museum particularly |  |  | ### All galleries of the building to be renovated and modernized. To meet exacting international standards. Nine important exhibitions of eminent artists to be organized under its educational programme, 50 seats in each preliminary and advanced art appreciation course for awarding certificates. To organize summer art workshop. To organize 296 film shows and also 61 conducted tours to be organized for the benefit of the school children. More than 33 thousand persons expected to visit the museum and benefit from its presentations and other activities. | ### In addition to maintaining a well displayed Gallery, NGMA had organized; ### 9 Special exhibitions both a Delhi and Mumbai, 287 Film shows organized, 169 tours to the gallery organised for the benefit of school children, Art Sketch Club continued its activity at the Museum premises, Summer Art Workshop organized, 1210 student s visited the gallery, 210 children joined the Art Sketch Club, 216 children benefited from summer Art workshop, 18 delegations of both Indian and foreign country visited, 40740 persons visited the gallery of which 7540 were foreign nationals, 8 catalogues and 7 posters of special exhibitions were released, restoration of 45 art works and cleaning and conditioning of 517 art objects undertaken. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IX | Asiatic Society Kolkata | Declared as an institution of national importance. To launch research projects on language, literature, culture and socio-economical aspects | 4.60 | 2.50 |  |  | 2.30 | 1.25 |  |
| (i) | Development of Library System | To establish build, maintain institutions for promotion of research in humanities and sciences |  |  | (i) Book acquisition-2000 (ii) Micro film acquisition exposure-20000 sheets (iii) Cataloguing : Rare Books-8000 Nos. General Books-6000 Nos Journal-4000 Nos | 1400 volumes of books procured. 1464 titles of the journals acquired. 10079 sheet microfilmed / microfiched. 8000 rare books, 10000 general books and 4000 journals catalogued. |  |  | Continuous Process |
| (ii) | Augmentation of Research | Research work in different areas, imparting training, conduction seminars, lectures, workshops etc. |  |  | 30 projects, 10 Seminars, 40 Lectures, 4 Exhibitions/ Workshops. | 5 projects, 1 seminar, 4 workshops and 22 lectures conducted. |  |  | Continuous Process |
| X | Centre for Cultural Resources and Training, New Delhi | Aims to improve the quality of life through the medium of Academies working in the field of linking education with culture. | 2.10 | 5.75 |  |  | 1.22 | 5.05 |  |
| (i) | Propagation of Culture among school students | To conduct a variety of in-service Teacher Training Programmes such as Orientation Training Programmes, workshops, Seminars, Refresher course etc. |  |  | Orientation -3400 Teacher Educators/ In-service School Teachers Training Porgrammes/ Seminars/ Workshops/Refresher Course for Teacher Educators/in-service Teachers Teachers to be trained through Trainers-1500 Teachers Students to be trained under Community and Extension Programmes-30000 Students # Production Video films including CD Roms-4 Publications including reprints -12 Cultural Kits-800 | 2896 Teachers/ Teacher Educator have been trained in various training programmes. 1534 teachers trained through trainers. 93 Culture Clubs have been setting in various states in the country. 24302 Students have been trained. 93 Culture Clubs have been set up. 10 Publications including reprints. 800 sets of Cultural Kits have been produced till date. |  |  |  |
| (ii) | Cultural Talent Search Scholarship Scheme (CTSS) | Aims at providing facilities by awarding scholarship to study the performing and other arts to outstanding young children in the age group of 10-14 years. |  |  | Award of Scholarship under Cultural Talent Search Scholarships Scheme-350 | 385 Children have been awarded scholarship covering all parts of country including the north-east. |  |  | . |
| XI | Financial Assistance for Professional Groups and Individuals for specified performing art projects. (Dance, Drama and Theatre Ensembles) | To promote the Guru Sishya Parampara and support organizations / individuals working in the field of Performing Arts. | 1.30 | 10.00 | About 984 organisations/ individuals to be benefited. | About 1000 organizations were promoted and supported. | 1.20 | 9.84 | Do no anticipate any slippage as steps are already underway. Delay in convening the meeting. Includes 30% provision towards pro-women. |
| XII | Gandhi Peace Prize | Government of India announced institution of an annual international Gandhi Peace Prize for social, economic and political transformation through non-violence and other Gandhian methods as a part of celebration of 125th birth anniversary Mahatma Gandhi. | 1.30 | -- | The recipient of this prize is selected by the Jury headed by Hon. Prime Minister in accordance with the prescribed code of procedure. | Gandhi Peace Prize 2005 has been awarded to Archbishop Desmond Tutu in the Rashtrapati Bhawan. | 1.01* | - |  |
| XIII | Other Schemes |  | 34.90 | 80.91 |  |  | 27.65 | 38.77 |  |
|  |  | * position indicated as on 31.01.2007 |  |  |  |  |  |  |  |
| a. | Central Institute of Higher Tibetan Studies, Sarnath | Established with a view to educating the youth of Tibet and Himalayan border areas of India | 4.40 | 2.50 |  |  | 3.08 | 1.75 |  |
| (i) | Development of Library | ## 1. To Preserve Tibetan culture and tradition. ## 2. To restore ancient Indian sciences and literature preserved in the Tibetan languages. |  |  | Purchase of books, equipment and other material for its maintenance and development. | 150 books and also a number of computers were added to the library of the Institution. |  |  |  |
| (ii) | Publication and Printing. |  |  |  | 8 books to be published. | 2 books are under finalization for printing in multi languages. |  |  |  |
| (iii) | Rare Buddhist Text Research | To offer the alternative educational facilities to the students of Indian border area who formerly availed the opportunity of receiving higher education in Tibet |  |  | Workshop, Publication of Dhih journals and infrastructure to be held. | 2 magazines are being finalized for publication under this unit. |  |  |  |
| b. | Central Institute of Buddhist Studies, Leh | To develop multifaceted personality of the students through inculcation of the wisdom of Buddhist through and literature as well as to familiarize them with modern subjects | 2.64 | 6.50 |  |  | 1.85 | 4.54 |  |
| (i) | Construction of Building | A new complex with separate blocks for teaching, administration, library, hostel and residences being coming up in a phased manner with approximate cost of Rs.20.00 crore as approved by EFC. |  |  | To adhere to the time schedule in the past. | A new institute complex with separate blocks for teaching, administration, library, auditorium, hostel and residences purpose is coming up in a phased manner. |  |  |  |

| (ii) | Provision for existing Gonpa/ Nunnery school | To support educational activities in the number of Gonpas by providing teachers and stipend to the students. |  |  | 21 Gonpa/Nunnery schools to be opened | 21 Gonpa/ Nunnery schools to be opened and also creation of additional 26 posts of Gonpa teachers for the existing Gonpa/ Nunnery Schools. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (iii) | Other Activities under Plan like Publication of Books, Seminars,/ Symposium, conduct of Refresher courses, Purchase of Books, Fuel, Furniture/Furnishing items, Machine/ Equipments, etc. | These are the continuing activities of the academic nature and for efficient running of the Institute. |  |  | Continuing schemes will be dealt with by the organization as usual. | A number of rare manuscripts have been published by the Institute. These publications are reasonably priced for the benefit of the interested scholars / students. The institute offers four fellowships for research work leading to award of Doctorates in the field of Buddhism as well as in four other sects of Buddhism. |  |  |  |
| c. | Gandhi Smriti and Darshan Samiti | To propagate the life, mission and thoughts of Mahatma Gandhi by organizing various socio – educational and cultural programmes. | 2.45 | 4.50 |  |  | 1.90 | 4.10 |  |
| (i) | Promotional Activities | To plan and carry on activities for the promotion of Mahatma Gandhi’s ideals and of national causes identified by him. |  |  | Regular programmes with educational institutions, programmes for youth, programmes to mark, 100 years of Satyagrah: Gandhi and the contemporary world commemorative programmes. | For promoting of Gandhiji’s life and mission the samiti organized exhibitions conducted workshops, summercamps etc. at different parts of the country under auspices of Gandhi Kasturba Kendras. |  |  |  |
| (ii) | Dissemination | To undertake such activities as will lead to greater understanding of Mahatma Gandhi life, work and thoughts. |  |  | Publication of journals, books etc., research activities and strengthening of International Centre for Gandhian Studies and Research Training Seminars/ Workshops. | The samiti continued its activities on publishing of literature on Mahatma Gandhi and Research activities undertaken through ICGSR, also conducts workshops and organized training for women empowerment, panchayati Raj etc. |  |  |  |
| (iii) | Infrastructure and Development related activities | To acquire, maintain and preserve the personal papers and other historical materials pertaining to the life and works of Mahatma Gandhi. |  |  | Development of Gandhi Smriti and Gandhi Darshan Complexes; restoration; of Gandhian Heritage and Development of Gandhi and acquisition of art, objects, book etc. purchase of equipments etc. strengthening of Samiti’s infrastructure | The development of Gandhi Darshan and Gandhi Smriti complexes, acquisition of art works and books relating to Gandhi Ji and Strengthening of managerial and administrative matters were made under the programme of infrastructure and development of GSDS. |  |  |  |
| d | Nava Nalanda Mahavihara, Nalanda, Bihar | To revive past glories of the ancient university of Nalanda and to give post graduate studies and research in Pali language and literature and Buddhology. | 1.15 | 2.90 |  |  | 0.80 | - |  |
|  | Development programmes of the institution | Development and improvement of various ongoing programmes of the Institution including Cultural Exchange Programmes, workshops and printing of old and new publications and research work. |  |  | Books expected to be purchased - 1000. Workshops – 8 Seminars – 2 Couple of cultural exchange programmes. 500 copies each of the printed text to be brought out. Research workshops and seminars and their documentation to be taken. | In commemoration of Indian-Chinese friendship year, Mahavihara organized several events including receiving delegation from China along with a team of journalists from China and also visiting Indian Delegation to China. The Institute also organized an important cultural event in Korea titled “Glimpses of India-Cultural Events in South Korea.” Indian Food Festival, Indian Film Festival, Art Exhibition, Handicraft Exhibition etc. Mahavihara also organized workshops on Kharosti script and “Buddhist Philosophy and Modern Science.” |  |  |  |
| e. | Maulana Abul Kalam Azad Institute of Asian Studies, Kolkata | To conduct research and training of life and works of Maulana Abul Kalam Azad with the study of social culture, political and economic movement in Asia from the middle of the 19th century. | 0.55 | 3.00 |  |  | 0.39 | 1.93 |  |
| (i) | Research project including North East/ fellowship and other promotional activities. | To carryout research activities and revelation of political, social & economic changes particularly of South Eastern Asian countries. |  |  | One International Conference on “Calcutta as a Metaphor in Indian Diaspora” 5 lectures with 2-3 seminars | To develop a research programme for N.E India – concept note was discussed in the Institute. Two-day joint seminar on the theme “Rise to Challenge of Globalisation : Experiences of China and India” organized in collaboration with the China Centre for Contemporary World Studies, China. Few fellows of the Institute visited Yangon in Myanmar for a Conference / Seminar discussions with Myanmar Union Chamber of Commerce, Myanmar. Organized an International Conference on the theme “Away but not Apart – Evolving Relationships between Indian and her Diaspora”. 3 publications already released and 4 more books are expected to be released by the end of March 2007. |  |  | Delay in quarterly progress report and manuscript by the research scholars. |
| (ii) | Maulana Azad Museum | To establish a museum in honour of Maulan Azad at his residence at 5, Ashraf Mistry Lane, Kolkata-19. Contribution of Maulana Azad to Indian Nationality & Independence and its impact on posterities and collection of memorabilia for display for the visitors |  | - | Few dozens of photographs with caption and about a hundred memorabilia with LCD T.V. and the highest National Award will be displayed. | The building has been fully renovated by the CPWD and now houses the Maulana Azad Museum which was inaugurated on 11.11.2006. |  |  | Availability of Fund & completion of work by the C.P.W.D. & arrangement for display of the memorabilia |
| f | Kalakshetra Foundation, Chennai | A Cultural institution of International repute established for preservation of traditional values in Indian Art especially in the field of dance and museum. | 2.60 | 1.50 | The ongoing programmes of this institution will be taken up during 2006-07 | Foundation continued its ongoing programmes in the field of art and culture. | 1.82 | 1.05 |  |
| g | Fellowship to outstanding artists in the field of performing, literary and visual arts. | This scheme provides financial support to outstanding artists in the fields of music, dance, theatre, visual art, literature and traditional art forms of folk and indigenous art. | 1.10 | 4.00 | 400 scholarships, 85 junior and 85 senior fellowships to be awarded. | As against 400 slots, the Expert Committee has recommended 381 artists for award of scholarships. 85 Senior Scholarships and 85 Junior Scholarships were awarded. In addition to this, 9 Senior Fellowships and 8 Junior Fellowships have also been awarded in new areas. | 0.52 | 2.84 |  |
| h | Financial Assistance to distinguished art persons | To provide financial assistance to artists whose contribution in the field of art has been of great significance and who have attained an age of 58 years and above and are in indigent circumstances. | 1.50 | 2.40 | 1540 old artists to be provided assistance under this pension scheme. | 1317 old artists were provided assistance under this Pension Scheme. | 1.23 | 1.63 |  |
| i | Financial Assistance for Tribal/Folk Art | To promote and disseminate tribal art of culture. Also creating awareness of richness of tribal /folk art through documentation and organizing cultural activities including festivals. | -- | 1.80 | About 550 individuals /organizations to be assisted. | 600 organizations/ individuals were assisted. | - | 1.13 | Includes 20% provision for ST. |
| j | Financial Assistance for the Preservation & Development of cultural Heritage of the Himalayas | To promote, project and preserve the cultural heritage of Himalayas. | -- | 0.90 | 50 organizations to be assisted for promotion and dissemination of Himalayan Art. | 57 voluntary cultural organizations/ NGO/ Individuals have been benefited under the scheme. | - | 0.66 | Climatic condition of the North East could also affect timely implementation. |
| k | Financial Assistance for the Preservation and Development of Buddhist/Tibetan Culture and Art. | To promote and propagate the scientific development Buddhist/ Tibetan culture and tradition and also research in the relative fields. | --- | 2.50 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 222 Buddhist / Tibetan organizations were recommended for sanction of grant under the scheme. | - | 1.36 | The number of proposals to be approved by the Expert Committee will depend upon the quality of the project and capability of the organization |
| l | Setting up of multipurpose cultural complexes | To set up multipurpose cultural complexes including those for children and also creation of cultural infrastructure in state capitals and other towns. | -- | 15.00 | There are five applications each from Andhra Pradesh and Meghalaya. Some more applications from Madhya Pradesh , Uttar Pradesh, Jhankhand, Delhi, Chandigarh, Haryana, Assam, Nagaland are under finalization and some more are expected. | 12 States had been given grants for setting up of Multipurpose Cultural Complexes, out of 12, six new projects were given grants for the first time including Jharkhand, Karimnagar, West Bengal, Nanded, Gwalior, and another project P. Banga Jatra (W.B.). | - | 10.03 |  |
| m. | Building Grants to Cultural Organisations | To give grants to voluntary cultural organizations working in the field of dance, music, fine arts, indology and literature for construction of building and purchase of material. | -- | 5.00 | 385 beneficiaries will be awarded grants. | 400 beneficiaries were awarded grants. | - - | 6.41 |  |
| n. | Development of Cultural Organisations | To give grants to voluntary organizations of national fame engaged in cultural activities for holding a conference, seminars and symposia on important cultural matters. | -- | 2.00 | 106 organizations to be awarded grants. | 90 institutions/ NGOs have been recommended for Financial Assistance. |  | 0.44 |  |
| o. | Namgyal Institute of Tibetology, Sikkim | ## The Institute is an autonomous organization under the state govt. of Sikkim and gets regular grant- in- aid from this ministry. The main objective of this institute is to spread the knowledge of Chhos(Doctrine of Buddha). The Institute has ongoing programmes of translating and publishing the seminal texts preserved in its archives. | 0.30 |  |  | This institute continued its ongoing programmes of translating and publishing the seminal text on Buddhism preserved in its archives. This is also promoting the knowledge of chhos (doctorine of Buddha). | 0.15 | - |  |
| p. | #### Tibet House, New Delhi | ## A Charitable Society was set up by His Holiness Dalai Lama in 1965, is a regular grantee under the scheme of Financial Assistance for development of Buddhist/Tibet Organization.. The main aims and objectives of the Tibet house are to promote, preserve and protect the Tibetan culture, encourage the exchange the ideas and techniques between Tibetan and non-Tibetan artists and craftsmen. | - | 0.25 |  | This organization continued its activity for promoting, preserving and protecting the Tibetan culture and also maintain a museum in the Tibet house for the visitors. | - | 0.13 |  |
| q. | #### Delegation under Culture Exchange Programme | ## Promotion of Cultural relations with other countries of the world. | 0.80 | -- | The main purpose of this fund is to host cultural visits by foreign dignitaries organize meetings/ conferences under the cultural agreements. | 12 CEPs were signed with the countries Kuwait, Jordan, Romania, Russia, Latvia, Tajikistan, Tunisia, Italy, Botswana, France, Portugal, Egypt. | 0.06 | - |  |
| r. | #### Financial Assistance to Voluntary organizations for Centenary/ Anniversary Celebration | ## To highlight salient aspects of the life and times of important personalities in order to infuse in the public, particularly the young, the spirit of these great leaders. | 12.00 | 24.00 | To celebrate 2550th anniversary of Mahaparinirvana of Lord Buddha. (Non Plan) Funds for Khalsa Heritage Project to be given to Punjab Government as share of Central Government. (Plan) | For chalking out the programmes and the activities during the commemoration year a National Implementation Committee under the Chairmanship of Minister of Tourism and Culture has been constituted. For closing function to be held in Khushinagar on Budh Purnima Day in May 2007, a number of events and projects to be taken up 2007-08. A funds to the tune of Rs.6.68 crore has been given to the Government of Punjab in connection with Khalsa Heritage Project. | 3.69 | 6.68 |  |
| s. | #### Maintenance of National Memorials | ## To commemorate the role of eminent National Personalities who have contributed to and played a historic role in the history of the country. | 2.00 | -- | Financial assistance is given to the voluntary organizations for maintenance of National Memorials. | 2 organizations / NGOs were given grants for the year maintenance of National Memorials. | 0.10 | - |  |
|  | ## Total (Promotion of Art and Culture) |  | 66.78 | 152.16 |  |  | 45.46 | 97.43 |  |
|  | Archaeology, Archives and Museums |  |  |  |  |  |  |  |  |
| XIV | Archaeological Survey of India | This organization is mainly involved in conservation, preservation and maintenance of the built heritage of the country. | 177.00* | 75.00* |  |  | 137.41 | 50.27 | * includes establishment / administrative expenses. |
| 1 | Conservation & Preservation of Ancient Monuments: its up keeps and maintenance including environmental development. | For conservation, preservation and maintenance of centrally protected ancient monuments and sites. |  |  | Conservation works at about 800 monuments which include Structural Conservation of 700 monuments, scientific preservation in 120 monuments and integrated development which include structural conservation environmental development and chemical preservation. | 1124 schemes (works) for structural conservation, chemical preservation and horticulture operations were undertaken. |  |  | Natural calamities. |
| 2 | Providing basic amenities tourists | Development of basic amenities in Ancient monuments including provision of toilets, drinking water facilities etc. |  |  | Better visitors’ facilities and other amenities in 25 monuments. | Provided better tourist satisfaction and encouraged cultural tourism. |  |  |  |
| 3. | Excavation and Exploration. | Archaeological Exploration Scientific clearance and Marine Archaeological Explorations. |  |  | The projects include 8 excavation projects, 1 scientific clearance project, 8 exploration projects and 3 under water Archaeological Explorations. | These are ongoing and continuing programmes and are carried out on the basis of priority and terrain conditions. |  |  |  |
| 4. | Development of Archaeological Site Museums. | Maintenance and Development of Site Museums at various archaeological sites and monuments. |  |  | - Modernisation of existing site museums at Red Fort, Taj Agra, Hazrduary Palace, Kamlapur (Hampi). - Re-orientation of display in and in the site museums in new buildings which are under construction for site museums at Khajraho, Chanderi and Shivpuri. - Setting up new site museums at Fatehpur Sikri and Dholavira (Gujarat). | Maintenance, re-organization and modernization of 41 Archaeological Site Museums was carried out. |  |  |  |
| 5. | National Mission for Ancient Monuments and Antiquities | Inventorisation of unprotected monuments and antiquities. Creation of awareness. Preservation and conservation of unprotected built heritage and antiquities. |  |  | Preparation of a National database of unprotected monuments and another for antiquities. Documentation at regional and national level. Conducting workshops and awareness programmes for school children, college students and public. Training programme for stakeholders. | The project National Mission for Ancient Monuments and Antiquities is under consideration with the Ministry of Finance. The work will be initiated on this Mission as and when the approval of the project is received from the Ministry of Finance. |  |  |  |
| XV | National Archives of India | The custodian of non-current records of enduring value of Central Government Ministries / Departments / Offices and their predecessor bodies. The nodal agency for record management activities and their permanent preservation and use by the posterity. | 11.56 | 4.00 |  |  | 8.05 | 1.81 |  |
| (i) | Expansion of records Management Programme | i. Acquisition of Public Records ii. Appraisal of files iii. Vetting of Records Retention Schedule. |  |  | Acquisition of 20,000 files. Appraisal of 2500 files Vetting of 15 records 7 orientation courses to be conducted. Inspection of 12 developmental record’s room. | 20918 files acquired and also 13106 non-current files apprised. 8 schedules vetted, 6th and 7th Report of DGA was completed and distributed, 5 orientation cources conducted 8 departmental record rooms inspected. |  |  |  |
| (ii) | Expansion of National Register or Private Records | Publication of NRPR Volumes. |  |  | Volume 24 to be compiled and completed | Editing of Vol. 23 has been completed. Listing of 500 entries of volume 24 has also been completed. |  |  |  |
| (iii) | Expansion of repair and reprography | Repair of records, binding of books/ volumes/ preparation of security Microfilming, Preparation of Security Microfiche films, Positive printing of microfilms, Supply of copies (Xerox/ Photo/ Reader/ Microfilm to scholars as per their demand. |  |  | 1,18,000 sheets to be repaired, 4000 books/ volumes to be bound, 720 rolls to be microfilmed, 60,000 exospores to be completed, 28,000 meters printing to be done. | 79868 sheets repaired, 1539 books/ volumes binded, 406 rolls microfilmed, 8600 exposures completed. 43100 copies of zerox microfilm supplied to the scholars. 12000 mtrs. Positive printing done. |  |  |  |
| (iv) | Expansion of library and administration | Purchase of books Data Entry in to the computer Preparation of data input sheets. |  |  | 600 books to be purchased. 700 books to be made. 700 sheets. | 599 books have been ordered for acquiring for its library. data entry of 503 books completed, 464 data input sheets repaired |  |  |  |
| (v) | Listing of records ref. Media including computerization of records | Listing of private papers. Listing of oriental records and preparation of catalogue / reference cards of acquired documents. Data Entry of records. Validation of data/ online checking. Checking of printed entries of record series. |  |  | 5000 items of private papers to be listed 1680 items to be descriptively listed. 1,75,200 entries to be done 5,76,600 entries to be done 2,88,000 entries to be checked and corrected. | 2345 items of K. M. Munshi were listed, 125 items of oriental records listed, 5,89,000 entries for validation of data were completed, 325748 entries of reference media of records completed. |  |  |  |
| XVI | National Museum | A premiere institution in the field of art and culture in India and involved in important work of acquisition, conservation, exhibition and educational activities | 8.04 | 11.00 |  |  | 5.25 | 5.61 |  |
| (i) | Photo-documentation of art objects for printing purpose as well as for exhibition and for preparation of albums / colour photographs / transparencies. | - For printing purpose. - To have a record of the exhibits to be sent out and received at the Museum. - Preparation of albums / colour photographs / transparencies of the objects. |  |  | Subject to the requirements of various sections & exhibitions to be held. | Photo documentation done for Tejas and Gupta Exhibitions, Coloured photo documentation of Museum’s collection, exhibits for exhibitions and publications purposes and events publicity purpose done as per demand. |  |  | Subject to the requirements of various sections & exhibitions to be held. |
| (ii) | Display & Re-organization of Museum and Reorganization of existing galleries. | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | - Archaeological Galleries – Kushan, Ikshvaku & Gupta Galleries - Tanjore & Mysore Art Gallery - Modernization work carried from the previous year i.e. pre-Columbian & western Art, Central Asian Antiquities Manuscripts, Early Man & Gupta Gallery - Installation of modern gadgets such as plasma screen, kiosk etc in selected galleries - Modernization/ renovation of Reception counter/ dome, corridors, three rotunda - Design of Key galleries, including the Foyer, reception, entrance to the library & auditorium | Fabrication of show cases is under process, quotation for safety glasses have been invited and the case is under process for manuscripts galleries. |  |  |  |
| (iii) | Reorganisation of Reserve Stores | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | - Central Asian Antiquities - Textiles - Pre-Historic objects - Anthropology Pre-Columbian & western Arts | Call for fresh tenders processed, preparation of specifications, drawings, estimates and quantities to be completed. |  |  |  |
| (iv) | Setting up of New Galleries | About 90% of the Collection are in the respective stores of the departments. Stores have, therefore, to be suitably modernized on scientific lines. |  |  | Early Man Gallery | This work will be taken up during the next financial year as decided by the Museum. |  |  |  |
| (v) | Restoration and Conservation of art objects. Restoration of Oil Paintings / Conservation of antiquities / art objects / training course in conservation, Acquisition of equipments for conservation / binding of 7000 manuscripts. | - To protect the antiquities and art objects from decay. - To train the Museum staff of National Museum and other museums / Institutions in latest technology in conservation. - To keep laboratory well equipped with the latest equipments. |  |  | - Conservation of 1000 art objects of NM - Preventive treatment to 1000 art objects - Conservation of manuscripts - Three months training course of Paintings - Programme on preventive conservation for curators of different Museum/ Art Galleries (four days) - Teaching 2 conducting of practical class programme for students of NMI - Treatment of Paintings of Shri Chiba Art Gallery, Thirvananthap-uram Treatment of Paintings of North Block/ Parliament House/ | Cleaning and preservation of about 671 artifacts in laboratory, galleries, storage, Museum Garden and Rotanda’s National Museum. About 92 manuscripts treated under project for conservation and binding of manuscripts. Treating 13 paintings panes of Bharat Petroleum Corp., Noida, UP made by artist F.M. Hussain. Completed work on two big painting panels of National Bhawan. Work on canvas paintings of Rashtrapati Bhawan, Ashoka Hall is in progress. So far treated 4 paintings out of 20. Completed wok in Fresco room of Ministry of Finance on wall painting. Examined and prepared condition report of 67 artifacts selected in connection with exhibition at Rubin Museum of Art, USA, 41 manuscripts / artifacts selected for exhibition at Frankfurt, 5 bronzes prepared in connection with exhibition Chola bronzes at London. |  |  |  |
| (vi) | Exhibition | - To popularize the ancient Indian Art & Culture. - To organize thematic exhibitions. - To organize exhibitions under Cultural Exchange Programme |  |  | Exhibitions to be sent abroad - India’s contribution towards Islamic Art & Culture to the Gulf countries “Prakriti Purusha”, Budapest, Hungary - Exhibition on Chola Bronzes, Gupta Art to France - Buddhist Art of India, Korea - Gupta Art, Italy - Indian Art, Japan Exhibitions to be held at other places in India - “Marwar Paintings” at National Museum - “Kashmir Art”, Sri Nagar Nizam Jewellery Exhibition at National Museum | Exhibitions vis “On the path to Maha-Parinirvana in the foot steps of Lord Buddha” organized at Vigyan Bhawan and National Musuem, “Tejus” organized in Brussels, Belgium, “Nizam Jewellary” exhibition is under progress. The work of organizing “Gupta Art” exhibitions to be held in France during this year. |  |  |  |
| (vii) | Strengthening of Museum Security | To keep security arrangements up-to-date keeping in view the changing threat perceptions. - To keep the Museum and antiquities from threats such as fire etc. |  |  | - Conversion of black & white CC TV cameras into coloured ones - Extension of CC TV coverage to remaining galleries & storage area - Procurement of Thermal Surveillance cameras - Perimeter IR Detection System - Procurement of Perimeter fence (Electric) Procurement of Real time DVR, in CC TV Control Rooms | Installation of latest security equipments. Maintenance of CCTV system security equipments. |  |  |  |
| XVII | National Council of Science Museums | To popularize Science and Technology by organizing exhibition, seminars, training programmes for Science Teachers, students, young entrepreneurs, technicians etc. | 15.40 | 16.00 |  |  | 10.78 | 11.20 |  |
| (i) | Setting up of new galleries, upgradation and updation of exhibits, new circulating exhibitions, new mobile science exhibition units, new training facilities, educational programmes, strengthening of infrastructure and existing facilities of 25 science centers located at various parts of the country. | To modernize, upgrade and popularize the science and technology in the country. |  |  | Kalpana Chawla Planetarium Project, Kurukshetra and SRSC, Kalimpong SRSC, Jammu and Gangotk projects New Galleries on “Our Technology Heritage” at NSC, Mumbai and “Human Endurance at RSC, Calicut. Children’s gallery at VITM, Bangalore. Travelling Exhibitions on “Rivers” and “Illusion”, “Network”, “Human Genome” “An eye in the Sky” and “ A Century of Physics” | Inaugurated at NSC, Mumbai on October 9 2006. The gallery will be inaugurated on February 3, 2007 New Galleries on Behavioral Sciences, Biotechnology and Underwater exploration are completed at Regional Science City, Lucknow. ‘Fascinating Physics’ was opened at BITM, Kolkata on May 2, 2006. A life Science Galley was inaugurated at DSC, Digha on March 12, 2006. A new ‘Aquarium’ gallery was inaugurated at RSC, Guwahat on May 19, 2006. A new gallery on ‘Mathematics’ was inaugurated at RSC, Bhubaneswar on Sept. 18, 2006. The setting up of ‘Television’ gallery at BITM, Kolkata is in progress. The work of fabrication of cabinets is in nearing completion. Core exhibits under fabrication. The development work for the gallery at Science City, Kolkata has started. ‘Electronics’ at DSC is in progress. ‘Human performance’ at DSC, Burdwan is in progress. |  |  | By finalizing the Annual Action Plan 2006-07, the entire family will be phased out to four quarters to maintain the progress of work, a planned and steady flow of expenditure. |
| (ii) | Centralized procurement of LFFP system and Other Major equipment. | To set up large format film projection system at NSC, Mumbai. Procurement of high resolution 3D film and Motion simulator. |  |  | Addition of new facility by setting up of LFFP system at NSC, Mumbai to offer immerse science-learning ambience. | Various stages of approval have been obtained and final approval for Large Format Film Projection System is awaited. L.O.I. has been issued for the work as directed by Executive Committee of NCSM. Construction work has been started. Thermal imaging System procured and lying in CRTL. Material will be collected by respective centres shortly. |  |  |  |
| (iii) | On going new projects – KCMP, Kurukshetra | To set up Kalpana Chawla Memorial Planetarium at Kurukshetra |  |  | Being the first planetarium of its kind, being set up in the state of Haryana, this Planetarium is expected to provide astronomy education to the visitors. | The building for Kalpana Chawla planetarium has been completed and development of astro park is presently going on the project will be completed by 31st March 2007 |  |  |  |
| (iv) | Other New Projects: RSC, Ranchi, RSC, Jammu, SRSC, Kalimpong | To set up new centers in the state of Jharkhand, Jammu and Kashmir and West Bengal. |  |  | To popularize science and to spread science message and to create a scientific temper and awareness among the people of the region. | SFC clearance for RSC. Ranchi project has been obtained, Architectural planning completed, tenders floated for science centre. Work for RSC Jammu has not been initiated on account of non identification of a proper plot of land by the Government of J&K. The work for SRSC, Kalimpng is progressing as per schedule. The construction of science park path ways is completed. |  |  | RSC, Ranchi and RSC, Jammu will be taken up after SFC clearance and will be completed within 30 months from the date of commencement of construction SRSC, Kalimpong will be completed in 2007-08. |
| (v) | New Projects in NE states | To set up new Science Centres in the state of Sikkim |  |  | To popularize science and to spread science message and to create a scientific temper and awareness among the people of the region. | Frame structure of the building is nearing completion. Procurement of furniture, equipment etc. are complete and planning of exhibits is in progress. |  |  |  |
| XVIII | Science Cities | To popularize Science and Technology at selected centers in the country. | --- | 17.00 |  |  | - | 8.64 |  |
| (i) | To establish Gujarat Science City at Ahmedabad | To inculcate scientific temper in public at large and students in particular. |  |  | Facilities like Imax Theatre, Musical Fountain, Hall of Science, Energy Park, Simulator, Amphitheater are operationalized and Space and Communication Pavilion, Life Science Park, Children Activity Corner will be opened to public before December 2006. |  |  |  | To release balance one crore out of total grant of Rs.9.00 crore. |
| (ii) | Setting up of Pushpa Gujaral Science City, Kapurthala, Punjab. |  |  |  |  |  |  |  |  |
|  | Construction of 4 exhibit galleries and Convention Hall | For establishing exhibit galleries |  |  | Construction will be completed | The work is in progress. |  |  |  |
|  | Construction of buildings for Evolution Gallery | Establishing of Evolution Gallery |  |  | 80% construction work expected to be completed by March 2007 | The work is in progress. |  |  | Highly specialized buildings. |
|  | Electrification work, air conditioning, fire safety for the above buildings |  |  |  |  | The work is in progress. |  |  |  |
|  | Landscaping and garden development |  |  |  |  | The work is in progress. |  |  |  |
|  | Miscellaneous civil works Pending payment to M/s GEPC (Phase I buildings) |  |  |  | Pending Phase I work would be completed. | Work Under progress. |  |  |  |
|  | Construction of administrative block |  |  |  | 80% construction work expected to be completed by March 2007 | Work under progress. |  |  |  |
| XIX | Anthropological Survey of India | Committed to research activities on human population from bio-culture perspectives. Its activities include collection, preservation, maintenance, documentation and study of ethnographic materials as well as of ancient human skeletal remains. | 10.56 | 5.00 |  |  | 8.33 | 4.38 |  |
| (i) | Documentation and Dissemination | To maintain Anthropological Libraries in 7 Regional Centres and Headquarters. |  |  | Libraries of the Survey being center of excellence in the field of Anthropological research all over the country, through which around 1000 researchers, professors, administrators of different academic and other organizations take the help from this library as a center of reference and documentation. | Procurement of library books and journals for the Central Library at Head Office, Kolkata as well as Libraries in other regional centre made as a continuous process. |  |  |  |
| (ii) | Exhibitions | For promotion and dissemination of ethnographic materials as well as of ancient human skeletal remains and research carried out thereon. |  |  | Exhibitions on “Human Origin, Genome and People of India” in various places in N.E. India “Cultural Diversity” in Chhamba, H.P. | Surveys on going exhibition “Human Origin, Genome and People of India” has been disseminated at Guwahati, Kohima and is now undergone at Imphal during the period under review. |  |  |  |
| (iii) | Book Exhibitions/Fair | For promotion and dissemination of ethnographic materials as well as of ancient human skeletal remains and research carried out thereon. |  |  | Book Exhibitions: Kolkata Book Fair | The Survey would take part in the ensuing Kolkata book fare in January/ February 2007 with its noted publications. |  |  |  |
| (iv) | Induction of DNA technology | To establish DNA extraction lab and banking facilities in Shillong, Port Blair and Dehradun where the survey has its own buildings. To update and maintenance the DNA labs already functional at Kolkata, Nagpur, Mysore. |  |  | Preparing the infrastructure and trained manpower, to implement 11th Plan Project. | Under the programme of induction of Modern Techniques & methods for advancement of research in physical Anthropology with special reference to DNA Polymorphism, procuring of essential instruments, chemicals, gadgets, reagents etc. procured for laba analysis & extraction of the samples collected from the field investigation oat the DNA laboratories of the Survey at Kolkata, Nagpur, Mysore during this period which is a continuous process. |  |  |  |
| (v) | DNA study (reoriented as Human Origins, Genome and People of India) | To study and analyse the blood samples from the contemporary primitive tribes and skeletal materials. |  |  | Contribution to Genome Diversity in terms of DNA Banking. Impact publication (at least 3) in the field of Genetic Heritage of the country. To extract DNA from the fossilized bone materials of Rupkund (in collaboration with CCMB, Hyderabad) | The Survey is carrying out field work in connection with DNA study under four components vis. DNA Polymorphism & Diabetics, DNA Polymorphism & Phylogeny, DNA Polymorphism & Cardiomyopathy & DNA Polymorphism & Haemoglobinopa thies (Under Human Genetics Extension Programme) |  |  |  |
| (vi) | Growth (reoriented as children in N.E. : Growth and Development Study – A Public Health issue) | To generate information about the health status of the children of the North East India in Particular |  |  | During the year it is expected that 2000 children will be measured. | Growth and development study – a public health issue, teams of deployed research personal is carrying out extensive field work to generate information from the different population of NER on the aspects of growth of children and other health related issues. |  |  |  |
| (vii) | Transformation in India: Dormitory Systems among the tribes | To finalise the reports of the previous fieldwork. To supplement adequate information for formulating the database of the proposed documentary films on Dormitory System. |  |  | Two films will be produced for documentation and dissemination of cultural heritage on Dormitory System, before it vanishes. | The field work on the remaining communities/ locations is in steady progress to reveal the nature of change of the first decaying institution through documentation activities. Report writing based on the completed field work is going on steadily. |  |  |  |
| (viii) | Narmada Valley Excavation | The extensive excavation in Narmada Valley in search of Palaeo-anthropological materials, before submergence. |  |  | Field camp has been established, 2 research fellow deployed, 2 more research fellows to be appointed. Fellowwork to continue from January 2006. | Deployed research personal/ fellows of the survey had set up a camp at Saha ganj of Dist. Sehore (MP) and carried out excavation work of exploration in Central Narmada Valley during this period. The collected materials are being analyzed in the Paleoanthropological laboratory of the Survey. |  |  |  |
| (ix) | Indigenous Knowledge System | To prepare an inventory of the indigenous knowledge system of different communities of our country. Initially, it may be done from the studies already done by the survey. In the second phase, new areas of fieldwork may be conceived. |  |  | Under the name Study of Intangible Heritage, the survey has already initiated activities in this respect. The WRC, Udaipur has been conceived as the center for implementation of this programme. | The first and the second phase of the documentation work and profiling of medicine man in Gumla Dist. Of Jharkahand is under way on the basis of the field work under taken by the ASI. |  |  |  |
| XX | Nehru Memorial Museum and Library | Responsible for collection of books, newspapers, unpublished references, private papers/ photographs film takes, and also translation of important papers relating to Pundit Jawaharlal Nehru. | 5.50 | 2.60 |  |  | 4.85 | 1.29 |  |
| (i) | Promotion of Research/ Award of Fellowships. | To offer three level of fellowships namely Senior Fellowship, Fellowships and Junior Fellowships and to institute, award scholarships and monitory assistance. |  |  | Working on different research projects and the findings of the fellows/ research papers created by them are being published in the form of monographs. | NMM&L have sanctioned 32 senior fellowship, and Junior fellowship. Out of 32 sanctioned strength 16 fellows are in position for carrying out research on different important subjects. |  |  |  |
| (ii) | Publication Programme | To undertake to promote publication of books, monographs, periodicals and papers incorporating the research of the studies carried out at the NMML. |  |  | To bring out the following publication: Intercommunity Relations in Post Mughal India by Meenakshi Jain; Crises and Creativities Middle Class – Bhadra Loks in Bengal India, 1939-40 by Dr. A.K. Gupta (1951-52; The Role of Khatris in the British takeover of Delhi 1795-1857 by Shama Mitra Chenoy; Scientific Forestry and sustainable management of Forests in India: Myth and Reality by Dr. D.D. Dhangwal and Six monographs. | Besides periodical publications, 2 major publications viz. “Crusade Against Untouchability: Gandhian Movement for Uplift of Harijans in India” and “Cross Currents and Community Networks: The History of the Indian Ocean World” brought out during this period. The 3 new publications are on the verge of completion. |  |  |  |
| (iii) | Seminars and Lectures | To organize lectures, seminars, symposia and conferences to promote and encourage the study of Modern Indian History. |  |  | Proposing to organize four seminars two at the national level and another two at the international level. Tuesday seminars and other lectures will also be organized as usual. | Two days international seminar on “Nature in the Raj: Colonial Environments and Indigenous Knowledge” held in association with JNU and Susex University. About 16 presentations were made by the scholars from India and abroad to facilitate dialogue and debate on the new trends in the environmental history. A special lecture was delivered on ‘Jawahar lal Nehru and Indian Working Class: The pre –Independence Phase’ by Professor Sabyasachi Bhattacharya. |  |  |  |
| (iv) | Oral History Division | To record the reminiscences of eminent persons who have played an important role in national development. |  |  | We propose to interview at least 20 persons in the year 2006-2007 and finalise at least 20 transcripts. | NMM&L was engaged in finalizing about 14 transcripts including those of Tarkeshwari Sinha, Nemi Chand Jain, Bhai Mahavir and Ganga Sharan Sinha. |  |  |  |
| (v) | Acquisition of Library Books, Research Material | To maintain a Library of books, pamphlets, newspapers, periodicals, microfilms, still photographs, motions pictures, sound recording and other materials bearing on the History of Modern India with special reference to the Freedom Movement. |  |  | The Library will continue to acquire books, with a focus on Modern Indian History and related Social Sciences in addition to material on microfilm and photographs. | The Library added about 1500 publications including 9 journals, 200 microfilm rolls and 600 photocopies relating to Pt. Jawahar Lal Nejru and other prominent leaders. The library also completed retro –conversion of the catalogues of the books available into machine readable format, |  |  |  |
| (vi) | Development and Computerisation of Library and other Divisions | To automate the Library and other units of the organisation through computerization. |  |  | We propose to provide 25 personal computers to our Fellows for carrying out their research work and also install LAN for them separately for getting internet facilities. The retro conversion of the library will be completed in this year and it will place the library on par with international libraries. | With a view to providing fast internet service NMM&L instilled broad band internet connection in the library for the benefit of staff and Scholars. |  |  |  |
| (vii) | Development of Museum | To maintain a Museum of Jawaharlal Nehru Personalia, memorabilia, mementos and other objects pertaining to his life and the Indian freedom movement. |  |  | Proposing to mount two temporary exhibitions in the Museum including an exhibition on North East. Maintenance of Museum, replacement of old frames and replacement of tiles etc. | The newly created replica of the Central Hall of Parliament in the Museum was thrown open to the general public and 10 to 17 shows are being conducted for the visitors everyday. The Museum mounted exhibitions on “Lord Buddha through the eyes of jawahar lal Nehru” and “ Bhagat Singh”. |  |  |  |
| (viii) | Replacement of AC System | Preservation and Maintenance of the historical documents and other valuable materials available in the Library, Archives Division and the Reprography Unit. |  |  | The Present Air Condition system has outlived its life and giving us a lot of problem. We propose to install new AC System in our Library building. | Necessary steps are being taken to install a new A/C system in the Library Building. This work has been entrusted to CPWD. |  |  |  |
| (ix) | Nehru Planetarium Activities | We have taken over the Nehru Planetarium in August 2005. This is the only planetarium in the Capital and its programmes stimulate scientific interest among the children. |  |  | The Planetarium sky shows will educate the children. Also many competitions to popularize science will be conducted. | The Nehru PlaPlanetarium launched a fortnightly wall magazine in the name of Krittika. This magazine is now being brought out regularly and distributed to various schools in Delhi. The Planetarium in association with the Russian Centre of Science and Culture organized a seminar-cum-presentation on “Indo-Russian Space Cooperation: History and Perspective” to commemorate the 45th anniversary of Yuri Gagarin’s space flight on 10th April 2006. A photo Exhibitions on solar system update was put up in the foyer area of the Planetarium fo the public. A mini exhibition on the comet 73 P/Swasschman- Watchman was also put up. The Nehru Planetarium conducted a sky watch session with telescopes at Suraj Bhan DAV, School, Vasant Vihar on 5th April. The Planetarium also had interactions and interviews with media relating to its various activities. |  |  |  |
| XXI | Indian Museum, Kolkata | Engaged in reorganization and renovation of galleries housing unique treasures of Indian and foreign art representing centuries of cultural ethos and tradition. | ###### 4.00 | ###### 8.50 |  |  | 2.80 | 3.16 |  |
| (i) | Modernization, development, renovation and upkeep of galleries of art, Archaeology, and Anthropology Sections | The objectives include refurbishing, modernization & renovation of different galleries and reserve collections with updated arrangements and techniques |  |  | (A) Archaeology Section - - Reorganisation & renovation of Coin gallery - Setting up of a new Inscription gallery at the place vacated by Library Unit - Panorama of Indian Architecture from earliest time to medieval period in Eight Bays of the Long Archaeology Gallery - Renovation of Cellar Godown (2nd phase) - Maintenance and upkeep of other 15 galleries (B) Art Section - Renovation of Reorganisation of South-East Asian Art gallery and other galleries coming under the Art Section (15 galleries) (C) Anthropology Section - Renovation of Cultural Anthropology gallery - Setting up of Musical Instruments gallery - Setting up of a gallery of Arms & Weapons of different regions of India from the collection of the Museum - Reorganisation of Paleo- Anthropology gallery (D) Setting up of new “Children’s Corner” (E) Setting up of a gallery on “Glimpses on Art, Archaeology and Anthropology of Bengal” |  |  |  |  |
| (ii) | Strengthening of security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. | To strengthen the security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. |  |  | - Acquisition and maintenance of security gadgets - Upkeep of different electronic devices - Construction of water tank as per recommendation of the State Fire Brigade Department |  |  |  |  |
| (iii) | Programme of Educational and Mass Communication Cultural activities | Programme of Educational and Mass Communication Cultural activities : |  |  | i) Mobile exhibition programmes in different districts of West Bengal. ii)Training programme in Museum studies iii) Holding of National/International Seminar & temporary exhibitions |  |  |  |  |
| (iv) | Modernization and Renovation of the galleries under different Scientific Survey | Modernization and Renovation of the galleries under different Scientific Survey |  |  | The scientific galleries have remained unattended for long due to budgetary and other constraints of the respective surveys. To raise the standard of display and presentation of the scientific galleries and to bring them at par with those of the cultural galleries museum proposes to renovate and update the scientific galleries with the expertise of the respective Surveys |  |  |  |  |
| XII | Salar Jung Museum, Hyderabad | A museum of national importance houses rare and varied art collection from all over the globe acquired by Salar Jung I, II and III. | ###### 4.40 | ###### 7.20 |  |  | 3.04 | 2.70 |  |
| (i) | Developmental works (Existing Building) | Developmental works to the existing building are to be taken up in phased manner |  |  | Roof treatment Strengthening of Compound Wall Replacement of flooring at verandas; Replacement of chokes with electronic equipment Replacement of existing wiring; Provision for 500 KVA Gen. Sets; Cloak area development Fire fighting arrangements Improvements to existing galleries; Misc. works | All the work listed in the column 5 are in progress and shall be completed by the end of this year. |  |  |  |
| (ii) | Re-organisation of galleries | It ahs been planned to take up the Re-organisation & Modernisation of galleries |  |  | Re-organisation of two children Sections, wooden furniture gallery and wooden carvings gallery & certain carry forward works | The work is in progress and shall be completed in all respect by 31st March 2007. |  |  |  |
| (iii) | Reimbursement of cost of CISF | The Security of the Museum has been handed over to CISF from the year 1997. The cost of reimbursements of security by CISF is being included under Plan |  |  | Entire cost of security for one year | The reimbursement for the cost of security by CISF shall be done depending upon the amount of installment in the grant-in-aid as and when received. |  |  | It is required to include in Non-Plan as the security by CISF has become the regular affair. |
| (iv) | Modernization of Stores | Nearly 80% of the objects are in Stores, these objects have to be carefully preserved. Hence the modernisation of Stores is being taken up in phased manner |  |  | Three stores | The modernization of stores for arms and ammunition objects has been completed. The other store-rooms for the textiles is nearing completion. |  |  |  |
| (v) | Library and Manuscripts | Addition of books to the Library and preservation of precious and rare Manuscripts |  |  | Acquisition of 360 books and preservation of existing books | 18 albums of rare collection of photographs have been digitalized. 316 have been added to the library and digitlisation of 18 manuscripts has been completed. |  |  |  |
| (vi) | Cultural and Educational Activities | Conduct of Special Exhibitions, Lectures, Workshops, Seminars and Mobile Exhibition etc. as part of the out reach activities |  |  | 12 Exhibition, 2 Mobile Photo Exhibitions, 12 Gallery talks, 6 Lectures and 3 National workshops on the subjects of Archaeology, Art & Culture apart from regular Educational Activities | Exhibitions titled “Sree Rama” by exhibiting the artifacts of Salarjung collection, “Bharat Ratna Dr. B.R. Ambedkar”, “Naat-e-Rasool”, “Hyderabad – A – Photo Journey” were mounted in the museum displaying unique photographs of yesteryears of Hyderabad and Islamic Heritage. As a part of annual events, summer art camp was organized. In addition to these, various special photo exhibitions, seminars, national workshops were conducted during the period under review. |  |  |  |

| vii) | Computerization of Art Objects | The digital documentation of entire Museum objects, Office automation and procurements of Hardware required |  |  | Digital documentation of 12000 C & D objects | The digital documentation of Museum objects is in progress. So far 24,102 “A” objects and 2541 “AA” objects have been computerized. Other C and D objects are in process so far 7916 objects have been computerized. Necessary hardware and software is being added on need basis for office automation. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| XXIII | Indira Gandhi Rashtriya Manav Sangrahalaya Bhopal | A museum conceived as a growing movement to depict the story of human kind in time and space highlighting human biological and cultural evolution | ###### 1.70 | ###### 4.40 |  |  | 1.17 | 2.95 |  |
| (i) | Maintenance and strengthening of indoor museum with extensive galleries. | Develop infrastructure facilities for achieving the objectives of documentation, display and dissemination of rich and diverse cultural patterns of India through Education and Outreach activities and Operation salvage. |  |  | A: Infrastructure Development Upgrade the visitor facilities in the 200 acre museum campus: expansion of road network, sewerage systems, electrical installations, additional drinking water facility and toilets, children’s park etc. Upgradation of indoor galleries: Indoor museum galleries would be upgraded with additional exhibits and by providing interactive kiosks. Four more galleries will also be developed with thematic presentations of diversified aspects of Indian culture. | Road for handicap persons is widened. Construction of one urinal at main gate, construction of one RCC tank of 1 lakh liter capacity and information centre No.2 near Avritti Bhawan is under progress. Both the works likely to be completed very soon. The work in connection with development of virtual museum is under progress. Galleries are also enriched with audio-video recording displayed through multi-media presentation. |  |  |  |
|  |  |  |  |  | Open air exhibitions to be strengthened with traditional house types from Maharashtra, Orissa, Gujarat, West Bengal and Rajasthan and also from N.E. States. Regional Centre, Mysore to be strengthened with equipments paraphernalia. Strengthening of Archival materials to be made to collect nearly 1000 ethnographic specimens from various communities of India. | The IGRMS campus is surrounded by a series of painted rock shelters, where segment of open-air exhibitions on Tribal habitat, rock art heritage, Himalayan Village, Coastal Village, Desert Village etc., have been developed by adding traditional house of Jatapu Tribe of Andhra Pradesh. Presently work for re-erection of Paliwal house and a Haveli from Rajasthan is continuing as an open-air exhibition |  |  |  |

|  |  |  |  |  | B. Education and outreach programmes to be strengthened by oganising a. A variety of Do and Learn museum education programme with direct involvement of tribal/ folk artists to promote the vanishing aspects of traditional knowledge and technologies. b. Periodical exhibitions in various parts of India. c. Artists camps and workshop. d. seminar/ symposia/ museum popular lectures. e. Performing Art Presentations of classical, folk and tribal performing art forms in India. f. Publications of series on intangible Cultural Heritage of India and other occasional publications/ journal. C. Operation Salvage. Take up collaborative anthropological projects in Himachal Pradesh, Madhya Pradesh, Orissa, Karnataka and North Eastern Staes to ensure recapitulation and recirculation of vanishing or languishing knowledge systems. | The Sangrahalaya has organized five events of do and learn. Five temporary periodical and traveling exhibitions on role of Tribal Youth. Four workshops, nine National seminars and a special programme Sarjana under the theme Saswathi were organized. Brought out five publications, several periodical publications such as newsletters, annual report, brochures, exhibition guide during the period under report. During the year the Sangrahalaya teams toured Chattisgarh, Karnataka, West Bengal, Manipur and Rajasthan and documented lifestyles of different ethnic communities of these states. It has also collected 10018 ethnographic objects associated with the life and culture of these communities; three seminars were also organized on Intangible Cultural Heritage of states like Andhra Pradesh, Orissa, Tamil Nadu. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| XXIV | Other Programmes (Museums) |  | 5.16 | 20.86 |  |  | 3.62 | 16.39 |  |
| a. | National Research Laboratory for Conservation of Cultural Property, Lucknow | To develop the capabilities of different cultural institutions in the country in the conservation of cultural property and provide conservation services to Museum, Archives, Archaeology departments and other similar institutions. | 1.70 | 0.85 |  |  | 1.25 | 0.60 |  |
| (i) | Research Conservation | To develop and standardize better methods of conservation |  |  | 10 projects including 3 continuing projects from the previous year will be undertaken. | The projects “Scientific Examination of Photolam” “Effect of Different Types or Inks on Properties of Paper and Archival Material” and “Physico-chemical Studies on Polymers in Conservation of Stove” are in progress. In case of the project for follow up action of treated site Patiala Fort and Rajasthan monuments, Atrazine not found effective. |  |  |  |

| (ii) | Conservation service | To provide conservation services to different museums, art galleries and related departments |  |  | Conservation of maps and drawings of world heritage site CST, Mumbai. Conservation of objects of 10 museums including 2 defence museums. Objects from other institutions will be attended to for advice and conservation as and when required. | Three projects for Conservation of Artifacts have already been completed and two projects are in progress. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (iii) | Training in conservation | To impart training to conservators, curators and other museum professionals. |  |  | Six months course on conservation of cultural property. Two weeks orientation workshop on care and maintenance of museum objects. Workshop on preventive conservation of ethnographic museums in the north east. | Workshops on preventive conservation, orientation workshop on care and maintenance of music objects organized; six-month course on conservation of art objects, workshop on conservation on manuscripts, Thankas and metal objects and other workshops were also held. |  |  |  |
| (iv) | Regional Conservation Laboratory, Mysore. | To render conservation services in the southern region. Upgradation and setting up of advanced conservation facilities. To undertake research programmes. |  |  | Treatment of carved stone pillars and walls of Sri Sringeswara Swamy temple, Shringeri. Portraits of Maharajas of Mysore at the Lalita Mahal Palace, Mysore. Conservation of Swami Malai Temple, Kollegal. Establishment of facilities for conservation. To start conservation research programmes. | Documentation, recording, diagnostic research and testing of conservation treatment for conservation work on 3 rare books containing 1267 pages completed. About 2000 books were examined, fumigation of 525 books done. Documentation of 80 books for conservation treatment completed. Four months’ training imparted to 3 Project Assistants. National Conservation Conference was organized from 14-16 December 2006. |  |  |  |
| (b) | Victoria Memorial Hall, Kolkata | Museum of contemporary art involved in collecting material and data relevant to a period depicting art history during the freedom struggle. | 2.10 | 6.50 |  |  | 1.47 | 4.55 |  |
| (i) | Preservation, Restoration and Conservation of Art Objects | To preserve the Cultural property of the Nation (Oil painting, Water Colour Aquatints, Miniature, Lithographs, Manuscripts, Coins, Medal, Arms & Armour) |  |  | - Preventive Conservation on 100 paintings from VM collection - Curative restoration/ conservation of 25 paintings from VM collection - Conservation of 12 nos. antique frames Preservation of the third largest printings of the world in collaboration with the experts from GRABER Institute, Moscow | Physical verification of oil paintings was conducted and conservation status was recorded. 115 oil paintings displayed in the gallery. 17 paintings restored and 7 paintings are under restoration. Preventive conservation of Raj Paintings (3 super sized paintings) completed. 11 oil paintings of Tripura State Museum were restored. |  |  |  |

|  |  |  |  |  |  | 10 antiquity frames restored and 2 frames under restoration. 116 objects were conserved under the project of conservation of paper/ metal objects. 214 sheets of Diwan-e-hafiz-© conserved and kept in acid free Solander box for storage. 69 textile objects were conserved under the guidance of Ms. Jenny Lightfoot., U.K. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (ii) | Domestic Exhibition on temporary basis | To familiarize the public at large about the richness of the collections and to communicate our past history, culture and aesthetics |  |  | The world of Emily Eden – exhibition of paintings. | Exhibitions on ‘Exploring India : The Travel of Emily Eden, 1837-1840’ ‘Daniel Oriental Scenery’, ‘Making of Victoria Memorial’, ‘Child’s Right to Expression and Information – Deep Focus’ and ‘Majestic Kolkata (photo exhibition) were held during the period under review. |  |  |  |
|  |  |  |  |  | Exhibition “The Sikhs and the British Raj” |  |  |  |  |
|  |  |  |  |  | Travelling Exhibition Daniells “Oriental Scenery, India: Then and Now” along with Antonio Martenelli at Chhatrapati Shivaji Maharaj Vastu Sangrapahalaya, Mumbai |  |  |  |  |
|  |  |  |  |  | Exhibition of the art work of Abanindranath Tagore |  |  |  |  |
|  |  |  |  |  | International exhibition of Bradman’s Memorabilia |  |  |  |  |
|  |  |  |  |  | From Bibi to Srimoti: An exhibition on Queen Victoria |  |  |  |  |
| (iii) | Publication | To bring out high quality publication and some authentic catalogue on our unique collections of works of European artists and to create awareness of about our culture, history, heritage and aesthetics. |  |  | - Masterpieces of Victoria Memorial. - Catalogue of Arms and Armour - Catalogue on Oil Painting, water colours. - Catalogue on Persian Manuscripts - Reprinting of VM publications. | The preparatory work for publications mentioned in the column 5 are in progress. In addition to this, the special volume on proceeding of the seminar titled “Interrogating the Partition: India, 1947” monograph based on Himalayan Landscape Litho etc by Dr. Sumanta Banerjee, are in progress for bringing out. Sarak Grantha – 1413 was published. |  |  |  |
| (iv) | Strengthening of Security | To safeguard the artifacts and the monument from vandalism and theft and to protect the cultural property |  |  | - Installation of surveillance system and strengthening surveillance. - Installation of barbed wire fencing by single fencing for up to 10’ height (3KM radius) - Deployment of Calcutta Police/ CISF from manning, the 3 gates, Queen’s statues and the main building and the collections kept in the galleries stores and garden spread over 64 acres. | Fire extinguisher installed. Walkie Talkie facilities extended to Security Unit. 14 CCTV camera were installed. Estimates for installation of 12 feet-high barged wire fencing on the perimeter of the wall has been invited from the CPWD. Calcutta Police has been deployed for guarding the campus/ museum and the premises. |  |  |  |

| (v) | Setting up/ Modernisation of galleries including installation | Repair, renovation and modernization of 22 galleries, 6 stores and labs and to bring it to international standard. |  |  | - Installation of electrical wires and luminaries. - Air control system - Fire fighting system - Storage system - 3 new galleries | Modernisation of 72 stores and 74 North Porch rooms and Study collection for oil, paper and metals is under consideration of the Sub-committee of the Trustees for modernization. In this regard, NAD has submitted an estimate of Rs.71.04 crore for modernization of VMH. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (c) | Allahabad Museum, Allahabad | The main activities of the museum include acquisition of art objects, reorganization of galleries and reserves enriching the library and photography unit and publication | 1.06 | 1.20 |  |  | 0.71 | 0.52 |  |
| (i) | Renovation of building | To raise the height of the grill along the boundary wall after estimates for the work received from CPWD are vetted by the Building & Works Committee and to provide storage space, horizontal and vertical stitching in the cracks in the Museum galleries and laying of Kota stone in the Central Courtyard. |  |  | It will strengthen the security of the Museum. Additional space will be created for storage and the courtyard after modernization will give a better look | The flooring of the quadrangle on the ground floor building was replaced with checkered tiles and the old dilapidated storage space therein also got renovated. The work of re-flooring of sculpture gallery with Kota stone has also been carried out in the Museum. |  |  | Progress dependent on timely availability of funds |
| (ii) | Library | To fill up gaps in the number of journals and volumes of sets acquired by the museum, to microfilm certain books and journals which are not available by sending a team consisting of Museum personnel and a hired photographer to places like Mumbai, Kolkata, Delhi, etc. to enrich Museum’s library. | --- |  | It will meet the increasing demand of scholars for availability of latest books on various subjects for their study and research work and also enrich the library | 41 books on different subjects acquired, 250 books were classified and catalogue including there computerization & 8 issues subscribed were received. |  |  | Additional books will be acquired after ensuring that the new books do not already exist in the library. |
| (iii) | Modernisation of galleries | To mount a panorama of 258ivilizations of Middle Ganga Valley and setting up of a new diorama in the Archaeological Gallery to show the advent of man in the Belan Valley. |  |  | Modernization work will be carried out to provide better knowledge of our ancient culture/ heritage | The work on mosaic flooring of Central Hall, conversion of 4 library hall into a permanent air condition. Multipurpose braj Mohana Vyas Auditorium, renovated scultupture stands, exhibition hall, show cases have been carried out during the period under review. |  |  |  |
| (v) | Exhibition and display | It is proposed to mount exhibition on ‘Shiva in Indian Art’ and small exhibitions of budding artists from Central India some of which may also be taken to museums and art centres of the North Eastern Region |  |  | To encourage budding artists of the country and to increase the knowledge of religion and culture of people of North Eastern Region | Photographic Exhibition on “Krishnalila” was organized in the Allahabad Museum and was also taken to Vrindavan and mounted there in collaboration with Vrindavan Research Institute. An Exhibition titled Abhiruchi 2006 was inaugurated in the Exhibition hall of the Museum. |  |  | To improve the standard of the exhibition, modern display stands have been acquired. |
| (vii) | Security surveillance and safety measures | Acquisition of various equipments recommended by the Security Committee for security surveillance and safety of Museum’s objects after receipt of approval of the Ministry of Culture |  |  | To implement the recommendations of the Security Committee, appointed by the Government of India in order to strengthen and security and safety of Museum objects. | To strengthen the security surveillance of the Museum by adopting measures by acquitting various equipments such as close circuit T.V. metal detector, Fire alarm system and fire extinguisher, etc., as recommended by Security Committee. |  |  | This will increase security and safety of the Museum objects and antiquities |
| (d) | National Museum Institute of History of Art, Conservation & Museology, New Delhi | To provide education and training in the specialized areas of art, history, conservation and restoration of artifacts and their display and upkeep in museum. | 0.13 | 2.00 |  |  | 0.09 | 0.96 |  |
| (i) | Academic Programme | Dissemination and advancement of knowledge in the fields of History of Art, Museology and Conservation. |  |  | Conducting of courses by admitting students to M.A. courses (55 seats) and Ph.D. courses (12 seats) as well as running three short terms courses – two in English and one in Hindi (about 200 participants in all). | For dissemination and advancement of knowledge in the field of history of Art, conservation and museology the enrollment of students under MA PHD and short term courses was 30, 1 and 207 students respectively. |  |  |  |
| (ii) | Setting up & 260ealizing260ion of Library | Provide the reference materials (books, journals etc.) and slides for the benefit of faculty, students and the visiting public. |  |  | Books 1000 Slides 6000 | The institute could purchase 4339 slides and 429 books including 74 gifted books. 7 Indian and 28 foreign journals have been subscribed. The website has also been hosted. |  |  |  |
| (iii) | NOIDA Project | Establish its own premises, as, presently it is using the premises of National Museum. This will help in the expansion of the institution in terms of class rooms, library and research facilities, hostels and ultimately help in 261ealizing the goals set for it |  |  | Main & Hostel building up to the first floor | This project is still to be taken up. |  |  | Timely submission of the design and estimates by the CPWD and approval by the SFC, needs to be ensured to avoid time and cost overruns. |
| (iv) | Setting up of Conservation Laboratory | Establish a full-fledged Conservation Laboratory with all necessary equipments of latest technology. This will enable the students to have valuable practical training and also help in advanced research in the field of conservation of cultural property. |  |  | Various equipment like the spectrometers, electron microscopes, etc. and procurement of chemicals. | Some equipments and chemicals which were required for the conservation department were purchased and a temporary laboratory was established in the room over mezzanine floor. |  |  |  |
| (e) | Scheme for financial assistance for ‘Promotion & Strengthening of Regional & Local Museums’ | To promote the strengthening and modernization of existing museums at the regional, state and local level. | --- | 10.00 | Out of about 150 proposals received from the different museums every year, 50 museums receive grant every year. | 62 organizations working in the field of Museum were benefited under the scheme. | - | 9.76 | Release of funds depends upon the number of complete/proper proposals received from different museums |
|  |  | Total (Archaeology, Archives, Museums) | 243.32 | 171.56 |  |  | 204.54 | 137.30 |  |
|  | Public Libraries |  |  |  |  |  |  |  |  |
| XXV | National Library, Kolkata | To serve as a repository of all reading and information materials produced in India as well as abroad concerning India | 14.60 | 6.50 | National Library targets to acquisition 35000 Indian publications and 3500 foreign books. It also intends to digitize 10 lakh pages of old and rare books and retrospective conversion 4 lakhs bibliographical records in digital format. | National Library acquired 20,000 Indian publications/ books and 1500 foreign books. The programmes on digitization and retrospective conversion of records are under consideration of the library and this work will be initiated during this year. | 11.07 | 3.75 | The deposits under the Delivery of Books and Newspapers Act, 1954 depend mainly upon cooperation by publishers |
| XXVI | Delhi Public Library (DPL) | To provide free library and information services to the people of NCT of Delhi and also to provide mobile library services in rural area of Delhi. | 6.50 | 3.00 |  |  | 4.55 | 1.33 |  |
| (i) | Collection Developments | The basic objective of DPL is to provide free library and information services to people of Delhi. In order to achieve this objective, DPL proposes to strengthen its collection development in all the service units. Besides this updating of Reference Collection of Central Library and Sarojini Nagar will also be taken up by acquiring new reading materials. |  |  | Around 4000 titles. | 46728 new books were purchased for the entire system. All new books were transferred to service units. |  |  | Delay in constituting a Book Advisory Committee. |
| (ii) | Conservation and Preservation | Binding care and repair of books and other reading materials are continuous activity of DPL. Preservation of documents is a compulsion in a library for posterity purpose. |  |  | Around 40-50 thousand volumes are to be bound through commercial book binders. | Binders are carrying out the binding work which is in progress. |  |  |  |
| (iii) | Modernization and IT Development | Modernization of library activities is the continuous process of DPL. It is proposed to augment the computer system of library, which requires more computer, server, scanner, operating system, ISM etc. for creating of database in other Indian languages. |  |  | It is proposed to host DPL S website to make wider publicity of library activities. It is further proposed to strengthen the existing computerization activities by way of purchasing of 6 to 10 new computer and other accessories for DB Act a Division, BPPD/ZLS/ Karol Bagh Libraries. | DPL website launched, new computers purchased for automation of library activities. Under modernization the new furniture like racks, card cabinets and other library equipments etc. has been purchased. |  |  |  |
| XXVII | Raja Rammohun Roy Library Foundation | To promote and support public library movements in the country. | 1.90 | 20.00 | Raja Rammohun Roy Library Foundation through their matching schemes intends to assist 9000 libraries to acquire around 3 crore books, 125 libraries with the provision for mobile units, 2500 libraries with storage materials and 150 libraries for construction of library buildings. Under the non-matching schemes, the Foundation intends to give assistance to voluntary organization to set up 330 libraries, assist 364 children libraries or children section of public libraries, procure 1.5 crore books for 469 State Central Libraries and District Libraries etc. | 8570 libraries assisted, the replenishment of 21 million books stock of libraries, 45 libraries provided facilities to the remotest corners, 721 materials provided storage, 80 library buildings constructed under matching schemes. Under Non-matching schemes 145 libraries provided assistance to encourage voluntary zeal for providing library services. 67 children libraries assisted. 469 assisted of state/ district library. | 0.95 | 9.18 | The timely contributions by the State Governments under the matching schemes is have a bearing on finalization purchases |
| XXVIII | National Mission for Manuscripts | Aims at cataloguing, conserving and collecting the invaluable manuscripts from all over the country and to strengthen manuscript resource centers, manuscript conservation centers and digitization of catalogues and prestigious manuscripts. | -- | 13.00 |  |  | - | 7.92 |  |
| (i) | The National Catalogue of Manuscripts a) Creation of National Electronic Data base of Manuscripts | Indian Manuscripts are scattered in known & unknown collections across the country, creations of National data base. |  |  | 10 lakhs Manuscripts will be documented | (a) Total electronic data of 18 lakhs documented out of which 14 lakhs have already been edited. (b) National Survey has been carried out in 16 states. 4 surveys has been carried out in seven states. (c) 20 lakhs manuscripts have been identified and preserved. |  |  |  |
|  | (b)National Survey of Manuscripts and Post Survey Programme | The National survey for manuscripts is held in different states of India to locate manuscripts in every Distt.of the country |  |  | Survey will be done in 300 Distt. Covering 19 state/Union Tertiary. Post |  |  |  |  |
|  | (c) Expansion and strengthening of manuscripts Resource Centres (MRCs | Identifying, documenting, protecting and making accessible the manuscripts heritage of India. |  |  | 15 lakhs Manuscripts will be identified. |  |  |  |  |
| (ii) | Documentation through Digitization. (a) Digitization of portions of collection at 50 Institutions | The Mission is planning to digitize 500 important manuscripts each in 50 prominent institutions/repositories in India. |  |  | 25,000 manuscripts will be digitized. | (a) The work is under progress. (b) The pilot project for digitization of manuscripts completed in Kerala, Orissa, Tamilnadu and Kashmir. Work of NCC vol. is in progress. |  |  |  |
|  | (b) Pilot Project on Digitization. | As a means to documents and protect knowledge contained in manuscripts collection in India and for enhancing their preservation and accessibility. This long term project has resulted in several caches of manuscripts being available in digitized form. The Mission aims to safeguard the knowledge contained in manuscripts by developing a consists policy for digitization. |  |  | 12,000 Manuscripts will be digitized |  |  |  |  |
| XXIX | Other Libraries | To assist selected heritage and other libraries in their areas of specialization. | 4.60 | 5.92 | These Libraries would continue to function under the specified areas in which they function. These include Central Reference Library (CRL), Kolkata, State Central Library, Mumbai, Khuda Baksh Orientral Public Library, Patna, Rampur Raza Library, Rampur, Thanjavur Maharaja Serfoji’s Saraswati Mahal Library (TMSSML), Thanjavur and Connemara Public Library, Chennai | CRL: The manuscript of Index Indiana 1999 – 2003 has been sent to the press. Compilation of Annual vol. of INB 2006 completed. The Publication of Indian National Bibliography, Annual vol. 2005 completed in all respect and sent to press. The State Central Library, Mumbai and Connemera Public Library, Chennai continue to receive Central Grant in aid for their ongoing activities. Khuda Baksh Oriental Public Library: 5000 books and manuscripts acquired retrospective cataloguing and classification of 60,000 books/ periodicals. Publication of 20 books. Rampur Raza Library: has published 2 books out of 6 targeted. The documentation work of rate manuscripts and paintings of the Library have been carried out and is near completion. 26 personals of CISF deployed under the security of the library. About 11000 folios have been digitized. TMSSML: 56 books (39 reprints + 70 new books) of multilingual published, 734 manuscripts microfilm, 18156 zerox copies of reference manuscripts/ books made. | 2.67 | 11.27 | The deposits under the Delivery of Books and Newspapers Act, 1954 depend mainly upon cooperation by publishers |
|  |  | Total (Public Libraries) | 27.60 | 48.42 |  |  | 19.24 | 25.53 |  |
| XXX | Provision for Project/ schemes of N.E. Region and Sikkim |  |  |  |  |  |  |  |  |
| a | Project/ Schemes for promotion of Art and Culture | To promote, disseminate and protection of art and culture in NE States | -- | 16.00 | Organizing various programmes in the field of art and culture in various cities of the North Eastern States. | Various programmes / activities relating to dance, drama and theatre, folk art, and cultural allied fields were organized through National Akademies, CCRT, GSDS and also benefited cultural organizations/ NGOs through the Central Departmental schemes. |  | 6.42* |  |
| b | Archaeology, Archives and Museums | To promote cultural activities in the fields of Archaeology, Archives and Museums | -- | 26.62 | Development of Museums in North East Region and providing financial support to NGOs in N E R in the field of Archival activities. | Maintained monuments/ sites located in NER, in Guwahati circle of ASI. Promotional activities in the filed of Museum and Archives were conducted and also benefited, NGOs / individuals in the respective fields |  | 2.04* |  |
| c | Libraries | To promote Library activities in the NER | -- | 4.38 | Development of Library activities in North East Region. | Promoted and supported library movement in the NER by providing assistance to various libraries in the rural and urban areas. |  | 1.29* |  |
|  |  | Total ( provision for NER) | -- | 47.00 |  |  |  | 9.75 |  |
| *included under individual scheme / organization |  |  |  |  |  |  |  |  |  |
|  |  | TOTAL (Revenue) | 350.00 | 422.00 |  |  | 257.31 | 232.69 |  |
|  | Building projects of attached / subordinate offices |  |  |  |  |  |  |  |  |
| 1. | National Gallery of Modern Art | (i) Extension wing of NGMA, New Delhi |  | 10.00 | Work is under progress |  | - | 4.32 |  |
|  |  | (ii) NGMA, Bangalore |  |  | Capacity creation for the galleries. |  |  |  |  |
| 2. | National Archives of India |  |  | 5.00 |  |  | - | 1.98 |  |
|  | (i) | Construction of service block |  |  | Work is under progress | Creation of additional office accommodation and storage for records. |  |  |  |
|  | (ii) | Completion of remaining works such as Air Conditioned Plant |  |  |  |  |  |  |  |
|  | (iii) | Construction of functional building of record center, Bhubaneswar |  |  |  |  |  |  |  |
|  | (iv) | Proposal for acquiring 0.21 hectares of land adjacent to Record Centre, Pondicherry. |  |  |  |  |  |  |  |
|  | (v) | Addition and alteration of works of NAI Main/ Annexe building, Record Centre Jaipur and Pondicherry and Regional Office Bhopal. |  |  |  |  |  |  |  |
| 3. | Anthropological Survey of India |  |  | 15.00 |  |  | - | 7.66 |  |
|  | (i) | Construction of Office building of Eastern Regional Centre at Salt Lake, Kolkata |  |  | Work is under progress | Creation of additional office accommodation. |  |  |  |
|  | (ii) | Construction of Office Building at Head Office and Museum building under Phase II and phase III. |  |  |  |  |  |  |  |
|  | (iii) | Construction of residential quarters and guest house of International Standard etc. at Udaipur |  |  |  |  |  |  |  |
|  | (iv) | Construction of Guest House Library, Museum and Conference Hall of North East Regional Centre at Shillong. |  |  |  |  |  |  |  |
|  | (v) | Construction of residential quarters and guest house of North West Regional Centre, Dehra Dun. |  |  |  |  |  |  |  |
|  | (vi) | Construction of an International standard guest house NA ancient lab. At the SRC, Mysore. |  |  | Work is under progress |  |  |  |  |
|  | (vii) | Acquisition of land for Construction for Office Building of the SRC, Jagdalpur and Ranchi Fiedid station |  |  | Work is under progress |  |  |  |  |
| 4. | National Research Laboratory for Conservation of Cultural Property, Lucknow | i. Hotel cum guest house and residential quarters at Lucknow. ii. Remaining construction work of Regional Conservation Laboratory, Mysore |  | 1.00 | Work is under progress | Accommodation problem of NRLCCP, Lucknow addressed. | 0.00 | 0.75 | Completion of works depends on the efficiency of CPWD. |
| 5. | National Museum |  |  |  |  |  |  |  |  |
|  | (I) | Shifting of Air condition plant etc from National Museum campus etc. and Dismantling of ASI structure and start of construction of III Phase of National Museum Building. |  | 2.50 | Work still to be taken up. | Infrastructure development and capacity creation for National Museum. |  | 1.31 |  |
| 6. | National Library | Construction of readers’ hostel |  | 0.50 | Work still to be taken up. |  | - | 0.07 |  |
| 7. | Archaeological Survey of India | Construction of building and staff quarters for ASI at Dharwad, office building at Nagpur, Mysore, construction of Institute of Archaeology at Greater Noida, linear building at 24, Tilak Marg, New Delhi. |  | 14.00 | Work is under progress | Accommodation problem of ASI staff shall be solved. | - | 4.72 |  |
|  |  | Total (Building Projects) |  | 48.00 |  |  |  | 20.89 |  |
|  |  | Grand Total (Art and Culture) | 350.00 | 470.00 |  |  | 257.31 | 253.49 |  |