| 1. | a. Secretariat Social Service | To modernize the accommodation for efficient functioning of the Ministry and also provide information technology support. Maintenance of the office equipments and procurement of stationery. | 13.60 (a+b) | 3.00 (a+b) | Modernization of about 10 rooms in the ministry, Providing Web based delivery of the services and information of the ministry. Training of the employees of the Ministry in IT related areas and to upgrade LAN. | To provide modern and computer facilities to the staff of the Ministry of Culture. | Continuous process for the entire year. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | b. Central Secretariat Library (CSL) | To provide information and research services to Academicians, Research Scholars and Policy Planners. It is the main reference library for all purposes. |  |  | To strengthen the reference and referral services of CSL. Conservation of 6000 thousand rare books. Renovation of main Reading Hall. Installation of RFID system in CSL. Acquisition of Micro Film rolls of Indian official documents. | Enhancement of readership and dissemination of knowledge. Providing proper maintenance of books in the Library. | Continuous process for the entire year. |  |
| 2. | Zonal Cultural Centre | Aims at the promotion of Grassroot Culture and Cultural Kinships which transcend territorial boundaries and to arouse and deepen awareness of local culture. | -- | 13.00 |  |  |  | Includes 30% provision towards pro-women, and 20% provision for ST allocation. |
| (i) | National Culture Exchange Programme | Exchange of artists, Musicians, performers, & sculptors etc. between different regions within the country for the promotion of rich cultural heritage of India. |  |  | About 700 programmes would be organized benefiting a large number of artists. | Strengthen and promote National Integration and preserve, promote and disseminate folk art forms. | The artists would be exchanged as per requirement from time to time |  |
| (ii) | Documentation | Documentation of various folk & tribal art forms particularly the vanishing art forms for their proper preservation. |  |  | Various folk & tribal art forms, great masters of member states will be documented as per advice of Programme Committee and research oriented projects would be taken in hand for publication | Preservation of folk traditions and possible creation of IPRs (Intellectual Property Rights) | Being a continuous – process, the time taken in the completion of project is extendable. |  |
| (iii) | Lok Tarang Folk Dance Festival 2008 | This festival is organized for Republic Day Celebrations during January each year for the promotion of our rich cultural heritage & national integration |  |  | This festival provides a unique performance opportunity for the folk artists from various parts of country at the national level. Besides this a large number of school children participate in R.D. Parade | Increased awareness of regional cultural traditions showcased at a National Level. | Celebrated in the month of January every year |  |
| (iv) | Kurukshetra Utsav | Celebrated on the occasion of Geeta Jayanti Samaroh at Kurukshetra-a Sacred place related to Mahabharta |  |  | Very suitable occasion for the promotion of Indian art & culture. Classical & folk artists perform benefiting large number of people. Besides this a large number of craft persons are given opportunity to display & sell their products | Synergise performing arts and crafts traditions. Impetus to local crafts. | Regular feature |  |
| (v) | Guru Shishya Parampara | For the promotion & preservation of our Fast vanishing art Forms |  |  | Not only Gurus but shishyas are also benefited. About 100 gurus with 500 shishyas are likely to be benefited during the year. Art forms are decided in Consultation with State Governments from time to time. | Strengthening Guru Sishya Parampara. | It is a continuous process involving extension in time period. |  |
| (vi) | Theatre Rejuvenation | Providing an opportunity to the theatre artists to stage plays & other theatre activities. Also interacting with each other on the Common platform |  |  | About 100 theatre groups would stage their plays and more than 1000 artists and a large number of people would be benefited in promoting the theatre. Workshops to promote theatrical skills will also be held. | Give an impetus to folk and traditions theatre. | Theatre organizations would be invited for theatrical performances from time to time |  |
| (vii) | Crafts Mela | For promotion of crafts persons to demonstrate their skills & to sell their artifacts |  |  | About 1000 craft persons from various parts of the country would participate attracting large number of people | Fillip to craft industry | Craft persons would be invited and crafts fair would be organized in coordination with Ministry of Handicrafts & Handlooms, Govt. of India & other organisations |  |
| (viii) | Young Talent Scheme | To recognize & encourage young Talented artists in various folk Art forms |  |  | About 100 folk art forms would be selected & competitions would be held involving sufficient number of upcoming artists & public. | Youth involved in folk traditions encouraged. | An advertisement would be given in the newspapers & other cultural & educational institutions would be contracted. |  |
| (ix) | Shilpgram | Shilpgrams established by ZCCs are playing very significant role for the promotion & preservation of Indian Art & Culture and providing platform to the talented artisans. The main objective is to boost the activities in Shilpgram/ Kalagram |  |  | A large number of artists & artisans are benefited. A large number of people are made aware of our rich cultural heritage. | Artisans benefited; urban population made more aware of traditional crafts. | All the year around various types of cultural activities are undertaken |  |
| (x) | Festival of the North East - OCTAVE | The objective of the proposed festival of the North East is to help the people in general and artists from the North East in particular to have a closer interaction with the rest of the country. |  |  | Around 500 artistes from North East including folk artistes, musicians, film & literary personalities etc. will be performing in this Annual event. | To showcase the colorful and vibrant art and culture of the N.E. Region to audiences. | January-March, 2008 |  |
| 3. | Sangeet Natak Akademi, New Delhi | The Academy devotes to the furtherance of the performing arts of India, and seeks to achieve this by arranging performances by renowned veterans as well as by talented artists of the younger generations through training programmes, award of scholarships and documentations. | 5.90 | 10.50 |  |  |  |  |
| (i) | Survey, Research, Documentation & Dissemination and Publication | Preservation and collection of recordings of rare traditions of Performing Arts, development of theoretical and academic knowledge of performing arts and publishing literature on performing arts. |  |  | 200 hrs of audio and video recordings, survey of performing arts of 5 states, release of 20 audio CDs, 10 video CDs, and 500 photographs, 50 hrs of audio and video dubbing. | Expansion of data base on performing arts, Development of scholarship and encouragement to young scholars, greater availability of information and literature to enable policy formulation and planning of practical application by students, teachers and artists. | These are ongoing programmes and will be held through out the year 2007-08 |  |
|  |  |  |  |  | Two regional seminars and one national conference, 10 books, 4 journals and 12 news bulletins, 1 Annual Report and 50 monographs. Engagement of 5 scholars for encyclopedia on performing arts. |  |  |  |

| (ii) | National Museum of Performing Arts, Library and Archive | Development of Academe’s existing museum musical instruments, puppets, masks and other art objects into a national level museum of performing arts by acquiring a separate building / campus. To develop an exclusive archive of audio video and photographic records of performing arts of India including a parallel archive in South India by acquiring rare collections scattered in the country and expansion of Akademi’s existing specialized library. |  |  | Acquisition of 2 acres of land, engagement of 6 project staff, preparation of 3 catalogues of existing collection, acquisition of 100 objects, organization of 3 workshops on restoration. Digitization of 500 hrs of existing archival holdings – acquisition of specialized equipment and project trained staff. Digitalization of 1000 books, computerizing access for Library information facilities. | Preservation of intangible form (the wealth of Indian performing arts developing and integrated system of information and knowledge about this wealth by combining the facilities of Museum, archives and Library). | These are ongoing programmes and will be held through out the year 2007-08 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

| (iii) | National Institutes and Centres of Akademi for Specialized fields/ forms of India : Kathak Kendra, New Delhi, Kutiyattam Centre, Kerala, Chhau Centre, Baripada / Jamshedpur, Other National Projects, Jawaharlal Nehru Manipur Dance Academy, Imphal and Sattriya Centre, Guwahati | To create Kathak dancers of professional standing through well specialized training course, To upgrade and develop Akademi’s project support to Kutiyattam, Upgradation and development of the ongoing project support to Chhau Dances of Eastern region, Development of training programmes in traditional land folk theatre forms of India - Yakshagana of Karnataka, Bhagwat Mela of Tamilnadu, To create Manipuri dancers of professional standing through well specialized training course, Development of Akademi project support to Sattriya Dance and allied music and theatre traditions. |  |  | 3-4 new production of dance drama in a year, platforms to about 200 artistes and creating new audience for Kathak in the country. The ongoing project of Kutiyattam involving a number of projects training, production, research and performance directly benefiting about 400 artistes and scholars in urban and semi-urban areas. | To create the awareness of traditional dances and music among the masses and benefit to the artists (dancers and musicians) in their respective fields. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | The ongoing project of Support to Chhau Dances involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. 3-4 new productions of dance dramas in a year, platforms to about 200 artistes and creating new audience for Manipuri dance in the country The ongoing project on Sattriya Dance involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. |  |  |  |
| (iv) | Training and Perform Support: Training and Preservation of traditional Folk & Tribal Performing Arts Sponsorship and promotion of young artists Assistance to Young Theatre Workers Promotion and preservation of puppetry | To support different forms of music, dance and theatre, encourage young members of the traditional arts, support to such forms, style, traditions, gharanas etc. that are threatened by change. To identify and promote talented young artistes of the country in dance and music and to subsidies and create new audiences. To support experimental works by young theatre directors, production of new plays, training for young theatre workers, upgrading standards in different regions. . |  |  | Training programme including 100 artistes Four festivals of young musicians and four festivals of young dancers in North, South, East and West Zones, two festival for North Zone. Workshop for Young Theatre artistes for different zones Monthly performances of puppetry and interaction programme in Delhi, financial assistance to almost 30 institutions, national and international exhibition of puppets and associated musical instruments, four training programmes in Rajasthani Kathputali making and manipulating | Participants in the workshop would create a movement for motivating other children to participate in theatre activities. 100 students would be trained in lighting, stagecraft etc. This new initiative would lead to creating job orientation for new generation. |  |  |
|  | Assistance and support to Contemporary and Experimental Works on Music, Dance, and Theatre Support to Children's Theatre (New Scheme) Certificate courses in identified areas of performing arts (New Scheme) | To provide to assistance and development of traditional and contemporary puppet theatre, preserve the richest heritage of puppetry in the world To support a contemporary expression and idiom of Indian dance and new compositions of experimental music and production of experimental theatre. To create cultural space for children’s theatre which appears to be shrinking. The aim is to intervene through launching a scheme for supporting activities in the domain of children theatre. Certificate Course : Objective : To provide quality training in identified areas such as lighting, stage craft, choreography and choral singing, conservation and management of performing art heritage. |  |  | The workshop and festival of contemporary choreographers / composers / experimental works in theatre, financial assistance and individuals.. 2-3 workshops for children will be held in different parts of the country for the participants of the age group of 8-15 years. |  |  |  |

| (v) | 1. Grants to voluntary cultural institutions 2. Project Grants to Individuals 3. Grants for Academic Research in Performing Arts 4. Publication Grants | Support to Voluntary institutions nationwide for common goal of promotion of arts. To promote scholarship and public awareness in the field of Indian music, dance and theatre. |  |  | Over 500 cultural organizations will be supported with financial assistance. | Sustains of artistic contribution at local level in urban and rural area. | Through out the year. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (vi) | Festivals, Workshops and National Exhibitions 1. SNA Festivals, Workshops & Exhibitions 2. Collaborative Programmes with State Akademis, Organizations, Central Govt. Organizations & Major Cultural Institutions and Sponsored Programme (New Scheme) | To preserve, promote and development of performing arts traditions in live practice on regional and national levels and support exchange of ideas, concepts and techniques nationwide. |  |  | - Lok Utsav – National Festival of Folk and Traditional arts - Theatre Festival and Seminar - National Festival of Andhra Dance Tradition and Seminar - Rang Sangam Festival of Theatre - Nritya Sangam Festival of Dance - Sangeet Sangam Festival of Music - Festival & Seminar on Theatre Music | Promotion and Dissemination of music, dance and drama through these seminars and festivals | These are ongoing programmes and will be held through out the year 2007-08. |  |
|  | 3. Regular Programme in Meghdoot Theatre Complex |  |  |  | - Regional level celebration of Music Day, Dance Day & Theatre Day. - Two regional seminars on folklore. |  |  |  |
| (vii) | Awards, Honours and Prizes : SNA Fellowships and Awards (Akademi Ratna Sadasyata and Puraskar) Yuva Puraskar (New Scheme) | To recognize excellence and sustained contribution in performing arts and support eminent old artists. A new scheme i.e. Yuva Puraskar in the name of Ustad Bismillah Khan has been constituted for the young artists of less than 35 years old. |  |  | 33 Awards and 5 Fellowships Mediclaim insurance for 350 Awardees and Fellows. 33 Awards to young artists. | National honour to artists for further promoting their performing arts. National recognition to young artists. |  |  |
| (viii) | # Cultural Exchange Programmes # 1. Inter - State Cultural Exchange Programme 2. Indo-Asian Cultural Exchange Programme (New Schemes) | National Integration through cultural exchanges |  |  | 15 exchanges involving 30 States/UTs | It will create national integration and develop better relations with the other countries. |  |  |
|  | 3. Indo-Foreign Cultural Exchange Programme | The Government of India concludes cultural exchange programme with various countries to have better understanding with each other cultural heritage. |  |  | Cultural Exchange Programmes finalizing between Government of India and with other countries. Purpose of exchange undertaken have resulted in high appreciation of Indian Performing Art tradition and also halt improvement diplomatic relations. |  |  |  |

|  | 4. Bi-annual International Cultural Festival # (New Schemes) |  | On the line of trienalle held by Lalit Kala Akademi it has been decided to hold international festival of performing arts with the objectives to create better understanding with cultural institutions in India and abroad and to create opportunity for interactions and exchanges to ideas. |  |  | The festival will develop as a major window to showcase the best of Indian performing arts tradition for foreign visitors and festival directors thus promoting them at international level. The events may also develop as a major attention for cultural tourists. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ix | Infrastructure and Development Activities 1. Meghdoot Theatre Complex |  | To maintain Open Air Theatre, Exhibition Gallery and temporary office |  |  | Megthdoot Theatre is one of its kinds in the heart of Delhi. It attracts substantial crowd in programmes organized by the Akademi. |  |  |  |
|  | 2. Rabindra Rangashala, N.D. |  | Maintenance of Rabindra Rangashala, New Delhi |  |  | Building will be constructed for Kathak Kendra Campus in Chanakyapuri. |  |  |  |
|  | 3. New Campus for Kathak Kendra, N.D. (Capital Component) |  | To construct a building for Kathak Kendra at Chanakyapuri, New Delhi |  |  | Help the support structure of 3 Akademies |  |  |  |
|  | 4. Development of Rabindra Bhavan Facilities |  | Improvement in Rabindra Bhavan facilities by joints services of the Complex. |  |  |  |  |  |  |
|  | 5. Setting up of regional Centres of the Akademi (New Schemes) |  | Regional Centres of the Akademi has been proposed keeping in view to make the Akademi's work more assessable to artists, working in different regions and to coordinate activities successfully in the regions. |  |  | To regional centres set up proposed one South in Hyderabad one in Kolkata | Regional Centres serve as activities centre of the Akademi. |  |  |
|  | 6. New Campus for JNMDA, Imphal(Capital Component) |  | New campus of JNMDA - to construct a new building of JNMDA at Imphal, Manipur |  |  | Building will be constructed by the JNMDA and land to be given by the State Govt |  |  |  |
|  | 7. Setting up North East Centre of Sangeet Natak Akademi. |  |  |  |  |  |  |  |  |
| x | # Promotion of Performing Art through Media & Information Technology |  |  |  |  |  |  |  |  |
|  | 1. Computerization & Website |  | Technical upgradation of computers technology and website |  |  | To put performing art on website | Data Performing art may available on website. | It will help in spreading information on performing arts on website. |  |
|  | # 2. Promotion Activity through Media (New Scheme) |  | Promotion of performing art tradition of India by utilizing the electronic media. |  |  |  | Programmes and compilation of Akademi, Archives are to be telecast on regular basis. | Writers in the printing media shall be engaged to write and spread awareness about rare tradition column and features in newspapers and journals |  |
| 4. | Lalit Kala Akademi |  | Promotion of visual and plastic arts | 4.10 | 5.50 |  | Propagation and popularization of interstate music, dance and drama |  |  |
| (i) | Promotional activities in the field of visual & plastic art. Art Development |  | The main objectives of the Academy are to provide infrastructural facilities to the artist’s community for the development of art activities of the country especially in the field of contemporary art. |  |  | Exhibitions: (Resonance, National, Outgoing, Incoming & Regional Art) – 14 Delegates: visiting India from abroad - 4 Delegates: visits to abroad – 12 Camps & workshops at National - 4 Regional - 1 | People engaged in the field of Lalit Kala will be benefited and awareness to mass by organizing programmes with the State Akademis and the ZCCs. | Throughout the year. | The Akademi proposed to built two Regional Centre one each in Kolkata and Shillong. Negotiation with the respective State Govt. is at final stage. |
|  | Com. Dissmn Outgoing Exh,. National Exh. Triennale Archives Lectures & Film Camps Library Cons & Restn. Grants to State Akademis. Regional Centres Scholarships |  |  |  |  | Scholarships - 40 Fellowship - 1 Memorial Lectures/ Workshops - 54 Art Publications Portfolios - 2 Journals(Hindi/English)– 4/3 Artist Directory - 1 Regional Journals - 3 Reproductions - 5 Art Books - 3 Art Festival in North East – 1 North East Festivals in other cities - 1 | . Promotion of visual and plastic arts, camps & workshops at National and regional level, providing scholarships, Fellowships, arranging Memorial Lectures/ workshops and bringing out the Art Publication |  |  |
| 5. | Sahitya Akademi |  | To undertake publishing & promoting Indian literature | 4.00 | 9.75 |  |  |  |  |
| (i) | Upgradation of Libraries and Information Services |  | To provide readers/ intellectuals the complete range of books and update basic information about writers and literary activities in India at one place, make documentary tele films on eminent writers and scholars in the field of literature with modern archive unit of visuals. |  |  | Purchase of books in 24 languages. Subscription and New journals to be added. Upgradation of the Akademi’s web site and Hindi web site will be launched. Ten Documentary films on writers will be made. | Dissemination of the literary activities in India Scholars and other users shall be benefited by Akademi’s website. | It is an ongoing scheme and targets will be achieved on quarterly basis. |  |
| (ii) | ### Publication Schemes |  | The scheme to full fill the basic objective of the Akademi dissemination of Indian Literature and making available to multilingual societies of Indian Literary masterpieces from other language into their own language, histories of literature, monographs on Indian Writers, translation of important Indian and foreign classics, anthologies of poetry, short-stories, one-act plays, literary essays etc. |  |  | It is proposed to publish around 300 books in all the 24 languages recognised by the Akademi. The publication of bi-monthly journals Samkaleen Bharatiya Sahitya (Hindi) and Indian Literature (English) and a half yearly journal Sanskrit Pratibha (Sanskrit) to continue. | Propagation and dissemination of literature of various regional Indian languages. Scholars in a multilingual society benefited. | It is an ongoing scheme and will executed in a schedule manner to achieve the targets. |  |
| (iii) | Modernisation and improvement of administrative functioning |  | To keep pace with the improved technology of the modern electronic age. |  |  | The computerisation in the Akademi will be upgraded. The accommodation at New Delhi, Mumbai, Kolkata, Chennai and Bangalore on hire will continue. The interior of the Regional Office Kolkata office premises being purchased from Municipal Corporation Kolkata will be done. | Scholars will be benefited by modern technological innovations in management. | It is an ongoing scheme and shall be implemented according to release of funds by the Ministry |  |
| (iv) | Literary functions and programme |  | To celebrate centenaries of great writers, hold regional, national and international seminars, writers camps, workshops, symposiums etc., provide writers a forum for their periodical gathering by organizing meet the author, men and books, Kavi Sandhi, Asmita for women writers, Katha Sandhi, Kavya Bharati, Mulakat, Samvad, Kavya Sandhya and Antral etc. |  |  | Around 35 Seminars including international seminars, Literary Forums, Men and Books, Katha Sandhi, Kavi Sandhi, Avishkar, Meet the Author, Through My Window, Asmita, Mulakat, Samvad, Book Release Functions and Sur Sahitya etc. | Promotion of literary arts of great writers by celebrating their centenaries | It is an ongoing scheme and programmes will be held as per the recommen-dation of the committees |  |
| (v) | Awards to writers |  | To enable young and old writers in Indian language to visit other parts than their own, send Indian writers and host foreign writer delegation under Cultural Exchange Programmes, to give award to literary works which merit appreciation and encouragement in all 24 Indian languages recognized by the Akademi, give honorary fellowships to eminent writers in recognition of their contribution to Indian Literature. |  |  | Around 50 young writers to avail the Travel Grant scheme of the Akademi. The Akademi will participate in different Cultural Exchange Programmes including new ones as per the decision of the Government of India or on reciprocal basis. The Annual Awards will be given to writers in 24 Indian languages recognized by the Akademi. To conduct meetings of the 24 language advisory boards besides other committees. | Young and old writers in Indian language shall be benefited by providing travel grant through this scheme | It is an ongoing scheme and will continue as per the yearly schedule |  |
| (vi) | Promotion of sale of academi publication, advertisement publicity and book exhibitions |  | To advertise Akademi publications through literary journals, organize and participate in book exhibitions at regional, national and international level. |  |  | The Akademi will participate in around 90 book exhibitions at National/ Regional / International (Lahore / Frankfurt) levels. The Akademi proposes the sales target around Rs.250 lakhs for the year 2007-08 The target is to be achieved by participating in various book exhibitions at national/ regional levels. | Promoting and disseminating latest books of renowned writers from various states and countries through book organizing book exhibitions | It is an ongoing scheme. |  |
| (vii) | ##### Translation schemes |  | Translation is the basic activity of the Akademi. The translation centre “SABDANA” will be strengthen to make arrangements for training of translators and train the practicing translators by conducting workshops, to do the inter-lingual research and translation, prepare a register of translators and identify titles for translations and their publications into other Indian languages and into foreign languages. It is proposed to establish a few more Translation Centers on the lines of SABDANA. |  |  | The Translation Prizes in 24 languages recognized by the Akademi will continue. The Translation Centers at Bangalore and Kolkata are likely to publish more than ten books in regional languages and English. Besides publication by the Translation Center will continue by translating important books in various Indian languages and vise-versa. The Centers will conduct Translation Workshops in languages recognized by the Akademi as well as un-recognised languages to strengthen the translation activities. New Translation Centers will be launched in Western and Northern regions. | Literary art of different regional languages and English through translation scheme promoted. It will raise the tempo and standard of literary translation activity, promote national integration, overcoming linguistic barriers by giving prize for best translation in 24 languages recognized by the Akademi. | It is an ongoing scheme and will be executed as per the approval of the advisory boards. |  |
| (viii) | REGIONAL LITERATURE STUDY PROJECT |  | To strengthen the inter-regional studies as also comparative studies with one linguistic group of language and literatures to another by the Regional Boards. The scheme envisages conducting workshops, seminars and writers meet at regional and national level. To bring out the revised editions of Modern Indian Literature, Medieval Indian Literature and Ancient Indian Literature. |  |  | Meetings of all the four Regional Boards will be held as per schedule. The work on printing of works shall be taken up. Recommended seminars / workshops will be held | Meetings of all the four Regional Boards will be held as per schedule. The work on printing of works shall be taken up. Recommended seminars/ workshops will be held. | It is an ongoing and scheme will continue |  |
| (ix) | NEW SCHEMES CONSTRUCTION OF OFFICE BUILDING ON A PLOT OF LAND ALLOTED BY DDA |  | To have a permanent office building at DDA allotted land. |  |  | A Office Building cum Sales Godown will be constructed on the land bought from Delhi Development Authority. The basement will have the godown and the first floor will house the office. The second floor will have four rooms on the second floor. | The Akademi would be able to save Rs.40 Lakhs annually. | After completion of formalities. |  |
| (x) | A GOLDEN JUBILEE MULTIPLEX |  | To develop the Meghdoot Open Air Theatre into a multiplex to mark the Golden Jubilee of the three sister Akademies, the Sahitya Akademi, Lalit Kala Akademi and the Sangeet Natak Akademi to be named ‘The Golden Jubilee Multiplex’. |  |  | The multiplex will have an auditorium, conference room, guest’s rooms and display lounge etc. with modern amenities. The project will be implemented through the Sahitya Akademi which is the nodal agency for the upkeep of Rabindra Bhavan Complex also. | For providing larger scope for organizing various programmes relating to promotion of Art & Cultures through the National Akademies. |  |  |
| 6. |  | Festival of India | To organize major cultural festivals in selected foreign countries for achieving better understanding and cooperation | 4.00 | -- | To hold “India Week” in Brazil. Organization of “ Festival of India” in United Kingdom is under process. | Awareness about the cultural richness of India created opportunities to Indian artists in these countries provided. | Through out the year. |  |
| 7. |  | Indira Gandhi National Centre for the Arts (IGNCA) | IGNCA was established to commemorate the memory of the Former Prime Minister Late Smt. Indira Gandhi. It and envisioned as a centre for research, academic pursuit and dissemination in the field of the arts. | -- | 45.00 |  |  |  |  |
|  |  | Construction of Buildings | Completion of two buildings and construction of concert hall. |  |  | (i) Completion of Kalanidhi-Kalakosha Building in all respect. (ii) Foundation work in Sutradhara Building. (iii) Preparation of estimates, architectural drawings and obtaining clearances for the Concert Hall. | Full operationalisation of the Kalanidhi-Kalakosha Building including guest house block. | (i) One year for Kalanidhi-Kalakosha building (ii) 2 years for Sutradhara building (iii) One year for pre-construction work on Concert Hall. | (i) Timely release of funds and sanctions (ii) Timely permissions for statutory bodies for the Concert Hall. |

|  | Promotion of Multidisciplinary Research and Critical Dialogue among diverse Arts. | Enlarge its programme of research and publication of fundamental texts, reference works, glossaries, dictionaries, encyclopedia, comparative history of Indian arts, thesaurus of fundamental terms, inter-dialect and inter-disciplinary glossaries and dictionaries, explore relationship of arts and science, dimensions and explore relationship between arts of India and the world, special focus on the North-East and its cultural dimensions. |  |  | Studies on the following dimensions: (a) Multiple levels of identity and their manifestation in Arts (b) Language and Cultural Diversity (c) Wisdom Tradition, Ecology, Resource Management and Sustainable Development (d) Religious Identities, Confluence of Traditions and composite Cultures (e) Inter-Cultural Dialogue (f) Contribution of Women to Indian Art and Cutlure. | (a) Publication of critical editions of fundamental texts, monographs on tribal and folk culture, republication of texts by eminent scholars (b) Research and field studies. (c) Audio-video documentation (d) Conference, seminars and workshops (e) Exhibition and multi-media events (f) Production of films, CDs, audio-video recordings. | (i) Research and Field study – 1st and 2nd Quarter (ii) Pre-publication work, documentation – 2nd and 3rd Quarter (iii) Publication, audio-video production and exhibition – 4th Quarter. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Resource augmentation and modernization | Augment the repository of primary source material – written, oral, auditory, audio-visual and pictorial of the IGNCA, to serve as the national centre for the arts and culture and support research and publication activities of its other in-house divisions, Upgrade and install modern management and technological tools and systems, Upgrade technology and set-up permanent galleries for display and exhibition. |  |  | (a) Purchase of Books, Journals, Rare Books & Personal collections. (b) Collection of slides through in-house digital photography and Purchase of slides (c) Microfilming of Manuscripts (d) Acquisition of Cultural archival material (e) Modernization of Digital Library, Annonated Bibliography Index, Reprographic unit & Audio-visual equipments (f) Cultural Informatics (g) Creation of Galleries | (i) Addition of books, periodicals, journals in the Library (ii) Modernization of the Library services State-of-art equipments in Reprography7, Computer centre and media production (iii) Setting up of three galleries for display of arts and crafts (iv) Digitization of manuscripts, internal repository etc. (v) Operationalising e-governance in the cultural field. (vi) Collection of archival material from the North-East | Through out the year |  |
|  | Modernization of office equipments in IGNCA | To equip the office with furniture and quipment, in keeping with the design and structure of the state-of-the-art building. |  |  | To procure office equipments and information technology tools. | Installation of modern equipments will enhance the work output and better working conditions. | Through out the year. |  |
|  | Cultural Cartography | Map ecological and cultural profile of diverse communities of India along with specific aspects of art and crafts traditions prevalent among them. |  |  | (i) Creation of a Cell (ii) Research and field study (iii) Preparation of Atlas. | (i) Training and capacity building (ii) Publication (iii) Seminars, conferences and workships. | Through out the year. |  |
|  | Fellowships for Enhancing knowledge | Induction of core academic personnel, by opening the “top” and by allowing free movement of scholars to come into the institution and work on specific areas of its activity. |  |  | Ten Long-term Fellowships (two years) and ten short term fellowships (upto one year) to be awarded. | (i) Augment research capability of the institution (ii) Enable the IGNCA to substantially reduce expenditure on “regular” employment of staff associated with academic divisions. | (i) Selection – 1st and 2nd Quarter (ii) Award – 2nd to 4th Quarter |  |
| 8. | National School of Drama, New Delhi | Promote Theatre and to conduct theatre training programme | 4.45 | 11.00 |  |  |  |  |
| (i) | Theatre workshop and part time courses in regions and locally and other training courses for faculty and staff. | To benefit a vast majority of theatre enthusiasts in various states with diverse languages and cultural backgrounds and to create theatre awareness in them. |  |  | 10 theatre workshops to be conducted. 15 Theater Groups to be Assisted. 2 Part time Courses will be conducted. 3 Teachers training and refresher course for faculty & staff. 10 Collaborative workshops with theater groups. | Theatre awareness with diverse languages and cultural backgrounds | During the course of year. |  |
| (ii) | Organizing of course of training Children Theatre in Delhi and outside Delhi | To develop personality and give exposure to children in terms of their expressions and confidence. |  |  | 15 children theatre workshops to be conducted in Delhi and outside Delhi. 10 Collaborative theater Workshops. 12 theater groups will be provided technical assistance. | Children will be exposed to new techniques of theatre. | During the course of year. |  |
| (iii) | Organising of collaborative programme of traditional group in villages and theatre festival/ exhibition. | Providing 3-year Advanced Dramatic Training Course and to acquaint the students from theatre from existing in different regions of the country. |  |  | 6 collaborative programmes. 2 Festivals are to be conducted. 20 exhibitions of plays are to be displayed. 35 contractual experts will be benefited. | Theatre culture among students from different regions of the country popularized. | During the course of year. |  |
| (iv) | Promotion of Folk, Tribal Arts and Educational Tours | To familiarize the students with the existing folk and tribal art relating to theatrical and music forms. |  |  | 3 Performances of Folk and Tribal to be held in Orissa, Educational tours for the students will be conducted and also performances with tribal groups to be organised. | Folk and tribal arts to the children undergoing theatrical courses promoted. | During the course of year. |  |
| (v) | Formation of Repertory Company of Adults performing for children | Aim to promote theatrical performances for children. |  |  | Summer festival in 12 centres in Delhi and outside Delhi. 15 Saturday and Sunday club performances. 12 performances with invited groups. 5 workshops with children teachers. | To promote theater among children | During the course of year. |  |
| (vi) | Extension of Repertory Company | Dissemination of Indian plays in India and Outside the country. |  |  | 155 Performances of play in Delhi/ outside Delhi. 16 Collaborative performances with theater groups. 3 performances in foreign countries. | Promotion of theater culture | During the course of year. |  |
| (vii) | National Theatre Festival & Satellite Theatre Festival | To conduct National Festival. |  |  | 10th BRM and Satellite Theater festivals are to be conducted with Indian and foreign theatre groups to be held in January 2008 | Theatrical awareness in the country created. | As approved by the Parliamentary Committee. |  |
| (viii) | Independent campus construction & renovations expenses | To provide facilities for the cultural activities on the larger and better scale |  |  | Renovation and construction work to be taken up as per estimate prepared by the Architect and submitted to the Min. of Culture. | Upgrading the theatrical culture in the country. | During the course of year. |  |
| ### 9. | ### National Gallery of Modern Art (NGMA) | ### To create an understanding and sensitivity among the Indian public towards visual and plastic arts in general and to promote the development of contemporary art in particular. | ### 1.75 | ### 4.50 |  |  |  |  |
|  | ### Upgradation, Modernisation and maintenance of museum | ### To promote development of contemporary art at par with international level. |  |  | Maintenance of a well displayed Gallery at par with International standards both at New Delhi and Mumbai. Operationalisation of a new branch of NGMA at Bangalore and a new wing of the Gallery at New Delhi.. | ### Increased Aesthetic awareness of public. Creation of world class modern art galleries. | ### Through out the year. |  |

|  |  |  |  |  | Organisation of at least 8 special and retrospective exhibitions of renowned Indian artists and 2 exhibitions of contemporary foreign artists under cultural exchange programme. Development of Sculpture Garden at NGMA, New Delhi |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | To organize summer art workshop during May-June 2007. To organize 300 film shows and also 6 5 conducted tours to be organized for the benefit of the school children. Around 35 thousand persons expected to visit the museum and benefit from its presentations and other activities. |  |  |  |

| 10. |  | Asiatic Society Kolkata | Declared as an institution of national importance. To launch research projects on language, literature, culture and socio-economical aspects | 5.00 | 3.00 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (i) |  | Development of Library System | To establish build, maintain institutions for promotion of research in humanities and sciences |  |  | (i) Book acquisition-2000 (ii) Micro film acquisition exposure-20000 sheets (iii) Cataloguing : Rare Books-5000 Nos. (iv) CD ROM Acquisition – 3000 sheets (v) Binding/Mending – 4000 nos. | Dissemination of knowledge contained in the manuscripts to the research scholars by providing developed library facilities. Estimated 2250 male and 9500 females will be served by library facility. | Continuous Process | Continuous Process |
| (ii) |  | Development of Museum & User facility | To preserve manuscripts which has a rich collection of archival records, coins inscriptions and very valuable lithographs. |  |  | Cataloguing/Documentation of MSS, archival Material etc. – 5000 MS, 1000 letters, 200 others | Around 350 Indian and 250 foreign visitors, Research Scholars will be benefited. | Continuous Process |  |
| (iii) |  | Conservation & Preservation of rare books, MSS & Other document | To take effective measure for the preservation of brittle and fragile manuscripts, rare books and other ancient objects kept in the Museum and Library of Society. |  |  | Restoration of 3000 sheets of Lithographic prints. | To give impetus to longevity of the rare books and mss. | Continuous Process |  |
| (iv) |  | Publication Programme | To bring out the publication of high academic standard for which the society is known to the world of scholars. Particular emphasis is made on the publication of books under the Bibliotheca Indica series. |  |  | Publication of 12 books, 4 journals, 11 booklets. | Providing more coverage and knowledge for the scholars. | Continuous Process |  |
| (ii) |  | Augmentation of Research | Research work in different areas, imparting training, conduction seminars, lectures, workshops etc. |  |  | 35 projects, 12 Seminars, 25 Lectures, 3 Training Programme, Exhibitions/ Workshops. | Upgrading research facilities by providing rare and unpublished manuscripts | Throughout the year | Continuous Process |
| 11. |  | Centre for Cultural Resources and Training, New Delhi | Aims to improve the quality of life through the medium of Academies working in the field of linking education with culture. | 2.30 | 8.50 |  |  |  |  |
| (i) |  | Propagation of Culture among school students | To conduct a variety of in-service Teacher Training Programmes such as Orientation Training Programmes, workshops, Seminars, Refresher course etc. in different parts of the country for school teachers, teacher educators etc.organisation of educational activities for school students and children belonging to governmental and non-governmental organizations. Workshops for children of resettlement and basti colonies and for physically challenged students. |  |  | Orientation -5000 Teacher Educators/ In-service School Teachers Training Porgrammes/ Seminars/ Workshops/Refresher Course for Teacher Educators/in-service Teachers Teachers to be trained through Trainers-2000 Teachers Settingup of Cultural Clubs - 100 Students to be trained under Community and Extension Programmes-40000 Students # Production Video films including CD Roms- 4 Publications including reprints -15 Cultural Kits-800 | Cultural awareness among school going children | Teachers are deputed by respective state Education Departments as per the eligibility criteria of CCRT. |  |
| (ii) |  | Cultural Talent Search Scholarship Scheme (CTSS) | Aims at providing facilities by awarding scholarship to study the performing and other arts to outstanding young children in the age group of 10-14 years. |  |  | Award of Scholarship under Cultural Talent Search Scholarships Scheme-400 | Providing facilities by awarding scholarships to study performing and other arts among outstanding young children | Children for the award of scholarship are selected on the recommendations of Central Selection Committee and Regional Selection Committees. | . |
| 12. |  | Financial Assistance for Professional Groups and Individuals for specified performing art projects. (Dance, Drama and Theatre Ensembles) | To promote the Guru Sishya Parampara and support organizations / individuals working in the field of Performing Arts. | 1.35 | 11.00 | About 1000 organisations/ individuals will be promoted and supported. | NGOs working in the field of performing arts will be promoted and supported. | Advertisements have to be released in time so that meeting of Expert Committee are held in order to release funds in right sequencing. |  |
| 13. |  | Gandhi Peace Prize | Government of India announced institution of an annual international Gandhi Peace Prize for social, economic and political transformation through non-violence and other Gandhian methods as a part of celebration of 125th birth anniversary of Mahatma Gandhi. | 1.30 | -- | The recipient of this prize is selected by the Jury headed by Hon’ble Prime Minister in accordance with the prescribed code of procedure. | Promoting Gandhian values. | Nominations are invited from competent persons by 30th April each year as per the code of procedure. Synopsis on each nominee are prepared and compiled in a booklet, which is then put up to the Jury for selection of an awardee. | Gandhi Peace Prize 2005 has been awarded to Archbishop Desmond Tutu. |
| 14. | National Culture Fund (NCF) |  | Public Private Partnership in the sphere of culture. To mobilize the funds from corporates/PSU & for funding of conservation and other cultural activities. | -- | 3.00 | Projects of NCF are for preservation of both tangible and intangible aspects of India’s rich cultural heritage. For this purposes many ongoing projects are being implemented. | Better Preserved Monuments and flourishing of intangible aspects of Indian Culture. | Through out the year |  |

| 15. | Centenary/ Anniversary Celebration |  |  | To celebrate the Centenary/Anniversary of important personalities and events | 15.07 | 19.00 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Celebration of 2550th Anniversary of Mahaparinirvana of Lord Buddha |  |  | To highlight salient aspects of the life and times of Lord Buddha and to acquaint the people particularly the young generation with the great soul, who successfully diverted the attention of masses towards Ahimsa for the betterment of human. |  |  | Programmes are to be organized in memory of Lord Budha and funds will be provided for the projects associated with Lord Budha to strengthen the infrastructure to propagate the teachings of Lord Budha. | The programmes and projects to be taken up will help to highlight the spirit of great soul and to provide opportunity to spread the message of Lord Budha. |  | From 13.5.2006 to 11.5.2007 |  |  |
|  | Celebration of Birth Centenary of Lal Bahadur Shastri |  |  | In order to create a Chair in the Institute of Defence Studies and Analysis, N.Delhi in the name of Shri Lal Bahadur Shastri. |  |  | A provision of Rs. 7.00 lakh has been kept for this purpose. |  |  |  |  |  |
|  | Celebration of 150th anniversary of 1st war of independence, 1857. |  |  | To highlight the sacrifices of our great heroes / leaders who laid their life for freedom of the country and to pay home-age to them. To make aware the people specially young generation about the history of our freedom struggle to infuse into them the spirit of the National Integration and also highlight the achievement of Nation in various areas in past 60 years. |  |  | To celebrate the event, programmes will be organized in memory of great heroes/ leaders to educate the people. funds will be provided for maintenance/ restoration of monuments and places associated with the event. | The programmes being organized will promote National Integration and will help in restoration/ maintenance of the places connected with the event. the sacrifices of the heroes/ leaders will be acknowledged which will infuse the spirit of patriotism in the young generation. The generation will also be told of the glorious achievements of 60 years of Independence. |  | Throughout the year starting from 11th May, 2007 |  |  |
|  | Financial support to Khalsa Heritage Project |  |  | To highlight salient aspects of the important events relating to Khalsa Heritage in order to infuse in the public, particularly the young, the spirit of these great events. |  |  | Funds for Khalsa Heritage Project to be given to Punjab Govt. as 1/3rd share of Central Govt. (Plan) as reimbursement of the amount spent on the project on quarterly basis. | Awareness of the important events and also to highlight the spirit of these great events. |  | Through out the year |  |  |
| 16. |  | Other Schemes |  |  | 27.42 | 59.21 |  |  |  |  |  |  |
|  |  | Central Institute of Higher Tibetan Studies, Sarnath |  | Established with a view to educating the youth of Tibet and Himalayan border areas of India | 4.90 | 3.00 |  |  |  |  |  |  |
| (i) |  | Development of Library |  | ## 1.To Preserve Tibetan culture and tradition. ## 2.To restore ancient Indian sciences and literature preserved in the Tibetan languages. |  |  | Purchase of 200 books, equipment and other material for its maintenance and development. | Literature on Tibetan culture and tradition spread by development of library activities | Throughout the year |  |  |  |
| (ii) |  | Publication and Printing. |  | To provide printed material on Tibetan culture for scholars and others |  |  | 8 books to be published. | Preservation of Tibetan culture and literature | Throughout the year |  |  |  |
| (iii) |  | Rare Buddhist Text Research |  | To offer the alternative educational facilities to the students of Indian border area who formerly availed the opportunity of receiving higher education in Tibet |  |  | Workshop, Publication of Dhih journals and infrastructure to be held. | Research scholars benefited by acquiring rare and unpublished manuscripts in book form | Throughout the year |  |  |  |
|  |  | Central Institute of Buddhist Studies, Leh |  | To develop multifaceted personality of the students through inculcation of the wisdom of Buddhist through and literature as well as to familiarize them with modern subjects to acquaint them with collection, conservation, translation, publication of rare manuscripts and research works relevant to Budhist Studies etc. | 3.00 | 7.50 |  |  |  |  |  |  |
| (i) |  | Construction of Building | Construction of Physical Infrastructure for CIBS and DPS, Zanskar. |  |  |  | To adhere to the time schedule in the past. | Better facilities for the users of the institute created | Construction is going through CPWD and State PWD. |  |  |  |

| (ii) |  | Provision for existing Gonpa/ Nunnery school | To support educational activities in the number of Gonpas by providing teachers and stipend to the students. |  |  |  | 29 Gonpa/Nunnery schools are going on. Approval of opening 21 Gonpa/Nunnery schools has also been obtained from Govt. of India, Min. of Culture. |  | Preservation and promotion of Monastic System of Education. | New Gonpa /Nunnery schools are likely to start from April, 2007 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (iii) |  | Other Activities under Plan like Publication of rare Books, Manuscripts Seminars/ Symposium, conduct of Refresher courses, Purchase of Books, Fuel, Furniture/Furnishing items, Machine/ Equipments, etc. | These are the continuing activities of the academic nature and for efficient running of the Institute. |  |  |  | Continuing schemes will be dealt with by the organization as usual. |  | Academic Buddhist studies in the area promoted. | Throughout the year |  |
|  | Gandhi Smriti and Darshan Samiti |  | To propagate the life, mission and thoughts of Mahatma Gandhi by organizing various socio – educational and cultural programmes. |  | 3.00 | 6.00 |  |  |  |  |  |
| (i) | Promotional Activities |  | To plan and carry on activities for the promotion of Mahatma Gandhi’s ideals and of national causes identified by him. |  |  |  | Regular programmes with educational institutions, programmes for youth, programmes to mark the 100 years of Satyagrah: Gandhi and the contemporary world commemorative programmes. |  | The message of Gandhi is likely to reach about one lakh people through special programmes directly and to similar number indirectly. Around 5 lakh people will be directly benefited through multi-media exhibition established at Gandhi Smriti. | Various promotional activities will be carried out during the year |  |
| (ii) | Dissemination |  | To undertake such activities as will lead to greater understanding of Mahatma Gandhi’s life, work and thoughts. |  |  |  | Publication of journals, books etc., research activities and strengthening of International Centre for Gandhian Studies and Research Training Seminars/ Workshops. |  | Through these publications the message of Mahatma Gandhi will reach nearly 20,000 people directly and atleast to equal number indirectly. | These programmes will be carried out as per schedule |  |
| (iii) | Infrastructure and Development related activities |  | To acquire, maintain and preserve the personal papers and other historical materials pertaining to the life and works of Mahatma Gandhi in consultation and collaboration with the other Governmental organizations engaged in Gandhian work. To preserve and maintain Martyr Column at Gandhi Smriti and pavilion at Gandhi Darshan Complex. |  |  |  | Development of Gandhi Smriti and Gandhi Darshan Complexes; restoration of Gandhian Heritage and acquisition of art, objects, book etc. purchase of modern office equipments etc. strengthening of Samiti’s infrastructure |  | Through these infrastructure/ development works Samiti will be able to maintain both the complexes properly. This in turn will help implementation of various programme for spreading the message of the Mahatma Gandhi effectively. | Various activities will be carried out during the year |  |
| (iv) | North East |  | To spread ideas and thought of Mahatma Gandhi in North-East. |  |  |  | 8 special programmes will be organized in the North-East Region. |  | Message of Mahatma Gandhi is likely to reach nearly 8,000 people directly and similar number indirectly. | Programmes will be organised during the year. |  |
|  | Nava Nalanda Mahavihara, Nalanda, Bihar |  | To revive past glories of the ancient university of Nalanda and to give post graduate studies and research in Pali language and literature and Buddhology. |  | 1.30 | 3.00 |  |  |  |  |  |
|  | Development programmes of the institution. |  | Development and improvement of various ongoing programmes of the Institution including Cultural Exchange Programmes, workshops and printing of old and new publications and research work. |  |  |  | Books expected to be purchased - 1000. Workshops – 8 Seminars – 2 Couple of cultural exchange programmes. 500 copies each of the printed text to be brought out. Research workshops and seminars and their documentation to be taken. |  | Research material in Pali language and literature and also buddhology preserved. |  |  |
|  | Development of Xuan Zang Memorial Hall |  | To provide creative works, as paintings, murals inside and outside the XHM and on landscaping etc. |  |  |  | Procurement of various paintings and murals connected with the life of Xuan Zang. |  | To awareness of Xuan Zang. | Through out the year |  |
|  | Construction of 100 beded new hostel |  | To accommodate the foreign students |  |  |  | Fund will be released to CPWD |  | It will attract the foreign students | Carried out through CPWD on call of tenders |  |
|  | Construction of Faculty building |  | To accommodate teachers and students for teaching and research |  |  |  | Fund will be released to CPWD |  | Will create better environment for study | Carried out through CPWD on call of tenders |  |
|  | Community Hall |  | For recreational activities of staff of Navnalanda Mahavihara. |  |  |  | Fund will be released to CPWD |  | To provide better facilities. | Carried out through CPWD on call of tenders |  |
|  | Maulana Abul Kalam Azad Institute of Asian Studies, Kolkata |  | To conduct research and training of life and works of Maulana Abul Kalam Azad with the study of social culture, political and economic movement in Asia from the middle of the 19th century. |  | 0.65 | 4.00 |  |  |  |  |  |
| (i) | Research project including North East/ fellowship and other promotional activities. |  | To carryout research activities and revelation of political, social & economic changes in India and other Asian countries. |  |  |  | 30/40 Fellows will be engaged to under take Research on various areas including North East India. In addition to this new campus will provide hostel facility to out station fellows. Foreign visits & seminars at National & International level will be conducted. |  | Facilities for research and training of life and works of Maulana Abul Kalam Azad along with the study of social, cultural, political and economical movement in Asia created | Monthly and Quarterly progress reports are considered by the authority to assess the progress and to provide further grant. | Delay in quarterly progress report and manuscript by the research scholars. |
| (ii) | Construction of Office Building & Hostel |  | To accommodate office staff, work station of fellows, Seminar Halls & Hostel facility. |  |  |  | Construction of 3 storied building for better functioning of officers/staff & Fellows. |  | It will improve the quality of work. | The work will be completed by December, 2007. | Availability of Fund & completion of work by the contractor engaged by the C.P.W.D. |
| (ii) | Maulana Azad Museum |  | To establish a museum in honour of Maulan Azad at his residence at 5, Ashraf Mistry Lane, Kolkata-19. Contribution of Maulana Azad to Indian Independence movement along with a collection of memorabilia are on display for the visitors |  |  | - | Few dozens of photographs with caption and about a hundred memorabilia with LCD T.V. and the highest National Award – Bharat Ratna will be displayed. |  | Memorabilia and arrangement of display accessible to the public at large. | The work in progress. Most of the work has been completed. |  |
|  | Kalakshetra Foundation, Chennai |  | A Cultural institution of International repute established for preservation of traditional values in Indian Art especially in the field of dance and museum. |  | 2.90 | 2.50 |  |  |  |  |  |
|  | Kamala Trilokeker Block |  | To augment the class room facilities available for Fine Arts and Crafts both in CFA & BASS School, it is proposed to renovated this block. |  |  |  | Three studios for painting, pottery and sculpture. |  | To provide better accommodation and environment to students. | Six months |  |
|  | Upgradation of the Theatre-Civil works. |  | The existing construction of theatre is in very bad shape and had not been upgraded so far. To improve the facilities in the dressing rooms, toilets and to be in line with the modern facilities. |  |  |  | The number of dressing rooms for male and female artists will be assessed based on the maximum number of the artists who may use the facilities at a time. |  | To provide better facilities to artists. | 12 months on a conservative estimate. |  |
|  | Revival and documentation of dance dramas. |  | To document the 23 dance dramas choreographed by Smt. Rukmani Devi Arundale. |  |  |  | Six numbers of dance dramas will be documented and recorded in DVDs. They are being done in phased manner. To start with the 6- part Ramayana will be completed. |  | This will be useful for tutorial purposes as well as to be a guide for young artists, apart from being a record of the work of Rukmini Devi. | 1st phase consisting of six dance dramas will be completed in June, 2007. Subsequent phases will be taken up on receipt of grants from the Ministry. | Depends on the availability of the artists. |
|  | Research and Library Building |  | To make the modern library with full-fledged facilities for preservation and for taking copies etc. |  |  |  | The library has around 4000 volumes of old and rare collection of books on music and dance and more than 3000 volumes of books on different subjects. These books will be properly mended and laminated wherever the need arises and properly catalogued. |  | It will create better amenities to the users. | This will be completed in 12 months time |  |
|  | Namgyal Research Institute of Tibetology, Sikkim |  | ## The Institute is an autonomous organization under the state govt. of Sikkim and gets regular grant- in- aid from this ministry. The main objective of this institute is to spread the knowledge of Chhos(Doctrine of Buddha). |  | 0.40 | -- | The Institute has ongoing programmes of translating and publishing the seminal texts preserved in its archives. |  | Spread the knowledge of Doctrine of Buddha. | Through out the year. |  |
|  | a) Fellowship to outstanding artists in the field of performing, literary and visual arts. |  | This scheme provides financial support to outstanding artists in the fields of music, dance, theatre, visual art, literature and traditional art forms of folk and indigenous art. |  | 1.10 | 4.50 | 85 junior and 85 senior fellowships to be awarded. |  | Monetary support to the outstanding artists | Throughout the year |  |
|  | b)Scholarship to young workers |  | This scheme seeks to give financial assistance to young artists of outstanding promise for advanced training within India. |  | 0.70 | -- | 400 scholarships to be awarded. |  | Monetary support to young artists. | Throughout the year |  |
|  | Presentation of Books & art objects |  | With the aim to promote Literary Art and Art objects abroad through ICCR. |  | 0.03 | -- | Funds provided to ICCR for presentation of books and Art objects to foreign govts., organizations, libraries and individuals and for organizing essay competitions abroad.. |  | Promotion and awareness of literary art. |  |  |
|  | Shanker International Children Competition |  | For holding Shanker International children’s competition and publication for children art. Min. provides grants to the Trust. |  | 0.03 | -- | As usual Min. will provide grants to Children Book Trust for holding the competition |  | Promotion of fine arts among the children. |  |  |
|  | Institutions / individuals engaged in literary activities |  | To assist the organizations of all Indian Characters engaged in the development of literary activities. |  | 0.17 | -- | Assistance will be provided to Institute/Individuals. |  | Promotion of Literary activities. |  |  |
|  | International cultural activities & grants to Indo-Foreign Friendship societies |  | To foster closer friendship and cultural contacts between India and the foreign country concerned. |  | 0.50 | -- | Grants are sanctioned on the specific recommendations of the Indian Mission concerned. The grant covers expenses of grantees on cultural activities. |  | To promote bilateral cultural contacts and projection of India’s cultural image and generation of greater understanding of its cultural heritage, present situation and perspectives in the country concerned.. | Throughout the year |  |
|  | Financial Assistance to distinguished art persons |  | To provide financial assistance to artists whose contribution in the field of art has been of great significance and who have attained an age of 58 years and above and are in indigent circumstances. |  | 1.55 | 3.00 | 1540 old artists to be provided assistance under this pension scheme. |  | Financial support to renowned artists who have attained an age of 58 years and above and are in indigent circumstances | Throughout the year |  |
|  | #### Delegation under Culture Exchange Programme |  | ## Promotion of Cultural relations with other countries of the world on the reciprocal basis. |  | 0.80 | -- | The main purpose of this fund is to host cultural visits by foreign dignitaries organize meetings/ conferences under the cultural agreements. |  | Promotion of cultural relations with other countries of the world and creation of awareness about the cultural richness of India through cultural exchange programme | Cultural visits/ meetings/ conferences with the foreign countries are organized in consultation with the Ministry of External Affairs. There is no time frame. |  |
|  | Financial Assistance for Tribal/Folk Art |  | To promote and disseminate tribal art of culture. The scheme aims at creating awareness of richness of tribal /folk art through documentation and organizing cultural activities including festivals. |  | -- | 2.00 | About 600 organizations / individuals to be assisted. |  | To promote and protect Tribal/Folk art and culture from extinction | Advertisements have to be released in time so that meeting of Expert Committee are held in order to release funds in right sequencing. | Includes 20% provision for ST. |
|  | Financial Assistance for the Preservation & Development of cultural Heritage of the Himalayas |  | To promote, project and preserve the cultural heritage of Himalayas. |  | -- | 1.00 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. |  | Preservation and development of rich cultural heritage of Himalayas through financial supports to NGOs / individuals | Advertisement has to be released in the month of May/June so that applications received from various organizations/ Individuals are considered by October, 2007. | The number of proposals to be approved by the Expert Committee will depend upon the quality of the project and capability of the organization. |
|  | Financial Assistance for the Preservation and Development of Buddhist/ Tibetan Organizations. |  | To promote and propagate the scientific development of Buddhist/ Tibetan culture and tradition and also research in the relative fields. |  | -- | 3.70 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. |  | Protection and development of Buddhist/Tibetan art and culture | Advertisement has to be released in the month of May/June so that applications received from various organizations are considered by October,2007 | The number of proposals to be approved by the Expert Committee will depend upon the quality of the project and capability of the organization. |
|  | Centenaries & Celebrations |  | To provide financial assistance to cultural organizations/NGOs for celebration of centenaries of renowned personalities of India. |  | 2.00 | -- | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. |  | To create awareness among the masses about great personalities of India | Advertisement has to be released in the month of May/June so that applications received from various organizations are considered by October,2007 | The number of proposals to be approved by the Expert Committee will depend upon the quality of the project and capability of the organization. |
|  | Maintenance of National Memorials |  | To commemorate the role of eminent National Personalities who have contributed to and played a historic role in the history of the country |  | 2.00 | -- | Financial assistance is given to the voluntary organizations for maintenance of National Memorials |  | Better maintenance of National Memorials of eminent national personalities | Through out the year |  |
|  | Building Grants to Cultural Organizations |  | To give grants to voluntary cultural organizations working in the field of dance, music, fine arts, indology and literature for construction of building and purchase of material. |  | -- | 7.00 | 400 beneficiaries will be awarded grants. |  | Financial assistance to NGOs for providing infrastructure facilities and also purchase of equipments in the field of art and culture | Advertisements have to be released in time so that meeting of Expert Committee are held in order to release funds in right sequencing. |  |
|  | Financial assistance to Cultural Organizations with a national presence |  | To provide assistance Institutions/Organizations engaged in cultural activity at the National level. |  | 1.95 | 3.80 | The grant will be given to the prominent institutions like R.K.Mission. INTACH and other organizations with the national presence. |  | Promotion and awareness of thoughts, knowledge and theological activities at the national level. |  |  |
|  | Development of Cultural Organizations |  | To give grants to voluntary organizations of national fame engaged in cultural activities for holding a conference, seminars and symposia on important cultural matters. |  | -- | 1.60 | Organizations to be awarded grants, as per the recommendations of the Expert Committee, as and when it meets during 2007-08. |  | Financial support to NGOs and National fame, engaged in cultural activities and research on Indian Culture | Advertisements have to be released in 1st quarter so that meetings of Expert Committee are held in 2nd quarter to release funds in 3rd and 4th quarter. |  |
|  | Twang Monastery |  | To educate the monks and als act as a centre for Buddhist Cultural Studies. |  | -- | 0.01 | Monastery will continue its on going programmes. |  | Promotion of Buddhist Culture in the area. |  |  |
|  | #### Tibet House, New Delhi |  | ## The main aims and objectives of the Tibet house are to promote, preserve and protect the Tibetan culture, encourage the exchange the ideas and techniques between Tibetan and non-Tibetan artists and craftsmen. |  | - | 30.00 | Tibet House will continue to implement there on going programmes including maintenance of Museum |  | Promotion of Tibetan culture. |  |  |
|  | #### Development of Jalianwala Bagh Memorial |  | ## In order to take up a comprehensive development of this Memorial, refitting its status and importance in the history of India freedom struggle. |  | -- | 0.50 | Developmental programme will be taken up to upgrade the Memorial. |  | To create awareness among the masses about this memorial. |  |  |
|  | #### Assistance for preservation and promotion of intangible heritage of humanity. |  | ## To preserve and promote Kutiyattam, Ramlila and Vedic Chanting. |  | -- | 4.00 | About 200 organisations/ individuals to be assisted. |  | NGOs working in the field of performing arts will be promoted and supported. | Advertisements have to be released in time so that meeting of Expert Committee are held in order to release funds in right sequencing. |  |
|  | #### Scheme for safeguarding and other protective measures in the area of Intangible Heritage and Cultural Diversity (arising out of UNESCO Convention) |  | ## In order to meet the obligations arising from the UNESCO conventions on the safeguarding of intangible cultural heritage and cultural diversity. |  | -- | 0.10 | A token provision has been made for the new scheme. |  |  | All procedural formalities will be completed for launching the scheme. |  |
|  | #### Awareness creation in the area of Intellectual Property Right (IPR) and Setting up of a National IPR Cell for Creative Artists and Artisans. |  | ## To protect the Intellectual Property Rights of Indian Artists. |  | -- | 0.10 | A token provision has been made for the new scheme. |  |  |  |  |
|  | #### Plan scheme for promotion and dissemination of Awareness about Indian Culture and Heritage |  | ## To take up activities relating to promotion of cultural and heritage through performing arts and theatres. |  | -- | 0.50 | A token provision has been made for the new scheme. |  |  |  |  |
|  | #### Cultural heritage volunteers (CHV) Schemes |  | ## To protect the young people from marginalization and neglect by ensuring their social inclusion and involvement in civic and cultural programmes. |  | -- | 0.20 | A token provision has been made for the new scheme. |  |  |  |  |
|  | #### Pilot scheme for cultural industries |  | ## In order to convert wide variety of creative expressions, traditional designs and endless variety of crafts into cultural industries products. |  | -- | 0.50 | The scheme is to be implemented through ZCC on pilot basis. |  |  |  |  |
|  | #### Contribution to ICCROM |  | ## A contribution is made to the international body for membership of India |  | 0.10 | -- | Share of India’s contribution to be given |  |  |  |  |
|  | #### Contribution to World Heritage Fund |  | ## contribution is made to WHF for preservation and conservation of monuments/sites. |  | 0.07 | -- |  |  |  |  |  |
|  | #### Other expenditure TA/DA to non-official members |  | TA/DA to non-official members for attending meetings of various committees constituted by the Ministry |  | 0.13 | -- | TA/DA to be provided to non-official members during the year. |  |  |  |  |
|  | #### Contribution to UNESCO |  | ## Annual contribution is made by the Ministry. |  | 0.14 |  | Share of India’s contribution to be given |  |  |  |  |
|  | #### Centre for management of cultural resources |  | ## To develop centre of Excellency for Research and Training in inter-disciplinary areas in an integrated manner so as to introduce capable managers and researchers for Cultural Resources. |  | -- | 0.05 | A token provision has been made. |  |  |  |  |
|  | ## Total (Promotion of Art and Culture) |  |  | 76.64 |  | 202.96 |  |  |  |  |  |

|  | Archaeology, Archives and Museums |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 17. | Archaeological Survey of India | This organization is mainly involved in conservation, preservation and maintenance of the built heritage of the country. | 185.50 | 98.00 |  |  |  | * includes establishment / administrative expenses. |
|  | Conservation & Preservation of Ancient Monuments: its up keeps and maintenance including environmental development. | For conservation, preservation and maintenance of centrally protected ancient monuments and sites. |  |  | Conservation works at about 800 monuments which include Structural Conservation, horticultural development of 150 centrally protected monuments and up gradation of science laboratory at Dehradun and set up of research/ conservation laboratory at Aurangabad. | Better preservation and conservation of monuments will enhance and encourage cultural tourism. Scientific conservation will arrest further deterioration of the ancient monuments. | These preservation works are planned to complete in one year. However, this is a continuing scheme. | Natural calamities. |
|  | Providing basic amenities tourists | Development of basic amenities in Ancient monuments including provision of toilets, drinking water facilities etc. |  |  | Better visitors’ facilities and other amenities in all World Heritage Monuments and sites. | Will provide better tourist satisfaction and encourage cultural tourism. | Expected to complete in one year (2007-08) |  |
|  | Excavation and Exploration. | Archaeological Exploration Scientific clearance and Marine Archaeological Explorations. |  |  | The projects include archaeological investigation using modern scientific methods, analysis of archaeological samples and artifacts, creation of systematic storage spaces for artifacts and potteries retrieved from exploration & excavation, establishment of new Excavation Branch for North East States and activities of Under Water Archaeology, etc. | - | The explorations are expected to be completed during the year. |  |
|  | Development of the Archaeological Site Museums. | Maintenance and Development of Site Museums at various archaeological sites and monuments. |  |  | Up gradation/ Modernisation, security up gradation, documentation and museum catalogue of 41 site museum and proposal to open 3 new museums. | Setting up of site museums will create awareness among masses besides ensuring proper protection and display of antiquities and museums objects. | This is a continuing project. However, during the year archaelogical museums will be upgraded where work has already been initiated. |  |
|  | National Mission for Ancient Monuments and Antiquities | Inventorisation of unprotected monuments and antiquities. Creation of awareness. Preservation and conservation of unprotected built heritage and antiquities. |  |  | (i) Preparation, documentation of a data base of unprotected monuments and another for antiquities. (ii) Conducting of workshops for awareness and training programmes for stake holders. | Mission will help to protect and preserve the cultural wealth of the country. Increasing of public awareness and encourage public participation in preservation of monuments and antiquities. | Total project is for 5 years. |  |
| 18. | National Archives of India | The custodian of non-current records of enduring value of Central Government Ministries / Departments / Offices and their predecessor bodies. The nodal agency for record management activities and their permanent preservation and use by the posterity. | 12.24 | 4.00 |  |  |  |  |
| (i) | Expansion of records Management Programme | i. Acquisition of Public Records ii. Appraisal of files iii. Vetting of Records Retention Schedule. iv. Holding of Meeting of Archival Advisory Board v. Compilation of 9th and 10th Report of DGA on Implementation of Public Records Act 1993. vi) Organizing Orientation course in RM for DROs. vii. Inspection of DRR’s of Ministry/ Departments/ Offices. |  |  | Acquisition of 25,000 files. Appraisal of 2500 files Vetting of 15 records 7 orientation courses to be conducted. Inspection of 12 developmental record’s room. 7 orientation course to be conducted. | Permanent preservation, care and conservation of records in its custody for posterity, preparation of reference media, dissemination of information and serving for research scholars | Throughout the year |  |
| (ii) | Expansion of National Register or Private Records | Publication of NRPR Volumes. |  |  | Volume 24 & 25 to be compiled and completed | Helping the scholars to have a tangible idea about the custody of documents / manu-scripts in the custody of individuals and other voluntary organizations. | By editing/ listing & compiling of entries and printing of the volumes. Throughout the year. |  |
| (iii) | Expansion of repair and reprography | Repair of records, binding of books/ volumes/ preparation of security Microfilming, Preparation of Security Microfiche films, Positive printing of microfilms, Supply of copies (Xerox/ Photo/ Reader/ Microfilm to scholars as per their demand). Out sourcing of negative and positive microfilming/ out sourcing of positing microfilming of negative microfilm rolls available in NAI. |  |  | 1,18,000 sheets to be repaired, 4000 books/ volumes to be bound, 720 rolls to be microfilmed, 60,000 exospores to be completed, 28,000 meters printing to be done. 50,000 copies to be supplied to scholars, 44,35,200 pages approximately (3168 microfilm rolls) & positive copy of 3168 master negative rolls. 7920 rolls to be completed. | Scientific preservation of records by latest techniques to save them for posterity and research purposes./ To have a backup copy as a part of disaster management by way of content preservation and also to save space./ It will facilitate the research scholars / individuals in their research work. | Done both manually as well as by machine by the departmental experts. |  |
| (iv) | Expansion of library and administration | Purchase of books Data Entry in to the computer Preparation of data input sheets. |  |  | 600 books to be purchased. 700 books to be made. 700 sheets. | Research scholars/ individuals in their research work facilitated. | By holding BAC meeting by the departmental experts and approval of Ministry of Culture. |  |

| (v) | Expansion of School of Archival Studies | - One Year Diploma Course in Archives and Record Management – 2006-07 and 2007-08 - Short Term Courses in Archival Management and allied disciplines. |  |  | (a) One year diploma course 2006-07 to be completed and one year diploma course 2007-08 to be commenced and continued . a. Short Term Course in Record Management-two courses to be conducted. b. Reprography - (two courses). c. Servicing and Repair of Records (two courses). d. Care and Conservation of Books/ MSS/ Archives- (two courses). e. Archives Management- (one course). | Creation of a work force of trained professionals in various disciplines of Archival Administration , Record Management, conservation etc to man various custodial institutions of Archival and documentary wealth of the nation. | Publication of advertisements and selection of Trainees vide written test/ Interview and imparting training in the School of Archival Studies by departmental experts/ external faculty/ Conducting examination/Award of Diplomas. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (vi) | Listing of records ref. Media including computerization of records | Listing of private papers. Listing of oriental records and preparation of catalogue/ reference cards of acquired documents. Data Entry of reference media of 25 lakh records in NAI by out sourcing. Upgradation of AIMS Software by NIC. |  |  | 5000 items of private papers to be listed 1680 items to be descriptively listed. After approval of competent authority the project of Data Entry of Reference Media of 25 lakh records in NAI has been awarded to M/S Micrografics India, New Delhi. Upgradation of AIMS Software. | Facilitate the research scholars/ individuals in their research work. | By subject listing of the private papers by departmental experts. By descriptive listing the acquired documents of Oriental Records by departmental experts. |  |
| (vii) | Setting up of a Record Centre in Eastern Zone | - Survey and Accession of non current records - Appraisal of Records - Vetting of records retention schedule |  |  | - Survey and acquisition of non current records of central Government Offices located in North Eastern Zone. - 2000 files to be appraised - Vetting of 2 record retention schedule | - Preserving the Eastern regional records for safe custody/posterity and for consultation by scholars/individuals for their research work. - The process helps in elimination of records of ephemeral value and identification of enduring nature for their eventual transfer to NAI Record Centre. - Helps the record creating agency for recording/ weeding of records to ensure that files are neither permanently destroyed nor kept for periods longer than necessary. | - By visiting Central Government Offices/ Departments in North Eastern Zone by the departmental experts of the Record Center at Bhubaneswar and transfer of the appraised Non-current Records to the Record Center. - By visiting Departmental Record Rooms in the various Ministries/ Departments/Offices. - By conducting spot study of the Records of various Ministries/ Departments/Offices. |  |
| (viii) | Scheme of financial assistance for preservation of manuscripts/ rare books to NGOs. | Grants – Committee Meeting. |  |  | One Grants Committee Meeting to be held and the amount recommended by the Committee to be released to the recommended Institutions. | To support the initiatives by individuals /NGO’s in securing the valuable documentary heritage of the country by providing financial assistance to Voluntary organizations /universities/individuals for listing, cataloguing, publication, microfilming and for technical know-how for scientific preservation of manuscripts/ rare books. | Applications are invited vide advertisements through DAVP and Grants Committee Meeting is being held by the departmental experts. Grants recommended is then released to the private institutions after taking approval of the IFD, Ministry of Culture. |  |
| (ix) | Scheme of financial assistance to State/ Union Territory Archival repositories and Museums. | Grants Committee Meeting. |  |  | One Grants Committee Meeting to be held and the amount recommended by the Committee to be released to the State Archives, Government Libraries/ Museums as recommended. | To support the initiatives by the State / UT Archival Repositories/ Government Libraries and Museums in securing the valuable documentary heritage of the country by providing financial assistance for preservation, conservation, publication, cataloguing, microfilming, computerization, etc. of manuscripts/ rare books. | Applications are invited vide advertisements through DAVP and Grants Committee Meeting is being held by the departmental experts Grants recommended is then released to the Government of State Archives/ Museums/ Library after taking approval of IFD, Ministry of Culture. |  |
| 19. | National Museum | A premiere institution in the field of art and culture in India and involved in important work of acquisition, conservation, exhibition and educational activities | 8.04 | 10.00 |  |  |  |  |
| (i) | Photo-documentation of art objects and events | Coloured photo documentation of Museum’s collection, exhibits for exhibitions and publication purposes and events for publicity purposes, done as per demands. - Miniature paintings - Central Asian antiquities - Manuscripts |  |  | A. Photo documentation of Paintings, Harappan objects, Manuscripts, Jewelry, Bronzes exhibits & Gupta exhibits etc. B. Photo documentation of Art objects and events is a continuous work of museum collections and events.` | Record of all art exhibits required from time to time maintained. | Throughout the year |  |
| (ii) | Display & modernization of Museum - reorganization of existing galleries. | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | - Modernization work carried forward from the previous year i.e. Jewellery Gallery, Central Asian Wall painting gallery, Pre Columbian and Western Art Gallery, Decorative Art Gallery and Maritime Heritage Gallery. - Installation of Modern gadgets such as Plasma Screen, Kiosks etc. in selected galleries. - Design of Key Gallery including the Foyer, Reception entrance to the Library and Auditorium. | Providing better awareness of our heritage and art objects. | - Designs are to be obtained from the empanelled firms to be prepared by display section - Designs are to be approved by the Expert Committee within 1st & 2nd quarter Dismantling of the existing structures wherever required & fabrication of structure in the last 2 quarter |  |
| (iii) | Reorganisation of Reserve Stores | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | - Central Asian Antiquities - Textiles Modular storage - Decorative Art: Special storage for wooden door collection. - Anthropology - Pre-Columbian & western Arts | Better display of objects will encourage tourists with better satisfaction | -do- |  |
| (iv) | Restoration and Conservation of art objects. Restoration of Oil Paintings / Conservation of antiquities / art objects / training course in conservation, Acquisition of equipments for conservation / binding of manuscripts. | - To protect the antiquities and art objects from decay. - To train the Museum staff of National Museum and other museums/Institutions in latest technology in conservation. - To keep laboratory well equipped with the latest equipments. |  |  | - Treatment artifacts of National Museum - Treatment & display of Central Asian Antiquities. - Conservation of manuscripts - Treatment of MSS, Central Asian Antiquities and Tribal Art artifacts. - Conservation of art objects using 3D digitization technology. - 3 months training course of paintings - Programme on preventive conservation for curators of different Museum/ Art Galleries (four days) - Teaching & conducting of practical class programme for students of NMI - Treatment of Paintings of Shri Chitra Art Gallery, Thirvananthapuram Treatment of Paintings of North Block/ Parliament House. | Protect and enhance the life of art objects from decay | do- |  |
| (vi) | Exhibition | - To popularize the ancient Indian Art & Culture. - To organize thematic exhibitions. - To organize exhibitions under Cultural Exchange Programme |  |  | Exhibitions to be sent abroad - Exhibition entitled “Gupta Art” to be organized in France. - An exhibition to be organized in Singapore & USA. - The work of organizing Nizam Jewellery is under progress. | Awareness and education of the masses about the Indian art and culture through exhibitions. | Throughout the year |  |
| (vii) | Strengthening of Museum Security | To keep security arrangements up-to-date keeping in view the changing threat perceptions. - To keep the Museum and antiquities from threats such as fire etc. |  |  | - Installation of barbed wire around the boundary of National Museum - Conversion of black & white CCTV cameras into coloured ones - Extension of CCTV coverage to remaining galleries & storage area - Procurement of Thermal Surveillance cameras - Perimeter IR Detection System - Procurement of Perimeter fence (Electric) Procurement of Real time DVRs, in CCTV Control Rooms. | Protect and preserve the cultural wealth of the country | To strengthen the safety and security of the Museum and antiquities |  |
| 20. | National Council of Science Museums | To popularize Science and Technology by organizing exhibition, seminars, training programmes for Science Teachers, students, young entrepreneurs, technicians etc. | 16.40 | 17.00 |  |  |  |  |
| (i) | Setting up of new galleries, upgradation and updation of exhibits, new circulating exhibitions, new mobile science exhibition units, new training facilities, educational programmes, strengthening of infrastructure and existing facilities of 27 science centers located at various parts of the country. | To modernize, upgrade and popularize the science and technology in the country. |  |  | SRSC Solapur, Gangtok and new wing “ The planet We live In” at Science City, Kolkata. Regional Science Centre Raipur, Ranchi & Dharwad New Galleries on “Bio-machine” at RSC, Guwahati, ‘Energy” at RSC Bhopal, “Information & Communication Technology” at RSC Nagpur. Gallery on “Poular Science” at DSC Dharampur & “Heritage” gallery at NSC, Delhi, KPSC Kurukshetra, “Electro Technique” gallery at VITM Bangalore, “Colamine” & “Transport” gallery Kolkata,”Fludics” gallery RSC Lucknow. Gallery on “Human Biology” at NSC Delhi Travelling Exhibitions on “Biodiversity” ,“Nanotechnology”, “Illusion”, “Human Genome” “An eye in the Sky”, “ The World of Astronomical Observatories” and “ A Century of Physics”. Two new exhibitions | Give an impetus to science and technology in the country | Projects will be completed in 2007-08 Work will continue. Galleries will be set up during the year. renovation will be completed. Will be extended. Will continue to be circulated. Will be developed. | By finalizing the Annual Action Plan 2007-08, the entire family will be phased out to four quarters to maintain the progress of work, a planned and steady flow of expenditure. |
| (ii) | Centralized procurement of LFFP system and Other Major equipment. | To set up large format film projection system at NSC, Mumbai. Procurement of high resolution 3D film and Motion simulator. |  |  | Addition of new facility by setting up of LFFP system at NSC, Mumbai to offer immerse science-learning ambience. | Give an impetus to science and technology in the country | The work will be completed by 3rd quarter of 2007-08 |  |
| (iii) | On going new projects – KCMP, Kurukshetra | To set up Kalpana Chawla Memorial Planetarium at Kurukshetra |  |  | Being the first planetarium of its kind, being set up in the state of Haryana, this Planetarium is expected to provide astronomy education to the visitors. | Providing and promoting astronomy education through planetarium | The project will be completed by 2006-07 but some spill over fund for final settlement of the bills will be required. |  |
| (iv) | New Projects in NE states – SRSC, Gangtok | To popularize science and to spread science message and to create a scientific temper and awareness among the people of the region. |  |  | To set up new Science Centres in the state of Sikkim | Popularizing science and technology in North Eastern Region | The project will be completed in 2007-08 |  |
| 21. | Science Cities | To popularize Science and Technology at selected centers in the country. | --- | 13.00 |  |  |  |  |
| (i) | To establish Gujarat Science City at Ahmedabad | To inculcate scientific temper in public at large and students in particular. |  |  | Facilities like Imax Theatre, Musical Fountain, Hall of Science, Energy Park, Simulator, Amphitheater are operationalised and Space and Communication Pavilion, Life Science Park, Children Activity Corner will be opened to public. | Give an impetus to science and technology in the country | The Ist phase will completed. |  |
| (ii) | Setting up of Pushpa Gujaral Science City, Kapurthala, Punjab. |  |  |  |  |  |  |  |
|  | Construction of 4 exhibit galleries and Convention Hall including Electrical, AC Services, Escalator, Elevator, Chairs etc. | For establishing exhibit galleries |  |  | Construction will be completed | Popularizing science among the masses | Construction is under progress and will be completed by July, 2007 |  |
|  | Construction of buildings for Evolution Gallery | Establishing of Evolution Gallery |  |  | Construction will be completed |  | Construction is under progress and will be Completed by May, 2007 | Highly specialized buildings. |
|  | Construction of Administrative Block | For smooth functioning of Administration |  |  | Construction will be completed |  | Construction is under progress and will be Completed by October, 2007 |  |
|  | Exhibit Development and Procurement |  |  |  |  |  | March 2008 |  |
|  | Audio Visual System | For Convention Hall |  |  |  |  | September 2007 |  |
|  | Landscaping and garden development |  |  |  |  |  | March 2007 |  |
| (iii) | New Projects: RSC Raipur, Ranchi and Dharwad, SRSC Solapur and Kalimpong, Science City/Centre at Mangalore. | To popularize science and to spread science message and to create a scientific temper and awareness among the people of the region. |  |  | To set up new centers in the state of Chattisgarh, Jharkhand, Karnataka, Maharashtra and West Bengal. | Give an impetus to science and technology in the country | All RSC’s will be taken up after the SFC clearance is obtained and will be completed with in 30 months from the date of commencement of construction. SRSC, Kalimpong will be completed in 2007-08. | . |
| 22. | Anthropological Survey of India | Committed to research activities on human population from bio-culture perspectives. Its activities include collection, preservation, maintenance, documentation and study of ethnographic materials as well as of ancient human skeletal remains. | 11.20 | 6.50 |  |  |  |  |
| (i) | Documentation and Dissemination | To maintain Anthropological Libraries in 7 Regional Centres and Central National Library at Kolkata. At present Survey possesses museum artifacts stored in all the seven zonal museums and central museum at Kolkata. During the current financial year it is proposed to initiate conservation & documentation of all these specimens with scientific methods by trained manpower. All the documentary films possessed by Survey to be converted to Beta-com will be completed. All silent films will be edited for voice and sound mixing. Production of new documentary films will be taken up on specific themes like 1. Children of Forest Jenukurumba 2. Village life in North Karnataka 3.Transhumans in Western Himalayas 4.Ghotul-The Kingdom of the young 5. Memorial pillaras of Bastar 6. Jarwa Life 7. Any specific films recommended by government. |  |  | Libraries of the Survey being center of excellence in the field of Anthropological research all over the country, through which around 1000 researchers, professors, administrators of different academic and other organizations take the help from this library as a centre of reference and documentation. More than 2,00,000 visitors including scholars, students and common man and dignitaries will visit anthropological museums. Survey has 25 16mm visual documentary films and more than 1,000 audio-cassettes. Steps have been taken by signing MOU with Film Institute for archiving the 16mm films and transforming them to Beta-cam to make DVDs and CDs. | Provision of literature and other material to promote anthropology and ethnology for research scholars. The audio Cassettes of folk songs and other cultural expressions are used for research purposes. | It is a continuous process. |  |
| (ii) | Exhibitions | For promotion and dissemination of ethnographic materials as well as of ancient human skeletal remains and research carried out thereon. |  |  | Exhibitions on “Human Origin, Genome and People of India” in various places in N.E. India and will be mounted at Itanagar, Shillong and Gangtok. Cultural Diversity: Dialogue and Empowerment is on the move in Central India and will be mounted in rural areas of Bihar. | For promoting ethnological and anthropological culture, this will attract more than 50,000 people of N.E. states visiting the exhibition. | It is a continuous process. |  |
| (iii) | Book Exhibitions/Fair | For promotion and dissemination of ethnographic materials as well as of ancient human skeletal remains and research carried out thereon. |  |  | Survey participates in several exhibitions organized by local authorities at Kolkata, including National book exhibition. In order to hold exhibitions at several places in Kolkata, where there is a continuous demand, survey proposes procurement of a specially built mobile van during the year. | Survey would be selling books of worth 1.00 lakh and will be visited by about 4-5 lakhs visitors It is expected that more than 2 lakh visitors will be visiting the stalls and books worth around Rs. 20,000 will be sold. | Through out the year |  |
| (iv) | Fellowship programme | The Survey proposes to revise the stipend of the fellows at par with the National Organizations like UGC, ICMR etc. since the fellowships that are offered are very meager and in terms of qualified manpower is inhuman. |  |  | Fellowships are an important component of manpower development as a resource in the country. At present the Survey has 47 fellows. It is proposed to enhance total fellowships to 67 and also increase the stipend. | It will attract intellectuals of the field. | It is a continuous process. |  |
| iv) | Induction of DNA technology | Maintenance of Infrastructure already developed at Kolkata, Mysore, Nagpur, Shillong and Port Blair. Procurement of Liquid Handling Systems at Mysore. Development of laboratory facilities with DNA technology up to PCR level and DNA Banking at Dehradun and Udaipur. Augmentation of DNA Banking facilities at all the regional centers including headquarters. Establishment of core Phenotypic facility at Kolkata and Mysore in terms of High Through put automated bio-chemical analyzers. A concerted effort to induct tissue culture technology for cell lines. |  |  | At the moment survey can boast of creating state-of-the-art advanced facilities, which are all functional, in 5 of its centers. The infrastructure development is planned in such a way that manpower training is also quite in place, by the time technology is inducted in survey. Now survey is poised to implement national programs concerning ‘genetics and health’ integrated with cultural practices of communities. | DNA labs will focus on genetic basis of diseases. | Continuous process. |  |
| (vi) | DNA Polymorphism of the Contemporary Indian Populations & Ancient Skeletal Material | Human Genome Diversity Analysis: 1) 27 populations Y SNP, Y and autosomal STRs. 2) Collection of blood samples from populations in north-east and other parts in India. 2) Candidate gene polymorphism of diseases in patient and population cohorts. |  |  | Baseline information that is being generated on Indian populations in terms of human genome diversity will be useful in medical applications | It will realize ultimate application, there is urgent need to initiate dialogue with private pharma sector, for meaningful collaboration as a policy, taking into account ethical issues. | This programme is to be continued as an ongoing project during the Eleventh Plan Period. |  |
| (vii) | Growth (reoriented as children in N.E. : Growth and Development Study – A Public Health issue) | To generate information about the health status of the children of the North East India in Particular |  |  | Growth of children as public health issue is a mission mode project in north-east. | Generating information on health status of the children of NER | This programme is to be continued as an ongoing project. |  |
| (viii) | Functional modernization of new and existing office buildings/ minor works/ furnishing | For modernization in terms of fabricating existing buildings and new buildings |  |  | Target: at Mysore Museum, ISA, Library and at Kolkata; Library, Social, Physical Administrative sections, HOD room, PA to HOD room, Confidential section, record room, conference room annex, entrance of spirit building (in collaboration with ZSI) of Hdq and eastern regional center building at salt lake, besides museums and office buildings in survey at different centers. | Modernization of working place in terms of modular functional space is undoubtedly a prerequisite for creating excellence. | Finalisation of the work plan, estimate etc. of the CPWD and timely approval of the work proposal from the Ministry, wherever necessary, may affect the implementation. |  |
| (ix) | Narmada Valley Excavation | The extensive excavation in Narmada Valley in search of Palaeo-anthropological materials, before submergence. |  |  | Field explorations will be continued in Narmada with the possibility of undertaking excavations as a collaborative program with ASI. Similar sites in the other parts of the country will be explored. The proposal to collaborate with European and African groups with extra mural funding will be further pursued. | Our country has important role to play in understanding ‘Human Origins’. However the effort in terms of institutional arrangements, only initiated by Survey from the last 3 years. This scheme needs full support. | This programme is to be continued as an ongoing project during the Eleventh Plan Period. |  |
| (x) | NEW SCHEMES 1. People of India: Cultural Diversity (Five components) | a) Intangible & Tangible Cultural Heritage: Oral Traditions, Folk Taxonomies, Social Structure & Bio-cultural Adaptations with Gender Perspectives. b) Establishing a National Centre for Community Knowledge at the new building at Udaipur. c) National Centre for Visual Anthropology: Kolkata d) Man & Environment e) Bio-cultural Linkages with border area countries. |  |  | a) Cultural Diversity of the people of India need to be scientifically documented and projected for greater harmony among the communities. The issues that are addressed are contexualization of ‘Traditional Knowledge’ and linkages of cultural diversity with bio-diversity in the context of ‘man and environment’. Besides, understanding the bio-cultural linkages with border area neighbouring countries is an urgent issue in view of globalization and merging of borders, and state sovereignty. Formulation of programme, area of studies through workshops and initiation of first phase of fieldwork by the deployed scholars among the SC/ST communities b) Establishment of ‘National Center for Community Knowledge ‘ at Udaipur and a center of excellence for ’visual anthropology’ will be tangible outcome of the scheme. Initiation of establishing the centre and to procure equipments for digitisation work for broader highlighting of the intangible cultural heritage of Western India. c) Initiation of establishing the centre for visual anthropology in the new building of the Head Office of the Survey in Kolkata. d) This project is earmarked for SC/ST, which requires extensive fieldwork to frame the All India schedule during the year. e) Reconnoiter tour for collection of first hand information for executing the project will be conducted during the first year of annual plan period. | It will create harmony among the communities / people of India. |  |  |
|  | # 2. Bio-cultural Adaptations (Two components) | a) Community Genetics and Health in North – East India b) Genetics & Health: Family Study |  |  | a) In this program we would like to initiate a collaborative program in North-East on the issue of G6PD deficiency and hemoglobinopathies. b) Bio-cultural risk factors for life style diseases need to be evaluated/ discovered by the analysis of several quantitative factors (genome/cultural/environmental) within families. It is proposed to initiate a well designed study at Mysore, which will be implemented with a consortium of specialties and will be known as ‘Mysore Family Study’ |  |  |  |
| 23. | Nehru Memorial Museum and Library | Responsible for collection of books, newspapers, unpublished references, private papers/ photographs film takes, and also translation of important papers relating to Pundit Jawaharlal Nehru. | 5.90 | 3.50 |  |  |  |  |
| (i) | Promotion of Research/ Award of Fellowships. | To offer three level of fellowships namely Senior Fellowship, Fellowships and Junior Fellowships and to institute, award scholarships and monitory assistance. |  |  | Working on different research projects and the findings of the fellows/ research papers created by them are being published in the form of monographs. | The fellowship programme will strengthen advanced historical scholarship in our country and will result in a number of standard publications. | It is a regular feature to continue the ongoing research scheme namely “Promotion of Research in Modern Indian History and Contemporary Studies.” “Perspectives in Indian Development (Social, Economic and Cultural) and “India and Changing Trends in World Economy and Polity.” |  |
| (ii) | Publication Programme | To undertake to promote publication of books, monographs, periodicals and papers incorporating the research of the studies carried out at the NMML. |  |  | Apart from bringing out the quarterly journals, NMML as also publishing the monographs created by the fellows of the NMML. A project has also been taken up to publish the selected writings of C. Rajagopalachari. | Promotion of research carried out by this organization on the life and ideas of Pandit Jawaharlal Nehru with regard to various socio economical issues | The publication of the Quarterly journal, and other research publications is a continuous effort to highlight the researches carried out in the Institution. |  |
| (iii) | Seminars and Lectures | To organize lectures, seminars, symposia and conferences to promote and encourage the study of Modern Indian History. |  |  | Proposing to organize four seminars two at the national level and another two at the international level. Tuesday seminars and other lectures will also be organized as usual. | The seminar programme will provide scholars an opportunity to interact and share the knowledge. | Organisation of seminars/ lectures is an ongoing programme. |  |
| (iv) | Oral History Division | To record the reminiscences of eminent persons who have played an important role in national development and to preserve the recording and the |  |  | Proposes to interview atleast 20 persons in the year 2007-08 and finalise at least 25 transcripts. | The Oral History transcripts will provide the missing links in the form of primary research material for researchers who mostly rely on written documents. | It is a continuous process. |  |
| (v) | Development of Library a) Acquisition of books, Periodicals/ Resource Material a) Acquisition of book Racks & Library furniture c) Moderanisation of Library with the state of the art knowledge management facility | To maintain a Library of books, pamphlets, newspapers, periodicals, microfilms, still photographs, motions pictures, sound recording and other materials bearing on the History of Modern India with special reference to the Freedom Movement. |  |  | The Library will continue to acquire books, with a focus on Modern Indian History and related Social Sciences in addition to material on microfilm and photographs. The Library will be provided with the state- of- the- art facilities like digital membership, wireless Lan, Highend computer storage facilities for digital materials and the seminar room will be fitted with modern projection systems. | The pre-eminent position of the NMML Library in the world of Social Science scholarship will be sustained with the addition of new books, periodicals and state-of-the-art information equipments. | It is a regular feature. |  |
| (vi) | Development of Museum | To maintain a Museum of Jawaharlal Nehru Personalia, memorabilia, mementos and other objects pertaining to his life and the Indian freedom movement. |  |  | Proposing to mount two or three temporary exhibitions in the Museum. It is also proposed to moderanise the Nehru Museum with the help of Information Technology and to install information kiosks,and audio-video projections. | The efforts to mount new exhibitions will attract more visitors to the Museum. | It will be a regular feature. |  |
| (viii) | Replacement of AC System | Preservation and Maintenance of the historical documents and other valuable materials available in the Library, Archives and the Reprography Division. |  |  | The Present Air Condition system has outlived its life and giving lot of problem. It is proposed to install new AC System in Library building including the Auditorium and Annexed building. | The installation of new AC System will provide necessary environment for preservation of historical documents and also the new technology will help in saving electricity charges. | To be completed in 2007-08. |  |
| (ix) | Nehru Planetarium Activities | We have taken over the Nehru Planetarium in August 2005. This is the only planetarium in the Capital and its programmes stimulate scientific interest among the children. |  |  | We proposed to moderanise the Planetarium. A new laser based planetarium equipment will be installed as present machine is very old. Also many competitions to popularize science will be conducted. The exhibition area will also be renovated. | The Planetarium sky shows will educate the children. | Through out the year. |  |
| 24. | Indian Museum, Kolkata | Engaged in reorganization and renovation of galleries housing unique treasures of Indian and foreign art representing centuries of cultural ethos and tradition. | ###### 4.40 | ###### 8.50 |  |  |  |  |
| (i) | Modernization, development, renovation and upkeep of galleries of art, Archaeology, and Anthropology Sections | The objectives include refurbishing, modernization & renovation of different galleries and reserve collections with updated arrangements and techniques. |  |  | i) Reconstruction, renovation of galleries - 18 nos. ii) Setting up of new galleries - residual work - 4 nos. iii) Intercom facility – 1 case iv) Equipment purchase – 3 cases v) Electrification of go-down – 1 case vi) Showcase – redesigning – 1 case | Modernization and renovation of different galleries and reserve collections will attract more tourists and will enhance India’s culture, ethos and tradition. | Through out the year | Non-execution of different plan schemes as detailed will defeat the purpose for which the Indian Museum has been established. |
|  |  |  |  |  | vii) Air-conditioning of gallery – 3 nos. viii) Fire proof arrangement – 2 nos. ix) Catalogue preparation – 2 nos. x) Documentary film – 1 no. xi) Label replacement – 200 nos. xii) Building study cum storage – 1 no. xiii) Field collection – 150 specimens |  |  |  |

| (ii) | Strengthening and modernization of security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. | To strengthen the security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. |  |  | i) Engagement of Security Agency & State Armed Police throughout the year. ii) Replacement of existing fittings, fixtures etc. - 10 nos. iii) Maintenance & purchase of upgraded & sophisticated security gadgets – 18 nos. iv) Illumination development of total campus area v) Upkeep of different electronic devices/fire/ burglary alarm, door frame and hand set metal detectors, CCTV etc. – 125 nos. vi) Purchase of computer -1 no. vii) Organisation of training – 4 prog. viii) Construction of water tank– 1 scheme ix) Intermittent test of security system – 10 nos. - x) purchase of vehicle – 1 no. | Safeguarding the precious and unique treasures, this step will give further impetus to museum movement in attracting more tourists. |  | Through out the year. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (iii) | Strengthening and modernization of Conservation Unit (Conservation Laboratory) | Scientific preservation of antiquities and restoration of art objects. |  |  | i) Conservation of sensitive materials – Textile, ivory, wood carvings, paintings, metal, stone, delicate artifacts etc. ii) Reorganization of mobile conservation Laboratory & its workshop; iii) Purchase of sophisticated instruments and equipments; iv) Reorganization of different laboratories (organic/ inorganic) v) Computerized documentation of conservation work; vi) Organization of refresher training courses on conservation, orientation course for museology students; vii) Organization of a Special long term project of laser conservation. | To preserve and conserve the antiquities for future. |  | Through out the year. |  |  |  |
| (iv) | Programme of Education and Mass Communication Cultural Activities | Organisation of education activities and training programmes holding of temporary/ special & inter-state, in-house exhibitions, outreach programme through Museum on wheels (Museo Bus), organisation of National/ International seminar and workshop. |  |  | i) National / International seminars and workshop; ii) Mobile exhibition, temporary exhibition; iii) Mass Communication Cultural programme; iv) Annual and memorial lecture series; v) Training programmes – In-service training course and short course in museum studies, practical aspects of Museum methods; vi) Development of Auditorium & Exhibition Hall; vii) Preparation of leaflets, exhibition folders, invitation cards, handout etc. viii) Purchase of computer, wheel chairs for physically handicapped; ix) Reorganisation & refurbishing of lecture room. | Awareness of Educational and Mass Communication cultural activities among masses. |  | Throughout the year |  |  |  |
| (v) | Reorganisation of Scientific galleries (Zoology, Geology and Botany) - | To raise the standard of display and presentation of the scientific galleries and to bring them at level with that of the cultural galleries museum proposes to renovate and update the scientific galleries also with the expertise of the respective Surveys. |  |  | i) Organisation of the Gemmology Section ii) Extensive renovation of the Meteorite Gallery iii) Extensive renovation of the Mammal Gallery iv) Reorganization of the Insect Gallery v) Air-conditioning of Bird Gallery. | Better presentation and display of exhibits will enhance the tourist. |  | Through out the year. |  |  |  |
| (vi) | Special repairs and maintenance of Museum buildings (heritage) | To develop and structural conservation of Museum buildings and other infrastructural developments |  |  | Repair and maintenance of A) Main Museum Building, B) Museum house and C) Other Building | To preserve the colonial period buildings which are more than 150 years old. |  | Through out the year. |  |  |  |
| (vii) | Development of museums in Eastern & North-Eastern states of the country | To bring about greater and deeper understanding and appreciation of the country’s rich cultural heritage as a whole. |  |  | Formulation of the infrastructural development of the museums of the North-East region during 2007-08 are being assessed by a team of technicians, experts, Directors and other Sr. Officers of the Museum including members of the Board of Trustees of the organisation. | People of North-East states will be benefited. |  | The programme with regard to execution of different developmental schemes remains operative during the year. |  |  |  |
|  | New Scheme |  |  |  |  |  |  |  |  |  |  |
| (viii) | Strengthening and upgradation of security arrangement | Reinforcement of existing security arrangements by modernization of overall security system. |  |  | 1) Installation of a full size live Luggage X-Ray machine. 2) Installation and commissioning of : a) Electronic Turnstile Gate System; b) Integration of LAN to 1st & 2nd floor of the Administrative Building. c) Full time training on Turnstile Gate System for a period of three months. 3) Installation of Intercom telephones with security control room for better and quick communication. 4) Installation of Smoke detector ad automatic Fire alarm system – 5) Installation of Electronic sensors and Infra-red alarm system. 6) Arrangement of Hand held metal detector in each gallery. 7) Computerized Photo-Ticket entry system. 8) Digital Video Recording system. | To control the activities of anti-national forces by the installation of high-tech equipments in important galleries and strategic places. |  |  |  |  |  |
| (ix) | Programme of Education and Mass Communication etc. | To educate the ordinary public and to make them aware of their past cultural heritage and natural history. |  |  | 1. Setting up of a gallery on the ‘History and Development of the Indian Museum’. 2. Setting up of a new ‘Children’s Corner’ 3. Installation of air-conditioned film and slide library 4. Organisation of museum workshops in the rural areas. 5. Construction of additional space of the Auditorium and Exhibition Hall. 6. Introduction of school linked Museum bus service. 7. Establishment of mini lecture room-cum-storage 8. Procurement of Hi-tech appliances and equipments. | It will educate and make aware the ordinary public about their past cultural heritage and natural history. |  | Through out the year. |  |  |  |
| 25. | Salar Jung Museum, Hyderabad | A museum of national importance houses rare and varied art collection from all over the globe acquired by Salar Jung I, II and III. | ###### 4.70 | ###### 7.50 |  |  |  |  |  |  |  |
| (i) | Project Building | Construction of additional floor over Western Block for expansion of Galleries. |  |  | Construction of additional floor measuring 2500 sq. mtr. For housing 4 new galleries. | It will create more space to keep the collections. |  | One year. |  |  |  |
| (ii) | Developmental works (Existing Building) | Under taking various developmental works of the existing building including reorganization of Galleries, modernization of stores, conservation of manuscripts, library etc. |  |  | - Replacement of flooring in verandas of first floor of main building. - Construction of compound wall. - Replacement of chokes with electronic ballasts. - Replacement of existing wiring in the galleries. - Supply, installation testing and commissioning of 120 TR chiller plant including dusting and control panel. - Construction of 2nd floor of CISF Barracks. - Roofing with checkered tiles for Courtyard of Central foyer. - Re-organisation of modern paintings, Founder’s Children Section, Ivory, Miniature, Rosary and walking sticks galleries including improvements to existing galleries. - Modernization of two stores. | Providing additional infrastructural facilities will enhance tourist attraction. |  | All the works shall be completed by the end of the financial year |  |  |  |
| (iii) | Cost of CISF | To reimburse the cost of security being provided by CISF. |  |  | Reimbursement of CISF Security for 12 months. | Safeguarding varied art collection housed in it, it will enhance promotion of museum movement. |  | One year. |  |  |  |
| (iv) | Upgradation of security | The security in the Museum is being upgraded by providing CCTV cameras, fire alarm system and fire hydrant system. |  |  | Amount required for upgradation of security of the museum for which the process has begun during previous year. | Safeguarding varied art collection housed in it, it will enhance promotion of museum movement. |  | One year. |  |  |  |
| (v) | Cultural and Educational Activities | Conduct of Special Exhibitions, Lectures, Workshops, Seminars and Mobile Exhibition etc. as part of the out reach activities |  |  | Educational activities like summer art camp, children week, museum week, 15 special exhibitions, seminars, workshops, special lectures, mobile photo exhibition. |  | Creating awarness of ancient culture through visual display of rare and varied art collection |  | The process planned for the year shall be completed by the end of the year |  |  |
| (vi) | Computerization | Computerization of artifacts and office automation. |  |  | Digitization of all the objects and the networking to the reserved collection. |  | It will enhance efficiency in reference and data retrieval. |  | The process planned for the year shall be completed by the end of the year |  |  |
| 26. | Indira Gandhi Rashtriya Manav Sangrahalaya, Bhopal | A museum conceived as a growing movement to depict the story of human kind in time and space highlighting human biological and cultural evolution | ###### 1.90 | ###### 5.00 |  |  |  |  |  |  |  |
| (i) | Maintenance and strengthening of indoor museum with extensive galleries. | Develop infrastructure facilities for achieving the objectives of documentation, display and dissemination of rich and diverse cultural patterns of India through Education and Outreach activities and Operation salvage. |  |  | A: Infrastructure Development Upgrade the visitor facilities in the 200 acre museum campus: expansion of road network, sewerage systems, electrical installations, additional drinking water facility and toilets, children’s park etc. Building for exhibition on ‘India and the World’, Building for ‘National Documentation Centre and Archive for Intangible Cultural Heritage’ and a 100 bedded artisans dormitory will be constructed. |  | Additional facilities will provide further impetus in attracting cultural tourists for indoor museum. |  | The process of calling tender will be done in 1st quarter and the work has to be undertaken in 2nd, 3rd and 4th quarter. Field trips will be organized in each quarter for collection of material culture objects and house types. |  |  |

|  |  |  |  |  | Up-gradation of indoor galleries: Indoor museum galleries would be upgraded with additional exhibits and by providing interactive kiosks. Four more galleries will also be developed with thematic presentations of diversified aspects of Indian culture. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Open air exhibitions: to be strengthened with traditional house types from Gujarat, West Bengal, Rajasthan, Haryana, Nilgiri Hills, Western Ghats, Islands and also from N.E. States. |  |  |  |

|  |  |  |  |  |  | Regional Centre, Mysore to be strengthened with equipments and paraphernalia. Strengthening of archival materials to be made to collect nearly 1000 ethnographic specimens from various communities of India. B. Education and outreach programmes to be strengthened by organizing. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | a. A variety of Do and Learn museum education programme with direct involvement of tribal/ folk artists to promote the vanishing aspects of traditional knowledge and technologies. b. 10 Periodical exhibitions in various parts of India. c. 5 Artists camps and workshop. |  |  |  |
|  |  |  |  |  |  | d. 10 seminar/ symposia/ museum popular lectures. e. 5 Performing Art Presentations of classical, folk and tribal performing art forms in India. f. Documentation of intangible Cultural Heritage of India |  |  |  |
|  |  |  |  |  |  | g. Publications of series on intangible Cultural Heritage of India and other occasional publications/ journal. h. nter-disciplinary training course on Ethno-Museum Education. |  |  |  |
|  |  |  |  |  |  | C. Operation Salvage. Take up collaborative anthropological projects in Himachal Pradesh, Madhya Pradesh, Orissa, Karnataka and North Eastern Staes to ensure recapitulation and recirculation of vanishing or languishing knowledge systems. |  |  |  |
| 27. |  | Other Programmes (Museums) |  | 5.69 | 22.64 |  |  |  |  |
|  |  | National Research Laboratory for Conservation of Cultural Property, Lucknow | To develop the capabilities of different cultural institutions in the country in the conservation of cultural property and provide conservation services to Museum, Archives, Archaeology departments and other similar institutions. | 1.85 | 1.20 |  |  |  |  |
| (i) |  | Research in Conservation | To develop and standardize better methods of conservation |  |  | 6 projects including 2 continuing projects from the previous year will be undertaken. | New and better method of conservation developed. | Experiments will be conducted to complete the projects. |  |
| (ii) |  | Conservation service | To provide conservation services to different museums, art galleries and related departments |  |  | Conservation of maps and drawings of world heritage site CST, Mumbai. Conservation of stone sculptures and Government Museum, Mathura. Conservation of Manuscripts from Rashtriya Sanskrit Sansthan, Allahabad. Conservation of Books, Paintings etc. received from different department in the Southern Region at RCL, Mysore. Objects from other institutions will be attended to for advice and conservation as and when required. | Rendering technical advice and conservation service to cultural institutes. | Objects will be received in NRLC or conserved at sites as feasible. |  |
| (iii) | Training in conservation |  | To impart training to conservators, curators and other museum professionals. |  |  | Six months course on conservation of cultural property. Two weeks orientation workshop on care and maintenance of museum objects. Workshop on preventive conservation of ethnographic museums in the north east. | Promoting conservation services by imparting training to in-service professionals. | Advertisement to be issued, selection of participants and organization of courses/ workshops. |  |

| (iv) | Regional Conservation Laboratory, Mysore. | To render conservation services in the southern region. Upgradation and setting up of advanced conservation facilities. To undertake research programmes. |  |  | Conservation of Books, Painting etc. received from different department in the southern region. Objects from other institutions to be attended as and when requests are received. Establishment of facilities for conservation. Conservation research programmes in collaboration with National Manuscript Mission. | Preservation of valuable heritage. | Conservation work to start as the requests have already been received and proposals submitted. Purchase of sophisticated conservation equipment. Recruitment of research associates/ fellows to assist in research work. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (v) | Library & Information | Acquisition of new books, journals, indexing and cataloging. Rendering information services, bringing out bibliographies. |  |  | Strengthening of Library service and bringing out new publications and bibliography. | Acquisition of new books, journals, indexing and cataloging. Preparation of Bibliography will help the research fellows. | - Purchase of Books and Journals. - Indexing and Cataloging. - Preparation of Bibliography. |  |

|  | Development of Instrastructure. |  | Procurement of equipments and updating of facilities |  |  | Proposal to setup a full fledged training institute. Purchase of equipments, furniture and other items. | Latest equipments will be procured and infrastructure facilities updated. | It is proposed to procure latest version of XRF, XRD, Emission Spectrograph. To develop infrastructure facilities at RCL, Mysore. Steps to be taken for the construction of Training Institute. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Victoria Memorial Hall, Kolkata |  | Museum of contemporary art involved in collecting material and data relevant to a period depicting art history during the freedom struggle. | 2.30 | 7.00 |  |  |  |  |
| (i) | Preservation, Restoration and Conservation of Art Objects |  | To preserve the Cultural Heritage of Modern Indian History (Oil painting, Water Colour Aquatints, Miniature, Lithographs, Manuscripts, Coins, Medal, Arms & Armour etc.) |  |  | - Preventive Conservation of artifacts and frames – 480 oil paintings - Curative restoration/ conservation of 20 paintings - Conservation of 15 nos. antique frames - Conservation of Textile objects – 60 nos.. - Conservation, repair & binding of 30 old rare books of library/Archive. - Conservation of 10 metal objects. - Technical assistance to other organizations like Raj Bhavan and Bhaskar Bhavan. | Protecting the rare and varied art objects will safeguard and enhance the life of rare and precious art collections. | Throughout the year. |  |
| (ii) |  | Domestic Exhibition | To familiarise the public at large about the richness of the collections and to communicate our past history, culture and aesthetics and atleast one traveling exhibition in any one of the Metropolitan cities in India. |  |  | Four exhibitions on topics related to the collection of Victoria Memorial in bringing out catalogue of the exhibition. One traveling exhibition. | Creating Past history, culture and aesthetics awareness among the masses. | During the year |  |

| (iii) | Publication | To bring out high quality publication and some authentic catalogue on our unique collections of works of European artists and to create awareness of about our culture, history, heritage and aesthetics. |  |  | - Masterpieces of Victoria Memorial. - Catalogue of Arms & Armour and oil paintings - Catalogue on Persian Manuscripts - Reprinting of VM publications and photos. | To create awareness of about our culture, history, heritage and aesthetics. | Throughout the year. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (iv) | Strengthening of Security | To safeguard the artifacts and the monument from vandalism and theft and to protect the cultural property |  |  | - Installation of Firefighting system - Installation surveillance system and strengthening surveillance. - Installation of 10 feet height ( 3 Km. radius) barbed wire fencing on the perimeter wall for protection - Fire detection / fire fighting system. - Deployment of Calcutta Police/ CISF from manning, the 3 perimeter gates, Queen’s statues and the main building and the collections kept in the galleries stores and garden spread over 64 acres. | Safeguarding and protecting the precious and rare artifacts. | Throughout the year |  |
| (v) | Setting up/ Modernisation of galleries and storage of art objects including additional lighting installation and air conditioning. | To restructures, remodel all the galleries of the Memorial with proper display, lighting system and air conditioning. |  |  | Modernization of stores 72 and 74, North Porch rooms and Study collections for oil, paper and metals and the Archive and plan for three galleries. | This will attract more cultural tourists. | Throughout the year |  |
| (vi) | Acquisition (Art Purchase and procurement of art objects and artifacts) | To augment our existing collection of artwork through Art Purchase |  |  | Acquisition of Art objects (Kalighat Paintings, paintings of the artists of Bengal School – Abanindranath, Nandalal Bose, Jamini Roy and their students art work of other modern Indian masters. Other historical objects, objects of artistic and historical value relevant to the areas of concern of V.M. | To fill up the gaps of museum collection by purchase. | Through out the year. |  |

| (vii) | Educational Programmes | To organize national and international seminars, workshop, sit and draw competition, quiz contest, art camps, monthly lectures, educate your parents’ programme, to cater informal education to children of under privileged and physically challenged children in collaboration with NGOs. |  |  | Guided tours and special lectures for the school children, VIPs and others. 12 special monthly lectures. 30 Nos sit and draw competitions for WCP. 20 Nos Quiz Competition for school children. 8 seminars and workshops on 18th and 19th Century History, Culture and heritage in collaboration with colleges, Universities and NGOs. One day seminar cum workshop on the “Bengali School of Paintings”.4 poets’ meet. Purchase of 150 books and journals for the reference library. 4 Nos art camp and workshops involving eminent artists and school children. Two programmes on “Educate Your parents” and Other Programmes to cater informal education to children of underprivileged and physically chalanged children. | To cater informal education to children of under privileged and physically challenged children. | Through out the year. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Allahabad Museum, Allahabad | The main activities of the museum include acquisition of art objects, reorganization of galleries and reserves enriching the library and photography unit and publication | 1.20 | 1.44 |  |  |  |  |
| (i) | Renovation of building | Road carpeting and landscaping of campus area of the Museum. Renovation of the gate complex, replacing the old time barrack in a dilapidated condition by waiting Hall, a pantry and a two room guest house. |  |  | It will strengthen the security of the Museum. Additional space will be created for storage and the courtyard after modernization will give a better look | Additional facilities to boost cultural tourism. | The work will be got executed through CPWD within a time bound frame | Progress dependent on timely availability of funds |
| (ii) | Library | To fill up gaps in the number of journals and volumes of sets acquired by the museum, to microfilm certain books and journals which are not available by sending a team consisting of Museum personnel and to acquire books and journals of importance to enrich the Museum library. |  |  | It will meet the increasing demand of scholars for availability of latest books on various subjects for their study and research work and also enrich the library | Development of library activities will attract more scholars, historians and art critics. | Through acquisition of books from reputed publishers/ book -sellers after obtaining the recommendations of the Library Book Purchase Committee during the year | Additional books will be acquired after ensuring that the new books do not already exist in the library. |
| (iii) | Modernisation of galleries | To mount a panorama of civilisations of Middle Ganga Valley and setting up of a new diorama in the Archaeological Gallery to show the advent of man in the Belan Valley. |  |  | Modernization work will be carried out to provide better knowledge of our ancient culture/ heritage | Creation of a world class museum | During the course of the year. |  |
| (iv) | Acquisition of Art Objects | To acquire art objects for the Museum through Art Purchase Committee in its meeting to be held at suitable intervals during the year 2007-08. |  |  | To augment Museum’s collection of antiquities with rare objects. | It will attract more visitors. | The antiquities will be acquired on the recommendations of the Art Purchase Committee comprising experts. | It will be ensured that no fake antiquities will be acquired. |
| (v) | Educational and culture activities | A course on Indian Culture and Tourism is to be arranged; national seminars and further various cultural programmes will be sponsored during the year and Children week in November, 2007. |  |  | This is an ongoing programme and efforts are made to improve the quality and quantum of its syllabus by inviting reputed and eminent scholars to attract better brain. | It will provide awareness of Indian Culture and Tourism. | The selection of candidates will be made through an Entrance Test and after preparing a merit list. |  |
| (vi) | Exhibition and display | To encourage the budding artists of the country and to increase the knowledge of religion and culture of people of North Eastern Region |  |  | To set up a gallery of the evolution of man in the Vindhyan Ganga Region through Diorama. Some replicas of important stupas etc. are proposed to set up. Besides exhibition according to a proposed programme will be organized. | Promoting budding artists; creating awareness of Indian art forms among the masses of North Eastern Region. | After the theme of an exhibition is finalized, the relevant material is collected and the exhibition is mounted | To improve the standard of the exhibition, modern display stands have been acquired. |
| (vii) | Security surveillance and safety measures | To implement the recommendations of the Security Committee, appointed by the Government of India in order to strengthen and security and safety of Museum objects. |  |  | To strengthen the security surveillance of the Museum by acquiring various equipments such as close circuit T.V. , Metal detector, Fire alarm system and fire extinguisher etc. | Safeguarding Museum objects from theft and fire. | The necessary equipment will be acquired as per prescribed rules and procedure | This will increase security and safety of the Museum objects and antiquities |
|  | National Museum Institute of History of Art, Conservation & Museology, New Delhi | To provide education and training in the specialized areas of art, history, conservation and restoration of artifacts and their display and upkeep in museum. | 0.17 | 3.50 |  |  |  |  |
| (i) | Academic Programme | Dissemination and advancement of knowledge in the fields of History of Art, Museology and Conservation. |  |  | Conducting of courses by admitting students to M.A. courses (55 seats) and Ph.D. courses (12 seats) as well as running three short terms courses – two in English and one in Hindi (about 250 participants in all). | Advance knowledge in field of History of Art and Museology imparted to the Specialized manpower | The maximum duration of M.A. course is 2 ½ years and Ph.D. is 5 years. The short term courses are for a duration of 5 months. |  |
| (ii) | NOIDA Project | Establish its own premises, as, presently it is using the premises of National Museum. This will help in the expansion of the institution in terms of class rooms, library and research facilities, hostels and ultimately help in realising the goals set for it. |  |  | Construction work will be taken up during the year. | Enhancing further academic activities for the institute. | Based on the designs and the estimates submitted by the CPWD and subject to approval of EFC. After its approval it may take 30-36 months for the completion of the building. | Timely submission of the design and estimates by the CPWD and approval by the EFC, needs to be ensured to avoid time and cost overruns. |
|  | Scheme for financial assistance for ‘Promotion & Strengthening of Regional & Local Museums’ | To promote the strengthening and modernization of existing museums at the regional, state and local level. | --- | 9.00 | Out of about 150 proposals received from the different museums every year, 50 to 60 museums receive grant every year. | Promoting museum movement in the country by providing financial support to small museums. | Advertisement for the grant would be published during month of May/ June 2007 and Expert committee meeting will meet in the month of Oct/Nov, 2007 and the grant is released before March 2008. | Release of funds depends upon the number of complete/ proper proposals received from different museums |
|  | Scheme for Modernization of Museums in Metro Cities | In order to bring some of the Museums in the Country at par with the best in the World. | --- | 0.50 | A token provision of Rs. 50.00 lakh has been made. |  |  |  |
|  |  | Total (Archaeology, Archives, Museums) | 255.97 | 195.64 |  |  |  |  |
|  | Public Libraries |  |  |  |  |  |  |  |
| 28. | National Library, Kolkata | To serve as a repository of all reading and information materials produced in India as well as abroad concerning India | 15.40 | 7.00 |  |  |  |  |
|  | Collection Building & Book Production Statistics | To collect books and other printed materials published in India, Acquisition of Foreign Books and Periodicals |  |  | National Library targets to acquisition 35000 Indian publications,3500 foreign books and 680 titles of Foreign journals . | Enhancement of readership and dissemination of knowledge | Acquisition thorough purchases and receipts/ deposits under the Delivery of Books and Newspapers Act, 1954 | The deposits under the Delivery of Books and Newspapers Act, 1954 depend mainly upon cooperation by publishers |
|  | Readers Services | Retro-Conservation, Digitization and Modernization of Laboratory, Preservation Computer Units |  |  | It also intends to digitize 15 lakh pages of old and rare books and retrospective convertion 4 lakh bibliographical records in digital format. | It will preserve the old brittle reading books and upgrade the preservation, conservation and computer units of the Library for readers service. | Through out the year |  |
|  | Strengthening of Administration | CCTV Installation,Furniture & interior decoration of Bhasha Bhavan etc. |  |  | CCTV on security angle, Furniture for shifting of all divisions to Bhasha Bhavan | To vacate the main old Building for upkeeping it as Museum. | During the year |  |
| 29. | Delhi Public Library | To provide free library and information services to the people of NCT of Delhi and also to provide mobile library services in rural area of Delhi. | 6.90 | 2.50 |  |  |  |  |
| (i) | Collection Developments | The basic objective of DPL is to provide free library and information services to people of Delhi. In order to achieve this objective, DPL proposes to strengthen its collection development in all the service units. Besides this updating of Reference Collection of Central Library and Sarojini Nagar will also be taken up by acquiring new reading materials. |  |  | Around 4000 titles (50,000 Multiple Copies to be purchased for the DPL system in English, Hindi, Urdu, Punjabi, Besides audio & video crassest also. | Addition of new collections will sustain library movement in Delhi for imbibing reading habits. | Continuous process and purchase will be made in all four quarters | Delay in constituting a Book Advisory Committee. |
| (ii) | Conservation and Preservation | Binding care and repair of books and other reading materials are continuous activity of DPL. Preservation of documents is a compulsion in a library for posterity purpose. |  |  | Around 40-50 thousand volumes are to be bound through commercial book binders. | For posterity of old and rare collections, this will lead to add more library membership for getting free library services. | After completing formalities the binding work will be executed from 2nd quarter onwards. |  |
| (iii) | Modernization and IT Development | Modernization of library activities is the continuous process of DPL. It is proposed to augment the computer system of library, which requires more computer, server, scanner, operating system, ISM etc. for creating of database in other Indian languages. |  |  | It is proposed that the Hindi version of DPL's Website will be made so that more number of reader can access to DPL. It is further proposed to acquire new library software, computers and server and other accessories for automation of library activities and to strengthen the existing computerisation activities. | Providing Better facilities to the readers. |  |  |
| (iv) | Construction of Library Building at Ashok Vihar & Patparganj Plots. | Delhi Public Library proposed to construct the library buildings in the two vacant plots located at Ashok Vihar & Patparganj during this financial year. After getting the building plans and estimates from CPWD. |  |  | CPWD is preparing the building plans and estimates and expected that the construction of library building at Patparganj will be started from 2007-08. | This will enhance the library activities in the new areas. | Throughout the year | Possible delay in getting NOC from DDA and building Plans from CPWD. |
| 30. | Raja Rammohun Roy Library Foundation | To promote and support public library movements in the country. | 2.10 | 25.00 | Raja Rammohun Roy Library Foundation through their matching schemes intends to assist 9000 libraries to acquire around 3 crore books, 112 libraries with the provision for mobile units, 2800 libraries with storage materials, 67 organisations for providing awareness, orientation to library professionals,41 libraries for supply of Audio-visual aid and supply of computers for Automation and 85 libraries for construction of library buildings. | Strengthening of the public library movements of the country and increase in the reading habits of citizens | For Matching Schemes: The library committee is responsible to chalk out the programme to implement the different schemes of the foundation. I Quarter: to hold SLC meeting to finalise the programme & implementation of residual proposals for previous year. Inviting proposals. | The timely contributions by the State Governments under the matching schemes is have a bearing on finalisation purchases |
|  |  |  |  |  | Under the non-matching schemes, the Foundation intends to give assistance to voluntary organization to set up 340 libraries, assist 157 children libraries or children section of public libraries, 61 libraries to establish children,s corner, procure 1.5 crore books for 469 State Central Libraries and District Libraries etc. 246 libraries to motivate youths. |  | II Quarter : Selection of books and libraries under different schemes. III Quarter: Implementation of different proposals. IV Quarter: Review and implementation. |  |
| 31. | Other Libraries |  |  |  |  |  |  |  |
| - a | Central Reference Library, Kolkata | To implement (a) Compilation and publication of the Indian National Bibliography (in Roman script and respective language scripts) which is a bibliography of current Indian Publications in Indian languages recognized by the Indian Constitution and in English and (b) Compilation and Publication of Index Indiana. | 1.10 | 0.40 |  |  |  |  |
|  | Indian National Bibliography | a. Publication of Indian National Bibliography Annual Volume 2005 b. Monthly issue of INB 2006 January to December |  |  | 250 copies of Annual Volume of INB 2005 12 monthly issues of 2006 INB | 4 months 12 months |  |  |
|  | Index Indiana 1999-2000 | Compilation and Publication of Index Indiana. |  |  | 100 copies to be printed | 6 months |  |  |
|  | Khuda Bakhsh Oriental Public Library, Patna | This Library has been evolved out of a personal collection of Maulvi Mohd. Bakhsh who was a man of letters with a great passion of books. It houses over 20000 manuscripts and some rare printed books. | 1.60 | 2.50 |  |  |  |  |
|  | Acquisition: Purchase of Books, manuscripts, microfilms, Video & Audio Cassets | To acquire books, manuscripts, microfilms, Audio & Video CDs for use of readers |  |  | Purchase of 5000 printed books, 50 manuscripts and 120titles of journals | To preserve them for future generation. |  |  |
|  | Research & Publication: Publication of rare material , Printing of Catalogue, Research seminars, Lectures & Cultural programmes, Khuda Bakhsh Research Fellowships and Publication of Quarterly Journal. | To bring out critical editions of manuscripts, publish books of rare value, lectures by distinguished scholars. To acquaint the outsiders with the hidden treasure descriptive catalogue. Organization of seminars, lectures of distinguished personalities. Fellowship and Scholarships to renowned scholars. |  |  | Publication of 20 books. Printing of 2 volumes of descriptive catalogue. National Seminar – 1 Annual Lecture – 1 Extension Lecture – 4 Popular Lecture – 12 Senior Fellowship – 3 Junior Fellowship – 7 Publication of 4 issues of Quarterly Journals. | Masses will be benefited. | Throughout the year. |  |
|  | Conservation & Preservation : Preservation Laboratory and development of books preservation & reprographic facilities | Preservation Lab. For routine maintenance, curative as well as preventive and preservation. To keep the books in the good condition. |  |  | Routine activities for preventive and curative preservations of books and manuscripts. Getting printed books and manuscripts bound on contract basis. | To keep the literature in good condition. | Throughout the year. |  |
|  | Moderanisation & Automisation: Computerisation including Dizitisation of Manuscripts, Purchase of equipment & furniture and moderanisation of stack area and reading facilities. | For dizitisation of manuscripts and collection of manuscripts, to keep pace with the developments around the country and the world and to add new modern stacks. |  |  | Dizitisation of 6 lakhs pages of manuscript Establishment of a reading room. Purchase of equipments for library, computers, printers and book stacks. | To provide complete picture of ancient manuscripts/documents to the Research Scholars. | Throughout the year. |  |
|  | Events & Exhibition: Founder’s Anniversary & Foundation day | To observe the birth & death centenary of the Founder and Foundation day of the library. |  |  | Organisation of Founder’s day celebrations. | Promotion of Art & Culture materil acquired by the founder. |  |  |
|  | Cultural Exchange: Exchange of visits with counterpart abroad | To invite scholars/librarians from abroad under CEP and to visit countries to see their collection. |  |  | Visit abroad under Cultural Exchange Programme | Will establish mutual exchange relations |  |  |
|  | Thanjavur Maharajas Serfoji’s Saraswati Mahal Library, Thanjavur | A priceless of repository of culture and knowledge, it was conceived as the Royal Palace Library in the 16th century. | -- | 0.50 |  |  |  |  |
|  | Publication of books from the manuscripts in Sanskrit, Tamil, Marathi etc. | To translate, transliterate the manuscripts and to bring out books. |  |  | 50 books | For the benefit of scholars from abroad and various parts of India. | Throughout the year. |  |
|  | Conservation | To apply citronella Oil to Palm leaves and to preserve the Paper manuscripts/ Valuable Old books etc. |  |  | To clean and apply 600 leaves Manuscripts perday and to clean and preserve 20 books daily. | To preserve them for future generation. | Throughout the year. |  |
|  | Micro Film | Microfilm of Manuscripts and rare books for preservation. |  |  | 600 frames daily | To preserve them for future generation. | Throughout the year. |  |
|  | Computerization | To printout books from the manuscripts as edited by languages experts. |  |  | 50 books every year | To avoid printing of books from private firms. | Throughout the year. |  |
|  | Research activities | Visiting and consulting other libraries for reference work. Collection of Manuscripts from Public copying and transcribing of M/s for Publication and Preservation. |  |  | It is a long standing process of every year. |  |  |  |
|  | Central Tibetan Library | Aim to acquire and conserve Tibetan books and manuscripts and to provide intensified reference service as well as Centre for Tibetan manuscripts, paintings and object of Arts. | 0.55 | -- | The ongoing activities of the Library continued to provide research facilities including documentation and written material for regular courses on Buddhist philosophy and Tibetan tradition. | Dissemination of all aspects of Tibetan civilization and also Buddhist philosophy in India. | Through out the year. |  |
|  | Rampur Raza Library, Rampur | The main objective of the library to acquire and conserve Indo-Islamic manuscripts, miniatures, books and other objects of arts and science in the library and to serve as a centre of reference and research and also act as a centre of Arts for International importance. | 1.15 | 2.00 |  |  |  |  |
|  | Publication & Printing | Publication of books of text of Arabic, Persian and Sanskrit manuscripts. |  |  | Proposed to publish 6 to 8 books of text of rare manuscripts. | To preserve the literature for academicians and scholars. | Through out the year. |  |
|  | Preservation and Renovation of two Heritage Buildings. | Two historical palaces of Raza Library viz Hamid Manzil and Rangmahal are monuments of archaeological importance. They involve scientific repairs of archaeological or special nature. |  |  | Repair and restoration of badly damaged or fallen ornamental ceilings of Darbar Hall of Hamid Manzil. | To preserve the palaces of the international importance. | Through out the year. |  |
|  | Deployment of CISF | To watch and ward of the library assets. |  |  | Deployment of 26 personnel of CISF for safety and security of Library. | Safety and security of Library collections and assets. | Through out the year. |  |
|  | Renovation and up gradation of infrastructure and installation of Fire Protection Equipments | To save the Library building from accidental fire. |  |  | Fire safety equipments will be installed at par the National Museum. | To save the assets and collections of Library from fire. | Work will be completed in phased manner. |  |
|  | National Mission for Manuscripts | Aims at cataloguing, conserving and collecting the invaluable manuscripts from all over the country and to strengthen manuscript resource centers, manuscript conservation centers and digitization of catalogues and prestigious manuscripts. | -- | 8.50 |  |  |  |  |
| i | Mapping, Listing, Cataloguing and awareness campaign | Indian Manuscripts are scattered in known & unknown collections across the country, creations of National data base. |  |  | To cover National Survey in 5 more states, Post survey in 7 more states. | Survey, documentation and cataloguing of Indian Manuscript and maintain accurate and up-to-date information about them. | Throughout the year. |  |
| ii | Formation of MRCs/MCCs | To monitor, Control of the work of identifying, documenting, protecting and making accessible of the manuscripts |  |  | To increase MRCs to 55 from 46 and MCCs to 40 from 33. |  | Throughout the year. |  |
| iii | Conservation and training | To conduct workshops to collaborate with digitization to conserve the identified manuscripts. |  |  | To conduct 9 more workshops |  | Through out the year |  |
| iv | Training on Manuscript logy and Paleography | Basic Course, Advance Course, Gurukula Scheme |  |  | To impart: 5 Basic Course, 5 advanced course and train 2000 students | To educate the staff and others in the field of Manuscript logy and Paleography. To protect the old manuscripts for the future. | Through out the year |  |
| v | Digitization of Manuscripts | The Mission aims to safeguard the knowledge contained in manuscripts by developing a consists policy for digitization. |  |  | To carry out second phase of Pilot project of Digitization all over India |  | Through out the year |  |
| vi | Cataloguing & Documentation | Publication of cataloguing books, cataloguing and documentation of Manuscripts |  |  | To document electronically 20 lakh more data | Giving an overall picture of documents/ manuscripts available in the library for the research scholars. | Through out the year |  |
| vii | Research and Publication | Publication of Kirti Rakshana – The NMM by – Monthly News letter, Publication of Tattvabodha and Samrakshika papers, Translation |  |  | To publish 6 issues of by monthly news letters as Kriti Rakshana | To bring out the activities of the Mission for the research scholars and interested people. | Through out the year |  |
| viii | Public Outreach | To impart training and knowledge about the National valuable assets of manuscripts through debates etc. at district levels, schools, colleges etc. |  |  | To conduct 12 programme of lectures at Delhi and 12 in various parts of India. Manuscripts extension programme for school children in West Zone (Gujarat, Rajasthan, Maharashtra, MP and UP) | To disseminate manuscript logy among school children. | Through out the year |  |
|  | Setting up of a National Mission on Libraries, leading to the formation of a Commission | To pointedly address the problems of Public Libraries and to upgrade the infrastructure and technological environment of the Public Libraries within a time frame | -- | 0.50 | Token provision has been made to initiate the spade work. |  |  |  |
| (a) | State Central Library, Mumbai | To acquire books and periodicals under the provision of press and registration of Books Act, 1867 and the delivery of Books Act, 1954 and preserve them for posterity. | 0.30 | 0.20 |  |  |  |  |
|  | Modernization/ computerization/Digitisation /Up gradation of state central library | To digitize rare books and manuscripts: Computerisation/ Retroconversion of DBA books |  |  | In the first phase 10 lakh pages of old / rare books/ manuscripts shall be digitized. Approx. 4 lakh DBA books are to be computerized. | Digitised / Retroconversion material will be displayed on internet. | Continuous process. |  |
| (b) | Conemara Public Library, Chennai | It is one of four recipient of Public Libraries under the provisions of the Delivery of Books and Newspapers (Public Libraries) Act of 1954 to receive all materials published in India free of cost. It serves as a UNESCO information center and receives all the publications of UNESCO. It is also a depository for Asian Development Bank Publications. | 0.30 | 0.60 | - Standard works excluding pamphlets, children books etc – 10815. - Newspapers – 272 - Periodical titles etc. – 3106 - The work of Gazette Notification, bulletins, maps, children’s books etc. will be accessioned, processed and maintained. | To provide the reading material received under D.B. Act required by the readers, researchers and scholars. | Throughout the year. |  |

| 30. | Provision for Project/ schemes of N.E. Region and Sikkim |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| a | Project/ Schemes for promotion of Art and Culture | To promote, disseminate and protection of art and culture in NE States | -- | 27.65 | Organizing various programmes in the field of art and culture in various cities of the North Eastern States. | Increase awareness of Indian art and culture and tradition in North Eastern Region. | During the entire year |  |
| b | Archaeology, Archives and Museums | To promote cultural activities in the fields of Archaeology, Archives and Museums | -- | 23.45 | Development of Museums in North East Region and providing financial support to NGOs in N E R in the field of Archival activities. | Creating awareness of ancient culture of India in NER. | During the entire year. |  |
| c | Libraries | To promote Library activities in the NER | -- | 4.60 | Development of Library activities in North East Region. | Inculcate reading habits through library movement. | During the entire year. |  |
|  |  | Total ( provision for NER) | -- | 55.70 |  |  |  |  |
|  |  | TOTAL (Revenue) | 375.61 | 507.00 |  |  |  |  |
| Building projects of attached / subordinate offices |  |  |  |  |  |  |  |  |
| 1. | National Gallery of Modern Art | (i) NGMA’s new Wing , New Delhi | --- | 4.00 | Work is under progress |  | Will be completed during the year. |  |
|  |  | (ii) Manikavelu Mansion, NGMA, Bangalore |  |  | Capacity creation for the galleries. |  |  |  |
| 2. | National Archives of India |  | --- | 5.00 |  |  |  |  |
|  | (i) | Gas based automatic fire alarm and extinguisher system. |  |  | Work is under progress | Creation of additional office accommodation and storage for records. |  |  |
|  | (ii) | Completion of remaining works such as Air Conditioned Plant, Jaipur. |  |  |  |  |  |  |
|  | (iii) | Construction of functional building of record center, Bhubaneswar |  |  |  |  |  |  |
|  | (iv) | Proposal for acquiring 0.21 hectares of land adjacent to Record Centre, Pondicherry. |  |  |  |  |  |  |
|  | (v) | Addition and alteration of works of NAI Main/ Annexe building, Record Centre Jaipur and Pondicherry and Regional Office Bhopal. |  |  |  |  |  |  |
|  | (vi) | Upgrading diesel generator set and A/C plant for NAI. |  |  |  |  |  |  |
|  | (vii) | Replacement of windows of all floors of NAI Annexe. |  |  |  |  |  |  |
| 3. | Anthropological Survey of India |  | --- | 7.00 |  |  |  |  |
|  | (i) | Construction of Office building of Eastern Regional Centre at Salt Lake, Kolkata |  |  | Work is under progress | Creation of additional office accommodation. |  |  |
|  | (ii) | Acquisition of land and construction of Guest House at the camp Office, New Delhi. |  |  |  |  |  |  |
|  | (iii) | Construction of residential quarters guest house and Museum of International Standard etc. at Udaipur |  |  |  |  |  |  |
|  | (iv) | Construction of Guest House Library, Museum and Conference Hall of North East Regional Centre at Shillong. |  |  |  |  |  |  |
|  | (v) | Construction of residential quarters and guest house of North West Regional Centre, Dehra Dun. |  |  |  |  |  |  |
|  | (vi) | Construction of an International standard guest house NA ancient lab. At the SRC, Mysore. |  |  | Work is under progress |  |  |  |
|  | (vii) | Acquisition of land for Construction for Office Building of the SRC, Jagdalpur and Ranchi Fiedid station |  |  | Work is under progress |  |  |  |
|  | (viii) | Procurement of land and construction of Museum at Central Regional Centre, Nagpur. |  |  |  |  |  |  |

| 4. | National Research Laboratory for Conservation of Cultural Property, Lucknow | i. Training Institute in conservation at Lucknow. ii. Dating & Authentication at Regional Conservation Laboratory, Mysore | --- | 6.00 | Work is under progress | For important activities of Laboratory, Training Instt.-cum-Hostel/Guest House at NRLCCP, Lucknow. | Works undertaken by CPWD | Completion of works depends on the efficiency of CPWD. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5. | National Museum |  |  |  |  |  |  |  |
|  |  | Shifting of Air condition plant etc from National Museum campus etc. and Dismantling of ASI structure and start of construction of III Phase of National Museum Building. | --- | 6.00 | Work still to be taken up. | Infrastructure development and capacity creation for National Museum. |  |  |

| 6. | National Library |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | i. Construction of readers’ hostel | --- | 1.00 | Work still to be taken up. |  |  |  |  |  |  |
|  |  | ii. Construction of Type-II & III Quartes. |  |  |  |  |  |  |  |  |  |
|  |  | iii. Construction of Garden Superintendent Office-cum-Godown. |  |  |  |  |  |  |  |  |  |
| 7. | Archaeological Survey of India | Construction of building and staff quarters for ASI at Dharwad, office building at Nagpur, Mysore, construction of Institute of Archaeology at Greater NOIDA, linear building at 24, Tilak Marg, New Delhi. Purchase office complex at Raipur. Construction of office building for ASI at INA, New Delhi. |  | 21.00 | Work is under progress | Accommodation problem of ASI staff shall be solved. |  |  |  |  |  |
|  |  | Total (Building Projects) | --- | 50.00 |  |  |  |  |  |  |  |
|  |  | Grand Total (Art and Culture) | 375.61 | 557.00 |  |  |  |  |  |  |  |