| 1. | a). Secretariat Social Service | To modernize the accommodation for efficient functioning of the Ministry and also provide Information Technology support. Maintenance of the office equipments and procurement of stationery. | 14.20 (a+b) | 3.40 (a+b) | Modernization of about 5 rooms in the Ministry, upgradation of the LAN, Network in the Ministry. Increased use of office automation equipment in the Ministry. | 3 rooms in the Ministry were taken up for modernization. 90 old and obsolete computers were replaced. LAN network upgraded by augmented its capacity from 100 nodes to 300 nodes other office equipments were purchased on need basis | 15.30 (14.09+ 1.21) | 2.49 (0.97+ 1.52) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | b). Central Secretariat Library (CSL) | To provide information and research services to Academicians, Research Scholars and Policy Planners. It is the main reference library for all purposes. |  |  | To install computers in CSL and Tulsi Sadan Library, conducting two training programmes, acquisition new books. Titles to be added in Regional Resource Centre TSL, Face lifting of R.K Puram Library branch, installation of security system in CSL, digitization of micro film rolls, conservation and preservation of rare books etc. | 25 computers purchased & installed and purchased /installed softwares in computers. The acquisition of microfilms rolls from British Library, London is under progress. Seminar/workshop also organized. Hosted CSL data in web. |  |  |  |
| 2. | Zonal Cultural Centre | Aims at the promotion of Grassroot Culture and Cultural Kinships which transcend territorial boundaries and to arouse and deepen awareness of local culture. | -- | 14.00 |  |  | -- | 26.16 | Includes 30% provision towards pro-women, and 20% provision for ST population |
| (i) | National Culture Exchange Programme | Exchange of artists, Musicians, performers, & sculptors etc. between different regions within the country for the promotion of rich cultural heritage of India. |  |  | About 700 programmes would be organized benefiting a large number of artists. | About more than 572 programmes organized benefiting a large number of artists deployed at fairs, festivals, cultural events to dissimilate the cultural diversity across the country. |  |  |  |
| (ii) | Documentation | Documentation of various folk & tribal art forms particularly the vanishing art forms for their proper preservation. |  |  | Various folk & tribal art forms, great masters of member states will be documented as per advice of Programme Committee and research oriented projects would be taken in hand for publication | More than 82 documentation works have been taken up. |  |  |  |
| (iii) | Lok Tarang Folk Dance Festival 2009 | This festival is organized for Republic Day Celebrations during January each year for the promotion of our rich cultural heritage & national integration |  |  | This festival provides a unique performance opportunity for the folk artists from various parts of country at the national level. Besides this a large number of school children participate in R.D. Parade | Necessary preparation requied for organizing the Lok Tarang to be held from 23rd January to 28th January, 2009 was completed. |  |  |  |
| (iv) | Kurukshetra Utsav | Celebrated on the occasion of Geeta Jayanti Samaroh at Kurukshetra-a Sacred place related to Mahabharta |  |  | Very suitable occasion for the promotion of Indian art & culture. Classical & folk artists perform benefiting large number of people. Besides this a large number of craft persons are given opportunity to display & sell their products | NZCC in collaboration with Kurukshetra Development Board organized Kurukshetra Utsav and Geeta Jayanti Samaroh. |  |  |  |
| (v) | Guru Shishya Parampara | For the promotion & preservation of our Fast vanishing art Forms |  |  | Not only Gurus but shishyas are also benefited. About 100 gurus with 500 shishyas are likely to be benefited during the year. Art forms are decided in Consultation with State Governments from time to time. | More than 184 Gurus and 1172 Shishyas from various art form alongwith their shishyas benefitted under the scheme. |  |  |  |
| (vi) | Theatre Rejuvenation | Providing an opportunity to the theatre artists to stage plays & other theatre activities. Also interacting with each other on the Common platform |  |  | About 100 theatre groups would stage their plays and more than 1000 artists and a large number of people would be benefited in promoting the theatre. Workshops to promote theatrical skills will also be held. | ZCCs have conducted various programmes in mode of theatre shows, theatre festivals, workshops and mythological theatre festival. More than 185 plays have also been staged. |  |  |  |
| (vii) | Young Talent Artists Scheme | To recognize & encourage young Talented artists in various folk Art forms |  |  | About 100 folk art forms would be selected & competitions would be held involving sufficient number of upcoming artists & public. | More than 77artistes were benefited under the scheme. |  |  |  |
| (viii) | Shilpgram | Shilpgrams established by ZCCs are playing very significant role for the promotion & preservation of Indian Art & Culture and providing platform to the talented artisans. The main objective is to boost the activities in Shilpgram/ Kalagram |  |  | A large number of artists & artisans are benefited. A large number of people are made aware of our rich cultural heritage. | A large number of Artisans benefited. |  |  |  |
| (ix) | Festival of the North East – OCTAVE-2008 | The objective of the proposed festival of the North East is to help the people in general and artists from the North East in particular to have a closer interaction with the rest of the country. |  |  | Around 400 artistes from North East including folk artistes, musicians, film & literary personalities etc. will be performing in a series of programmes to be organized in Trivandurm. | The N.E. festival has been held at Goa, Mumbai and Patna during Nov.-Dec. 08. |  |  |  |
| 3. | Sangeet Natak Akademi, New Delhi | The Academy devotes to the furtherance of the performing arts of India, and seeks to achieve this by arranging performances by renowned veterans as well as by talented artists of the younger generations through training programmes, award of scholarships and documentations. | 6.85 | 11.50 |  |  | 10.32 | 20.96 |  |
| (i) | Survey, Research, Documentation & Dissemination and Publication | Preservation and collection of recordings of rare traditions of Performing Arts, development of theoretical and academic knowledge of performing arts and publishing literature on performing arts. |  |  | 750 hrs of audio and video recordings, 20 audio CDs, 10 video CDs, 2200 photographs, 60 hrs of audio and video dubbing. | Targets indicating in col. 5 were achieved during the year by adding audio & video recording . |  |  |  |
|  |  |  |  |  | One national conference, Two regional seminars and 10 books, 4 journals and 12 news bulletins, 1 Annual Report and 10 monographs. 5 scholars for encyclopedia will be engaged. | Seminar held at Varanasi on Allen D Music. Two more seminars were held during the year. Books/journals/ news bulletins and annual report were published. |  |  |  |
| (ii) | National Museum of Performing Arts, Library and Archive | Development of Academe’s existing museum musical instruments, puppets, masks and other art objects into a national level museum of performing arts by acquiring a separate building / campus. To develop an exclusive archive of audio video and photographic records of performing arts of India including a parallel archive in South India by acquiring rare collections scattered in the country and expansion of Akademi’s existing specialized library. |  |  | Preparation of 3 catalogues, acquisition of 110 objects, organization of 3 workshops on restoration. Training programme in instrument and mask making, Digitization of existing archival holdings, Digitization of 22000 clippings, 2200 monographs records or 5500 photographs, | A large number of musical instruments have been acquired for the museum for which the matter for allotment of 5 acres of land in Delhi has been taken up with DDA. Training Centres for instruments making have been functioning in Kolkata and Meerut. |  |  |  |
| (iii) | National Institutes and Centres of Akademi for Specialized fields/ forms of India : Kathak Kendra, New Delhi, Kutiyattam Centre, Kerala, Chhau Centre, Baripada / Jamshedpur, Other National Projects, Jawaharlal Nehru Manipur Dance Academy, Imphal and Sattriya Centre, Guwahati | To create Kathak dancers of professional standing through well specialized training course, To upgrade and develop Akademi’s project support to Kutiyattam, Upgradation and development of the ongoing project support to Chhau Dances of Eastern region, Development of training programmes in traditional land folk theatre forms of India - Yakshagana of Karnataka, Bhagwat Mela of Tamilnadu, To create Manipuri dancers of professional standing through well specialized training course, Development of Akademi project support to Sattriya Dance and allied music and theatre traditions. |  |  | 3-4 new production of dance seminar on Kathak, The ongoing project of Kutiyattam involving a number of projects training, production, research and performance directly benefiting institutions 200 artistes and scholars. Ongoing project of Support to Chhau Dances involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. 3-4 new productions of dance dramas in a year, platforms to about 200 artistes and creating new audience for Manipuri dance in the country, ongoing project on Sattriya Dance involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. | 3 new productions by Repertory done. Imparting Kathak training to 316 students. For promotion and ancient art form from ‘Kutiyattam’ with assistance to Gurukulams in Kerala, 58 trainees have been imparted training. Also organized outreach programmes in different areas in and outside Kerala. Festival of Chhau Dance of India was held at Bhubaneswar in Feb.09. Centre for Puppetry started in Delhi. 4 new production of Dance Dramas were completed. Sattriya Centres started at Guwahati in Aug. 08. Training support to Sattriya Dance and Music continued. Nritya Parvah – Festival of Sattriya Dance was held at Guwahati. |  |  |  |
| (iv) | Festivals, Workshops and National Exhibitions 1 SNA Festivals, Workshops & Exhibitions 2. Collaborative Programmes with State Akademis, Organizations, Central Govt. Organizations & Major Cultural Institutions and Sponsored Programme (New Scheme) 3. Regular Programme in Meghdoot Theatre Complex | To preserve, promote and development of performing arts traditions in live practice on regional and national levels and support exchange of ideas, concepts and techniques nationwide. |  |  | 20 festivals and workshops in different cities 50 activities in collaboration with State Govt./academics and with central organizations in field of performing art. Fortnightly programmes of puppetry traditional theatre, film etc. Regional level celebration of Music Day, Dance Day & Theatre Day. Two regional seminars on folklore | A number of programmes were organized with State Culture Department and leading cultural institutions. Regular programmes in Meghdoot Theatre were organized on puppetry and traditional theatres. |  |  |  |
| (v) | Awards, Honours and Prizes : SNA Fellowships and Awards (Akademi Ratna Sadasyata and Puraskar) Bismillah Khan Yuva Puraskar, Yuva Puraskar , | To recognize excellence and sustained contribution in performing arts and support eminent old artists. The akademi awards fellowships and akademi award (Fellowship is restricted 30 living person) Ustad Bismillah Khan Yuva Puraskar has been constituted for the young artists of below 35 years old. The award carries purse money of Rs. 25, 000 |  |  | 33 Akademi Awards, 5 Fellowships 33 Yuva Puraskar to young artists. | Award ceremony and festival was held in March 09. Puraskar distribution ceremony and festival of award winner held in May 08. |  |  |  |
| 4. | Lalit Kala Akademi | Promotion of visual and plastic arts | 4.45 | 6.00 |  |  | 7.05 | 14.25 |  |
| (i) | Promotional activities in the field of visual & plastic art. Art Development Com. Dissmn Outgoing Exh,. National Exh. Triennale Archives Lectures & Film Camps Library Cons & Restn. Grants to State Akademis. Regional Centres | The main objectives of the Academy are to provide infrastructural facilities to the artist’s community for the development of art activities of the country especially in the field of contemporary art. |  |  | Grant in Aid to State Akademis &Art Organizations- 25 National Exhibition of Art - 1 Triennale India- 1 Exchange of Delegation Programmes under CEP- 4 Outgoing Exhibition- 4 Incoming Exhibition - 6 Mobile Exhibition- 3 Camps and Workshops- 4 Documentation, Lectures, Seminars, Archives, Library Book and Dissemination- 4 Art Festivals- 1 Art Gallery- 120 Conservation/ Restoration- 5000 | Organized various programmes in the fields of visual and plastic arts as indicated below:- National Exhibitions -1 Exchange of Delegation Progs. Under CEP- 4 Outgoing Exhibition-3 Incoming Exhibition-2 Mobile Exhibitio-4 Camps and Workshops-4 National Art week-1 Lectures, Seminar, Archives-3 Exhibition in Gallery-50 GIA to Art Organizations-6 Conservations/ restoration art works-50 National Art Festival-1 North East Exh. Under Octave-3 |  |  |  |
|  | Scholarships |  |  |  | Scholarships - 60 Fellowship - 1 | Scholarship-65 |  |  |  |
| ii | Publication & Documentation |  |  |  | 30 | Publications-16 |  |  |  |
| iii | Regional Centres |  |  |  | Programme 20 Lecture-8 | Programme -22 Lecture-8 |  |  |  |
| 5. | Sahitya Akademi | To undertake publishing & promoting Indian literature | 4.60 | 10.50 |  |  | 7.27 | 12.89 |  |
| (i) | Upgradation of Libraries and Information Services | To provide readers/ intellectuals the complete range of books and update basic information about writers and literary activities in India at one place, make documentary tele films on eminent writers and scholars in the field of literature with modern archive unit of visuals. |  |  | Purchase of books in 24 languages including foreign publication will continue Subscription and New journals to be added. The work of the Archives unit will be linked with the Akademi’s website. | Purchase of books in 24 ;anguages, subscriptions to various literary journals, retro conversion of bibliographic data continued, Akademi’s web site in English, three documentary filmsonwriter. |  |  |  |
| (ii) | Publication Schemes | The scheme to full fill the basic objective of the Akademi dissemination of Indian Literature and making available to multilingual societies of Indian Literary masterpieces from other language into their own language, histories of literature, monographs on Indian Writers, translation of important Indian and foreign classics, anthologies of poetry, short-stories, one-act plays, literary essays etc. |  |  | The publication of bi-monthly journals Samkaleen Bharatiya Sahitya (Hindi) and Indian Literature (English) and a half yearly journal Sanskrit Pratibha (Sanskrit) to continue. To initiate the project on translation vintage Indian novels from different Indian languages into English with 20 books/novels. | 190 books published in all the 24 languages recognized by the Akademi, new series of National Bibliography of Indian Literature 1954-2000 continued , other important publications as per demand by various Universities, Shiksha Missions of states were taken up on priority basis. |  |  |  |
| (iii) | Literary functions and programme | To celebrate centenaries of great writers, hold regional, national and international seminars, writers camps, workshops, symposiums etc. |  |  | 50 seminars and 150 literary forum meetings will be organized at national and international levels. | The Akademi organized literary programmes on all important Contemporary Literary topics as in the last year. |  |  |  |
| (iv) | Awards to writers | To enable young and old writers in Indian language to visit other parts than their own, send Indian writers and host foreign writer delegation under Cultural Exchange Programmes, to give award to literary works which merit appreciation and encouragement in all 24 Indian languages recognized by the Akademi, give honorary fellowships to eminent writers in recognition of their contribution to Indian Literature. |  |  | Around 30-40 young writers will avail the opportunities under this scheme. Annual Sahitya Akademi Awards in 24 Indian Languages will continue. | Around 40Young writers availed the Travel Grant scheme of the Akademi. Annual Awards were given to writers in 24 Indian languages recognized by the Akademi in the month of Feb, 2009. |  |  |  |
| (v) | Promotion of Akademi Publications\ Book Exhibition | To advertise Akademi publications through literary journals, organize and participate in book exhibitions at regional, national and international level |  |  | The Akademi will participate in around 100 book exhibitions at National/ Regional / International levels. | Participated in around 300 book exhibitions, in order to achieve a sales target of Rs.250 lakh. |  |  |  |
| (vi) | Translation schemes | Translation is the basic activity of the Akademi. Translation centre “SABDANA” to make arrangements for training of translators and train the practicing translators by conducting workshops, to do the inter-lingual research and translation, prepare a register of translators and identify titles for translations and their publications into other Indian languages and into foreign languages. |  |  | To translate and publish around 20 books. Translation of Children literature shall also continue to make available works of one language to another. | 21 Translation Prizes in languages recognized by the Akademi were given at function held in Aug. at Kolkata, the Translation Centres at Bangalore and Kolkata continued translating important books in various Indian languages and vise-versa. 5 translations of Akademi’s award-wining books from one Indian language to another were published. |  |  |  |
| 6. | Festival of India | To organize major cultural festivals in selected foreign countries for achieving better understanding and cooperation | 4.10 | -- | It has been decided to organize ‘Days of India’ in Poland during May-June, 2008. ‘Indian Days’ in Brazil to be held in 2008. ‘Days in Indian Culture’ in Takakistan are to be held in 2008. | Out of RE of Rs.3.86 crore, Rs.20.00 lakh were given to the ZCC for organizing function at China. The remaining amount was surrendered. | 0.20 | -- |  |
| 7. | Indira Gandhi National Centre for the Arts (IGNCA) | IGNCA was established to commemorate the memory of the Former Prime Minister Late Smt. Indira Gandhi. It is envisioned as a centre for research, academic pursuit and dissemination in the field of the arts. | -- | 25.00 |  |  | -- | 29.50 |  |
| (i) | Construction of Buildings | (i) Compilation of Kalanidhi Kalakosha Building in all respect. (ii) Foundation work in Sutradhara Building. (iii) Preparation of estimates, architectural drawings and obtaining clearances for the Concert Hall |  |  | Completion of Kalanidhi Kalakosha Building | Full operationalisation of the Kalanidhi Kalakosha Building including Guest House Block. |  |  |  |
| (ii) | Promotion of Multidisciplinary Research and Critical Dialogue among diverse Arts. | Enlarge its programme of research and publication of fundamental texts, reference works, glossaries, dictionaries, encyclopedia, comparative history of Indian arts, thesaurus of fundamental terms, inter-dialect and inter-disciplinary glossaries and dictionaries, explore relationship of arts and science, dimensions and explore relationship between arts of India and the world, special focus on the North-East and its cultural dimensions. |  |  | Studies on the following dimensions: (a) Multiple levels of identity and their manifestation in Arts- 49 (b) Language and Cultural Diversity 19 (c) Wisdom Tradition, Ecology, Resource Management and Sustainable Development 14 (d) Religious Identities, Confluence of Traditions and composite Cultures18 (e) Inter-Cultural Dialogue- 40 (f) Contribution of Women to Indian Art and Culture 27 | (a) Publication of critical editions of fundamental texts, monographs on tribal and folk culture, republication of texts by eminent scholars (b) Research and field studies. (c) Audio-video documentation (d) Conference, seminars and workshops (e) Exhibition and multi-media events (f) Production of films, CDs, audio-video recordings. |  |  |  |
| (vi) | Cultural Cartography | Map ecological and cultural profile of diverse communities of India along with specific aspects of art and crafts traditions prevalent among them. |  |  | Creation of a cell Research and field study Preparation of Atlas | (i) Training and capacity building (ii) Publication (iii)Seminars, conferences and workshops |  |  |  |
| 8. | National School of Drama, New Delhi | Promote Theatre and to conduct theatre training programme | 5.00 | 13.00 |  |  | 6.27 | 22.25 |  |
| (i) | Theatre workshop and part time courses in regions and locally and other training courses for faculty and staff. | To benefit a vast majority of theatre enthusiasts in various states with diverse languages and cultural backgrounds and to create theatre awareness in them. |  |  | Extensive Theatre Workshop- 10 Collaborative Theatre Workshop- 25 Assistance to Theatre Workshop- 8 Part Time Course- 1 Refresher Course- 2 Short term Workshop- 20 Intensive Theatre Workshop- 12 Acting Theatre Workshop- 3 Technical Theatre Workshop- 3 Theatre Music Workshop- 2 Theatre Design Workshop- 6 | 75 Theatre workshops conducted in which more than 700 trainees participated. |  |  |  |
| (ii) | Organizing of course of training Children Theatre in Delhi and outside Delhi | To develop personality and give exposure to children in terms of their expressions and confidence. |  |  | Children theatre Workshops in Delhi/Outside Delhi-18 Assistance to Theatre Group- 10 Theatre workshop with SC/ST Children- 5 Short Term Theatre Workshop- 6 | 46 Workshops were conducted in Delhi & Outside Delhi. Theatre training was provided to 1200 children. |  |  |  |
| (iii) | Organizing of collaborative programme of traditional group in villages and theatre festival/ exhibition. | Providing 3-year Advanced Dramatic Training Course and to acquaint the students from theatre from existing in different regions of the country. |  |  | Programme with traditional groups- 8 Summer Festival- 1 Winter Festival- 1 Displaying Exhibition- 7 Weekend Theatre Performances- 38 Overseas Productions 5 Reperation of Students/Fellows productions & Repertory Company- 15 | Summer Festival-1 Displaying Exhibition- 8, Overseas Productions -2, Repetition of Students/fellows production-11, Golden Jubilee productions-3 and 2 Visit to foreign Countries were undertaken during the year. |  |  |  |
| (iv) | Promotion of Folk, Tribal Arts and Educational Tours | To familiarize the students with the existing folk and tribal art relating to theatrical and music forms. |  |  | Workshop with Tribal Group- 2 Education tour for 1st 2nd 3rd years students- 3 | 2 production oriented workshops in Orissa and Assam were conducted with the design students and with students of 2nd year. 3 educational tours for the students were also organized in Aurangabad, Agra & Pune. |  |  |  |
| (v) | Extension of Repertory Company | Dissemination of Indian plays in India and Outside the country. |  |  | Performances of play in Delhi- 135 Outside Delhi- 40 Participation of NE theatre Groups in 10th BRM- 8 Children Festival & Bal Sangam- 6 Overseas Production shows-10 Winter Festival- 8 | Performances in Delhi- 67, Performances in Outside – 17, Performances- 36 Participation in 11th BRM |  |  |  |
| 9. | National Gallery of Modern Art (NGMA) | To create an understanding and sensitivity among the Indian public towards visual and plastic arts in general and to promote the development of contemporary art in particular. | 1.97 | 5.00 |  |  | 2.26 | 3.31 |  |
| (i) | Upgradation, Modernization and maintenance of museum | To promote development of contemporary art at par with international level. |  |  | Increased understanding and Aesthetic awareness of public. Creation of world class modern art galleries. 15 special exhibitions at Delhi, Mumbai & Bangalore both of Indian contemporary artists and foreign arts. To organize atleast 275 films shows in the auditorium. 150 conducted tours to be organized for the benefit of School Children. Development and Maintenance of Sculpture Garden. Art Sketch Club is held every Sunday at the museum premises. Summer Art workshop to be organized in May-June 2008. Atleast 4 seminars on Art and Art practices conducted by eminent artists and Art historian/critics to be organized. Atleast 10 Catalogues and 15 posters of Special exhibitions to be released. Conservation and Restoration of Art works and cleaning and conditioning of reserve collection are to be undertaken during the year. A new branch at Bangalore and a New Wing of the Galleries at New Delhi will fully operationalized. About 45000 of art lovers will visit the museum. | Maintaining a well displayed gallery both at New Delhi & Mumbai 9 special exhibitions held at Delhi, Bangalore & Mumbai 510 films shows on art were organized. Conducted tours were organized for 60 schools. 100 children attended the Art Sketch Club every Sunday. 180 children attended the summer art workshop organized in May-June, 2008. Produced 6 portfolios, 6 sets of souviner Mugs and 1 catalogue of exhibition ‘In the seeds of time’ were released. 16 different greeting cards were produced in addition to 3 exhibition catalogue produced in collaboration with various agencies. Conducted tours for various sponsored groups of Indian & Foreign delegation. Press conferences, press review were organized. A well organized Art reference Library having collection of 20000 reference books on Art is being maintained. A large new wing of NGMA Delhi was operationalized and inaugurated by Smt. Sonia Gandhi, on 19th Jan. 2009. A new branch of NGMA at Bangalore was also operationalized by Smt. Ambika Soni, Minister of Tourism of Culture on 18th Feb. 2009 |  |  |  |
| 10. | Asiatic Society Kolkata | Declared as an institution of national importance. To launch research projects on language, literature, culture and socio-economical aspects | 5.65 | 4.00 |  |  | 7.65 | 3.57 |  |
| (i) | Development of Library System | To establish build, maintain institutions for promotion of research in humanities and sciences |  |  | Book acquisition- 2000 Micro film acquisition CD ROM Acquisition and retrospective Cataloguing Computer documentation including Preparation of CD Rom- 7000 Binding / Mending – 2500 | 2250 male and 9500 females readers served by library facility. The new books were also added to its library binding/mending were also completed. |  |  |  |
| (ii) | Development of Museum & User facility | To preserve manuscripts which has a rich collection of archival records, coins inscriptions and very valuable lithographs. |  |  | Cataloguing/Documentation of MSS, archival Material etc.– 6000 Mss, 200 Archival material, 10000 letters, | 350 Indian and 250 foreign visitors, Research Scholars benefited from the facilities provided as mentioned in col.5. |  |  |  |
| (iii) | Conservation & Preservation of rare books, MSS & Other document | To take effective measure for the preservation of brittle and fragile manuscripts, rare books and other ancient objects kept in the Museum and Library of Society. |  |  | Restoration of 4000 sheets of Lithographic prints. | Preservation programme of rare books and MSS, Painting etc. of Library, Museum and other departments was undertaken. |  |  |  |
| (iv) | Publication Programme | To bring out the publication of high academic standard for which the society is known to the world of scholars. Particular emphasis is made on the publication of books under the Bibliotheca Indica series. |  |  | Publication: Books- 12 Journals- 4 Booklets- 11 | Publication of 12 books, 4 Journals, 11 booklets completed. |  |  |  |
| 11. | Centre for Cultural Resources and Training, New Delhi | Aims to improve the quality of life through the medium of Academies working in the field of linking education with culture. | 2.50 | 10.00 |  |  | 2.59 | 12.10 |  |
| (i) | Propagation of Culture among school students | To conduct a variety of in-service Teacher Training Programmes such as Orientation Training Programmes, workshops, Seminars, Refresher course etc. in different parts of the country for school teachers, teacher educators etc. organization of educational activities for school students and children belonging to governmental and non-governmental organizations. Workshops for children of resettlement and basti colonies and for physically challenged students. |  |  | Training Programmes for Teacher Educators- 250 Seminars/Workshops/ Refresher Courses in different States including North Eastern State Sikkim- 5000 Trainers to be trained in the Seminar\ Workshop/Refresher Courses- 250 Teachers to be trained through Trainers- 2500 Student to be trained under Community and Extension Programmes- 40000 Publication including reprints- 20 Setting up of Culture Clubs- 100 Educational Kit issued- 800 Setting of Cultural Clubs- 100 | 4505Teachers/ Teacher Educators have been trained in various Training Programme. 2077 Teachers trained through Trainers. 25531 students were trained. 167 Culture Clubs were setup in various states in the country. Production 4 Video films including CD Roms were produced. 16 publications including reprints were published. 731 sets of Cultural Kits have produced to participating Teachers and Teacher Educators. |  |  |  |
| (ii) | Cultural Talent Search Scholarship Scheme (CTSS) | Aims at providing facilities by awarding scholarship to study the performing and other arts to outstanding young children in the age group of 10-14 years. |  |  | Award of Scholarship under Cultural Talent Search Scholarships Scheme- 400 | 400 Scholarships have been awarded covering all parts of the country including North East. 2 Cultural festival have been organized for scholarship holders. |  |  |  |
| 12. | Financial Assistance for Professional Groups and Individuals for specified performing art projects. (Dance, Drama and Theatre Ensembles) | To promote the Guru Sishya Parampara and support organizations / individuals working in the field of Performing Arts. | 1.35 | 16.00 | About 1000 organizations/ individuals will be promoted and supported. | About 480 individuals/ organizations have been assisted. | 0.81 | 18.38 | Includes 30% provision towards pro-women, and 20% provision for ST population |
| 13. | Gandhi Peace Prize | Government of India announced institution of an annual international Gandhi Peace Prize for social, economic and political transformation through non-violence and other Gandhian methods as a part of celebration of 125th birth anniversary of Mahatma Gandhi. | 1.30 | -- | The recipient of this prize is selected by the Jury headed by Hon’ble Prime Minister in accordance with the prescribed code of procedure. | No recipient of this prize has been selected in the year 2008-09. | 0.01 | -- |  |
| 14. | National Culture Fund (NCF) | Public Private Partnership in the sphere of culture. To mobilize the funds from corporates/PSU & for funding of conservation and other cultural activities. | -- | 3.19 | The NCF’s plan for the future is to take initiatives to call for more collaboration with Corporate Sector and to make the people aware that only with their cooperation the culture will flourish. The ASI has identified 100 new projects indicating the items of work to be performed with cost estimates with a view to enable corporate\private section to choose the projects of their choice. | Under Tangible Monuments, 4 projects namely, Humayun’s Tomb, Shaniwarwada, Pune; Pardeshi Synagogue, Cochin; and Ramakrishna Mission, Kolkata; and other 3 projects under Intangible Culture Heritage were completed. In addition to, various projects under Tangible Monuments and Intangible Cultural Heritage are under progress. | -- | 3.19 |  |
| 15. | Centenary/ Anniversary Celebration | To celebrate the Centenary/Anniversary of important personalities and events | 26.21 | 11.50 |  |  | 74.29 | 8.34 |  |
| 15.1 | Celebration of 2550th Anniversary of Mahaparinirvana of Lord Buddha | To highlight salient aspects of the life and times of Lord Buddha and to acquaint the people particularly the young generation with the great soul, who successfully diverted the attention of masses towards Ahimsa for the betterment of human. | 5.00 |  | Programmes are to be organized in memory of Lord Budha and funds will be provided for the projects associated with Lord Budha to strengthen the infrastructure to propagate the teachings of Lord Budha. | Residual works, after concluding function of the event which was held at Kushinagar on 02.05.2007 were taken up, as per approval of the NIC during the year. | 0.95 |  |  |
| 15.2 | Celebration of Birth Centenary of Lal Bahadur Shastri | In order to create a Chair in the Institute of Defense Studies and Analysis, N.Delhi in the name of Shri Lal Bahadur Shastri. | 0.21 |  | A provision of Rs. 7.00 lakh has been kept for this purpose. | Due to financial constraints, project could not be taken up during the year. | 0.21 |  |  |
| 15.3 | Celebration of 150th anniversary of 1st war of independence, 1857. | To highlight the sacrifices of our great heroes / leaders who laid their life for freedom of the country and to pay home-age to them. To make aware the people specially young generation about the history of our freedom struggle to infuse into them the spirit of the National Integration and also highlight the achievement of Nation in various areas in past 60 years. | 21.00 |  | To celebrate the event, programmes will be organized in memory of great heroes/ leaders to educate the people. Funds will be provided for maintenance/ restoration of monuments and places associated with the event. | Various programmes/ projects/ events were held for commemoration of 150th anniversary of 1st war of independence, 1857 which includes concluding function on 75th Martyrdom/Birth Centenary of Shaheed Bhagat, preparation of National Register of Martyrs, Mobile exhibition on Train, function on Veer Kunwar Singh, Function on 1857 by SNA, Function on ‘Heritage of Mughals’etc. | 19.88 |  |  |
| 15.4 | Financial support to Khalsa Heritage Project | To highlight salient aspects of the important events relating to Khalsa Heritage in order to infuse in the public, particularly the young, the spirit of these great events. |  | 11.50 | Funds for Khalsa Heritage Project to be given to Punjab Govt. as 1/3rd share of Central Govt. (Plan) as reimbursement of the amount spent on the project on quarterly basis. | Funds to the tune of Rs.8.34 crore have been released to Govt. of Punjab for KHP |  | 8.34 |  |
| 15.5 | Development of Dandi Heritage Corridor | To provide infrastructural development of Heritage Sites in the Memory of Mahatma Gandhi. | 1.00 |  |  | No fund was released for the scheme | -- | -- |  |
| 15.6 | Construction of Memorials at Dandi | To provide infrastructural development in the Memory of Mahatma Gandhi. | 1.00 |  |  | No fund was released for the scheme | -- | -- |  |
| 15.7 | Ter-Centenary of Guru-ta-Gaddi | Aims to provide infrastructural development of Anandpur Sahib and Talwandi Sabo as a part of Ter Centenary Celebration of Guru-ta-Gaddi of Shri Guru Granth Sahib at Nanded. | 5.00 |  | This grant will be given to Govt. of Punjab for the infrastructural development of Anandpur Sahib and Talwandi Sabo. Various projects will be undertaken by the Govt. of Punjab. | Funds were released to Govt. of Punjab for Celebration of Ter-Centenary of Guru-ta-Gaddi | 53.94 |  |  |
| 16. | Other Schemes |  | 36.89 | 78.85 |  |  |  |  |  |
| (a) | Central Institute of Higher Tibetan Studies, Sarnath | Established with a view to educating the youth of Tibet and Himalayan border areas of India | 5.50 | 4.00 |  |  | 6.30 | 3.99 |  |
| (i) | Development of Library | 1. To Preserve Tibetan culture and tradition. 2. To restore ancient Indian sciences and literature preserved in the Tibetan languages. |  |  | Purchase of 80 books, and computer/ equipments. | 80 books and a number of computers/ equipments purchased. |  |  |  |
| (ii) | Publication and Printing. | To provide printed material on Tibetan culture for scholars and others |  |  | 8 books to be published. | 8 books published |  |  |  |
| (iii) | Rare Buddhist Text Research | To offer the alternative educational facilities to the students of Indian border area who formerly availed the opportunity of receiving higher education in Tibet |  |  | 4 sites to be visited for research purposes | 1 site visited |  |  |  |
| (b) | Central Institute of Buddhist Studies, Leh | To develop multifaceted personality of the students through inculcation of the wisdom of Buddhist through and literature as well as to familiarize them with modern subjects to acquaint them with collection, conservation, translation, publication of rare manuscripts and research works relevant to Buddhist Studies etc. | 3.38 | 7.00 |  |  | 4.54 | 5.33 |  |
| (i) | Construction of Building | Construction of auditorium, Guest House, 20 Residential Quarters and Building for DPS, Zanskar. |  |  | Construction works are in progress. | Construction is going on through CPWD and State PWD for the said buildings. |  |  |  |
| (ii) | Provision for existing Gonpa/ Nunnery school | To support educational activities in the number of Gonpas by providing teachers and stipend to the students. |  |  | Plan activities for 50 feeder schools in different monasteries of Ladakh and a branch at Zanskar Kargil will continue. | For preservation and promotion of Monastic System of Educ., activities in 50 Gonpa/ Nunnery Schools are going-on. |  |  |  |
| (c) | Gandhi Smriti and Darshan Samiti | To propagate the life, mission and thoughts of Mahatma Gandhi by organizing various socio – educational and cultural programmes. | 3.70 | 10.00 |  |  | 4.88 | 10.00 |  |
| (i) | Promotional Activities | To plan and carry on activities for the promotion of Mahatma Gandhi’s ideals and of national causes identified by him. |  |  | 4 Programmes for Children programmes with educational institutions to reach out to more than 50,000 students. 2 Programmes for Youth to reach out more than 25,000 youths. 2 Programmes for Women to cover about 10,000 women. 1 Programmes on Satyagraha to reach out to attest 50,000 people. Programmes in the North-East- 4 | As part of this initiative, regular interactions with children; exposure visit to Gandhi Smriti; quiz; discussions and competitions on variety of social and developmental issues; bringing out the children’s newspaper, the Yamuna were taken up during the year. Extensive summer schools and a series of programmes for youth & women were organized in various States of the country and Delhi. |  |  |  |
| (ii) | Dissemination | To undertake such activities as will lead to greater understanding of Mahatma Gandhi’s life, work and thoughts. |  |  | Publication of journals, Newsmagazine, children’s Newspaper, etc. These publications will held to reach out message of Mahatma Gandhi & other social issues to about 20,000 children youth and other cross section of the society. Research activities and Training programmes will be taken up. Seminars/ Workshops- 9 | The publications were published as per their periodicity. Society got acclimatized with the activities of the Samiti through these publications. |  |  |  |
| (d) | Nav Nalanda Mahavihara, Nalanda, Bihar | To revive past glories of the ancient university of Nalanda and to give post graduate studies and research in Pali language and literature and Buddhology. | 1.35 | 3.00 |  |  | 1.33 | 3.00 |  |
| (i) | Improvement & Development of Library Service | Developing the library with purchase of new books on Pali, Buddhism Philosophy, ancient History, Culture and Architect, Hindi, English, Sanskrit etc. |  |  | Around 7000 of books are expected to be purchased. | As indicated in the col. 5 new books on various subjects were purchased |  |  |  |
| (ii) | Development of Xuan Zang Memorial Hall | To provide creative works, as paintings, murals inside and outside the XZM and on landscaping etc. |  |  | Various paintings of and morals connected with the life of Xuan Zang. | Painting and morals for display inside and outside the XZM were procured . |  |  |  |
| (iii) | Construction of 100 beded new hostel | To accommodate the foreign students |  |  | For this work, funds will be released to CPWD for carrying out the construction work. | Tenders have been called for carrying out this work through CPWD |  |  |  |
| (e) | Maulana Abul Kalam Azad Institute of Asian Studies, Kolkata | To conduct research and training of life and works of Maulana Abul Kalam Azad with the study of social culture, political and economic movement in Asia from the middle of the 19th century. | 0.90 | 4.50 |  |  | 0.88 | 5.05 |  |
| (i) | Research project including North East/ fellowship and other promotional activities. | To carryout research activities and revelation of political, social & economic changes in India and other Asian countries. |  |  | Project Fellowship- 30/40 Field Trip (Domestic & Foreign)- 19 Seminar(National\International),EC\FC meeting, Society meeting- 14 | Organized 14 National and International Seminars and 1 Maulana Azad lecture. A weekly seminar programme continued during the year. |  |  |  |
| (ii) | Publications \Acquisitions of Book | To provide the printed material for conduct research and training and also to preserve and restore ancient Indian papers\materials on political and economic movement in Asia |  |  | Publication: Books to be published- 15 Journals to be published- 1 Acquisition: Books- 900 Journals- 100 | Produced 19 books and 1 journal. Introduced a rigorous reviewing process. 12 manuscripts submitted for its reviewing. |  |  |  |
| (f) | Kalakshetra Foundation, Chennai | A Cultural institution of International repute established for preservation of traditional values in Indian Art especially in the field of dance and museum. | 3.25 | 3.00 |  |  | 3.93 | 1.66 |  |
|  | Building Project | Theatre upgradation with audio and lighting equipments and also renovation of Refurbishing of Museum, etc. will be taken up |  |  | Theatre upgradation with audio and lighting equipments and also renovation of Refurbishing of Museum, etc. will be taken up. | Major works already indicated in col.5 have been completed during the year. |  |  |  |
| (ii) | Estate and Landscape | The compus is in existence for more than 40 years the Municipal service connection for water supply and sewerage has not been established. To improve these facilities in the campus in line with modern facilities. |  |  | The landscaping of the campus will be carefully planned to suit the ideals of the Foundation and implemented in phases. | Basic civic amenity of the water supplies and sewerage connection has been completed during the year. |  |  |  |
| (iv) | Research and Development | New Departments like Centre for Visual arts, Rukmini Devi Museum, Theatre and Research and Documentation are being developed to preserve for posterity the priceless treasures of Kalakshetra Foundation. |  |  | The current activities will continue under research and development wing by properly mending and laminated the library collection. | This is a ongoing process and has to be completed without compromising on the quality. |  |  |  |
| (g) | Namgyal Research Institute of Tibetology, Sikkim | The Institute is an autonomous organization under the state govt. of Sikkim and gets regular grant- in- aid from this ministry. The main objective of this institute is to spread the knowledge of Chhos(Doctrine of Buddha). | 0.40 | --- | The Institute has ongoing programmes of translating and publishing the seminal texts preserved in its archives. | The institute has completed all the plan activities conceptualized in the period under report. | 0.38 | -- |  |
| (h) | a) Fellowship to outstanding artists in the field of performing, literary and visual arts. | This scheme provides financial support to outstanding artists in the fields of music, dance, theatre, visual art, literature and traditional art forms of folk and indigenous art. | 1.10 | 7.00 | 125 junior and 125senior fellowships to be awarded. | Junior and Senior fellowships awarded to all eligible candidates during 2008-09 | 0.08 | 5.82 |  |
|  | b)Scholarship to young workers | This scheme seeks to give financial assistance to young artists of outstanding promise for advanced training within India. | 0.70 | --- | 400 scholarships to be awarded. | 400 scholarships awarded during the period. | 0.47 | -- |  |
| (l) | International cultural activities & grants to Indo-Foreign Friendship societies | To foster closer friendship and cultural contacts between India and the foreign country concerned. | 0.50 | ---- | Grants are sanctioned on the specific recommendations of the Indian Mission concerned. The grant covers expenses of grantees on cultural activities. | Grants of Rs.0.51 cr. was released to recommended organizations for cultural activities | 0.51 | -- |  |
| (m) | Financial Assistance to distinguished art persons | To provide financial assistance to artists whose contribution in the field of art has been of great significance and who have attained an age of 58 years and above and are in indigent circumstances. | 1.55 | 3.25 | 1927 old artists to be provided assistance under this pension scheme. | 1632 artists were given financial assistance during the period under report. | 1.32 | 2.54 |  |
| (n) | Delegation under Culture Exchange Programme | Promotion of Cultural relations with other countries of the world on the reciprocal basis. | 0.80 | -- | The main purpose of this fund is to host cultural visits by foreign dignitaries organize meetings/ conferences under the cultural agreements/CEPs. | The following CA/CEPs were signed respectively: Brunei, South Africa, Ecuador. The 14th meeting of the Joint Working Group between India Russia on Culture and Tourism was held on 30th October 08 at New Delhi and a Protocol was signed. | 0.01 | -- |  |
| (o) | Financial Assistance for Tribal/Folk Art | To promote and disseminate tribal art of culture. The scheme aims at creating awareness of richness of tribal /folk art through documentation and organizing cultural activities including festivals. | ---- | 2.00 | About 600 organizations / individuals to be assisted. | About 136 individuals/ organizations have been assisted. | -- | 0.31 |  |
| (p) | Financial Assistance for the Preservation & Development of cultural Heritage of the Himalayas | To promote, project and preserve the cultural heritage of Himalayas. | --- | 1.00 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 17 NGOs/ individuals were given financial assistance under this scheme. | -- | 0.56 |  |
| (q) | Financial Assistance for the Preservation and Development of Buddhist/ Tibetan Organizations. | To promote and propagate the scientific development of Buddhist/ Tibetan culture and tradition and also research in the relative fields. | --- | 5.00 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 129 NGOs/ individuals were given financial assistance under this scheme. | -- | 3.78 |  |
| (r) | Centenaries & Celebrations | To provide financial assistance to cultural organizations/NGOs for celebration of centenaries of renowned personalities of India. | 2.00 | --- | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 37 NGOs/ Organizations were given financial assistance for celebrating Centenaries/ Anniversaries | 0.42 | -- |  |
| (s) | Maintenance of National Memorials | To commemorate the role of eminent National Personalities who have contributed to and played a historic role in the history of the country | 2.00 | -- | Financial assistance is given to the voluntary organizations for maintenance of National Memorials | Rs.1.37 crore given to Govt. of Uttarakhand for Uday Shankar Akademy for dance and music, at Almora and Rs.0.45 crore given for Fakhrudin Ali Ahmed Memorial Trust. | 1.89 | -- |  |
| (t) | Building Grants to Cultural Organizations | To give grants to voluntary cultural organizations working in the field of dance, music, fine arts, indology and literature for construction of building and purchase of material. | ---- | 8.48 | 400 beneficiaries will be awarded grants. | About 32 individuals/ organizations have been assisted. | -- | 0.72 |  |
| (u) | Financial assistance to Cultural Organizations with a national presence | To provide assistance Institutions/Organizations engaged in cultural activity at the National level. | 2.21 | 2.00 | The grant will be given to the prominent institutions like R.K.Mission. INTACH and other organizations with the national presence. | Grants were given to R.K.Mission, for Plan & Non-Plan activities, whereas SPICMACAY & INTACH were given grants under Plan only for cultural activities. | 2.21 | 1.91 |  |
| (v) | Development of Cultural Organizations | To give grants to voluntary organizations of national fame engaged in cultural activities for holding a conference, seminars and symposia on important cultural matters. | --- | 1.60 | Organizations to be awarded grants, as per the recommendations of the Expert Committee, as and when it meets during 2008-09. | As the scheme was under modification, no grant under the scheme was given during the year. However, grants to old cases/ organizations already sanctioned were given grants. | -- | 0.31 |  |
| (w) | Twang Monastery | To educate the monks and als act as a centre for Buddhist Cultural Studies. | -- | 0.01 | Monastery will continue its ongoing programmes including maintenance of their museum. | Monastery continued its ongoing plan programmes from NE funds. | -- | 0.45 |  |
| (x) | Tibet House, New Delhi | The main aims and objectives of the Tibet house are to promote, preserve and protect the Tibetan culture, encourage the exchange the ideas and techniques between Tibetan and non-Tibetan artists and craftsmen. | -- | 0.30 | Tibet House will continue to implement their ongoing programmes including maintenance of Museum | Tibet House continued its ongoing programmes during the year. | -- | 0.30 |  |
| (y) | Development of Jalianwala Bagh Memorial | In order to take up a comprehensive development of this Memorial, refitting its status and importance in the history of India freedom struggle. | --- | 5.50 | Developmental programmes will be taken up to upgrade the Memorial. | Rs.5.50 crore was released to the Trust for carrying out developmental works at the site. | -- | 5.50 |  |
| (z) | Assistance for preservation and promotion of intangible heritage of humanity. | To preserve and promote Kutiyattam, Ramlila and Vedic Chanting. | --- | 2.00 | About 200 organizations/ individuals to be assisted. | This scheme has been transferred to Sangeet Natak Akademi. For implementation of this scheme Rs.4.00 crore was released. | -- | 0.00 | Scheme transferred to SNA from 2008-09 |
| (aa) | Scheme for safeguarding and other protective measures in the area of Intangible Heritage and Cultural Diversity (arising out of UNESCO Convention) | In order to meet the obligations arising from the UNESCO conventions on the safeguarding of intangible cultural heritage and cultural diversity. | --- | 0.10 | A token provision has been made for the new scheme. | This scheme is still to be implemented. | -- | 0.00 |  |
| (bb) | Awareness creation in the area of Intellectual Property Right (IPR) and Setting up of a National IPR Cell for Creative Artists and Artisans. | To protect the Intellectual Property Rights of Indian Artists. | --- | 0.10 | A token provision has been made for the new scheme. | This scheme has been dropped on the recommendation of the Bhaskar Ghosh Committee’s report. | -- | -- |  |
| (cc) | Plan scheme for promotion and dissemination of Awareness about Indian Culture and Heritage | To take up activities relating to promotion of cultural and heritage through performing arts and theatres. | --- | 2.00 | This scheme will be implemented through CCRT in the year 2008-09 | This scheme is under modification through CCRT and EFC memo is still to be finalized. | -- | 0.00 |  |
| (dd) | Cultural heritage volunteers (CHV) Schemes | To protect the young people from marginalization and neglect by ensuring their social inclusion and involvement in civic and cultural programmes. | --- | 2.00 | This scheme will be implemented through CCRT in the year 2008-09 | This scheme is under modification through CCRT and EFC memo is still to be finalized. | -- | 0.00 |  |
| (ee) | Pilot scheme for cultural industries | In order to convert wide variety of creative expressions, traditional designs and endless variety of crafts into cultural industries products. | --- | 0.50 | The scheme is to be implemented through ZCC on pilot basis. | Rs.0.45 crore released to 2- ZCCs for carrying out survey and providing facilities for this scheme. | -- | 0.45 |  |
| (jj) | Centre for management of cultural resources | To develop centre of Excellency for Research and Training in inter-disciplinary areas in an integrated manner so as to introduce capable managers and researchers for Cultural Resources. | --- | 1.00 | A token provision has been made. | This scheme is still to be implemented. | -- | 0.00 |  |
| (kk) | Financial Assistance for setting up of multipurpose cultural complex including those for children | To improve the quality of our life young people be made sensitive to what is aesthetically and morally good in society, to provide new avenues for young people and promote performing art and literature through MPCC. | -- | 2.00 | On the direction of the Plg. Comm., this scheme is being restructure as a Central Sector Scheme. All pending applications and ongoing projects to be financially aided. | 2nd installments of 6 – ongoing projects - 2 from Assam, 1 from Gujarat & W. Bengla each and 2 in Arunachal Pradesh were given assistance. | -- | 6.10 |  |
| (ll) | Flexible Engagements in Knowledge Institutions | It envisages lateral movement of scholars/academicians into the institutions to take up projects and research work related to main objective of the institutions and enrich them with a new creative edge. | -- | 1.00 | This is the new Plan scheme which has been referred to, for in principle approval from Plg. Comm. before the scheme is made operational | Scheme still to be implemented after its EFC’s approval. | -- | 0.00 |  |
|  | Total (Promotion of Art and Culture) | 100.87 | 208.54 |  |  |  |  |  |
| 17. | Archaeological Survey of India | This organization is mainly involved in conservation, preservation and maintenance of the built heritage of the country. | 201.00* | 111.00* |  |  | 232.20 | 108.14 |  |
|  | Conservation & Preservation of Ancient Monuments: its up keeps and maintenance including environmental development. | For conservation, preservation and maintenance of centrally protected ancient monuments and sites. |  |  | Structural conservation works at about 1000 centrally protected monuments, horticultural development of 150 centrally protected monuments and structural preservation of 104 monuments including upgradation of science laboratory at Dehradun and setting up of Research/ Conservation Laboratory at Aurangabad. | The targets reflected in col. 5 were almost completed. However, this is a continuing process |  |  |  |
|  | Providing basic amenities tourists | Development of basic amenities in Ancient monuments including provision of toilets, drinking water facilities etc. |  |  | Better visitor facilities and other amenities at 230 monuments including World Heritage Monuments and Sites/other important monuments by providing toilet blocks, drinking water facilities, ramps for physically disabled visitors. | Provisions of essential facilities at the major monuments/ sites have been completed. However, this is a continuing process. |  |  |  |
|  | Excavation and Exploration. | Excavation of Archaeological Sites and Exploration of antiquarian Remains, under Village to Village Survey and Problem Oriented survey |  |  | 1. 10 excavations. 2. Two excavation by UAW approved. 3. 10 exploration. 4. Training in archaeo-material by IIT, Kanpur. 5. Financial assistance to 12 Universities/Research Institutes. 6. Completion of 30 excavation reports. | Excavation of Archaeological sites and exploration of antiquarian Remains were completed for the identified projects. However, this is a continuing process |  |  |  |
|  | Development of the Archaeological Site Museums. | Maintenance/Development of Archaeological Museums |  |  | 1.Phased modernization / upgradation of 7 museums. 2. Opening of 2 new museums at Fatehpur Sikri & Shivpuri. 3. Expansion & Development of existing one museum i.e. Swantantrata Sangram Sangrahalaya, Red Fort, Delhi. 4. Shifting and re-organization of museums in 2 new buildings at Chenderi & Khajuraho. 5. Maintenance of 42 museums. 6. Organizing public awareness programme in each museum. | Completed. However, this is a continuing process |  |  |  |
|  | National Mission for Ancient Monuments and Antiquities | i) Remuneration for supporting staff engaged on contract basis and fee for consultants (for various consultancy work). Travel Expenses. ii) Equipment and software. iii) Stationery and other related expenditure in H.Q. & other centres. iv) Publication of popular literature v) Awareness programme Exhibition, Seminars etc. vi) Conservation of selected monuments vii) Miscellaneous and other unforeseen expenditure |  |  | 1. Documentation of antiquities that are lodged in 42 site museums of ASI covering nearly 1 lakh antiquities 2. Documentation of antiquities that are lodged in sculpture sheds of 24 Circles of ASI covering nearly 50,000 antiquities 3. Documentation of antiquities that are lodged in Central Antiquity Collection of ASI covering more than 1 lakh antiquities 4. Documentation of antiquities that are lodged in 251 archaeological museums under the control of 29 States and 6 UTs 5. Compilation of data on unprotected built heritage and sites in 35 States and UT from secondary sources i.e. both published and unpublished 6. Digitization and creation of data base of more than 4 lakh registered antiquities as lodged with data bank of ASI | The digitization work for the 48 volumes Indian Archaeology – A Review has been completed. The completed volumes have been into PDF format and uploaded in the official website of ASI. Various State and local antiquarian legislations has been compiled and are being uploaded in PDF format in the official website of ASI. More than 28,000 villages having antiquarian remains have been compiled. The digitization of registered antiquities documents is an ongoing process through IGNCA and a total number of 6000 documents have been digitized till date. National Mission has developed the following templates namely a) Documentation of Built Heritage b) Data on Built Heritage and Sites and Antiquities from village level. The following three softwares are being prepared through National Informatics Centre (NIC) for a digital database. a) Software on compilation of data on built heritage, sites from published secondary sources b) Web based village level database. c) Software on Centrally Protected Monuments. |  |  |  |
|  | Publication & Cultural Awareness | 1.Publications under Academic and Informative Series. 2.Dissemination of knowledge and awareness generation regarding heritage Celebration of World Heritage and other important days by Circle & Branche offices of |  |  | Academic 1. Indian Archaeology – A Review – one issue. 2. Memoirs Archaeological Survey India – one issue. Informative 1. Guide Books (WHS) – two issue. 2. Inventory of Monuments – one issue. 3. Special Publication (as and when material is received). Academic 1. Indian Archaeology – A Review – one issue. 2. Memoirs Archaeological Survey India – two issue. Informative 1. Guide Books (WHS) – one issue. 2. Guide Books (other than WHS) – three issues. 3. Inventory of Monuments – one issue. | Completed. However, this is a continuing process |  |  | Subject to the receipt of complete MSS along with illustrations and clearance of the text and approval of the competent authority |
| 18. | National Archives of India | The custodian of non-current records of enduring value of Central Government Ministries / Departments / Offices and their predecessor bodies. The nodal agency for record management activities and their permanent preservation and use by the posterity. | 12.42 | 3.75 |  |  | 12.87 | 3.57 |  |
| (i) | Expansion of records Management Programme | i. Acquisition of Public Records ii. Appraisal of files iii. Vetting of Records Retention Schedule. iv. Holding of Meeting of Archival Advisory Board v. Compilation of 9th and 10th Report of DGA on Implementation of Public Records Act 1993. vi) Organizing Orientation course in RM for DROs. vii. Inspection of DRR’s of Ministry/ Departments/ Offices. |  |  | Acquisition of 25,000 files\records. Appraisal of 25000 files of the records. Vetting of 10 spot studies of ministries/departments/PSUs of the Central Govt. | 12695 files from various Ministries/Department were acquired. 32137 files appraised. 9 schedules vetted. Work of 10th Report of DGA (2007) on the implementation of Public Record Act 1993 was completed. 53 Nominations of Chief Records Officers received. 7 courses conducted. 12 departmental Record Rooms inspected |  |  |  |
| (ii) | Expansion of repair and reprography | Repair of records, binding of books/ volumes/ preparation of security Microfilming, Preparation of Security Microfiche films, Positive printing of microfilms, Supply of copies (Xerox/ Photo/ Reader/ Microfilm to scholars as per their demand). Out sourcing of negative and positive microfilming/ out sourcing of positing microfilming of negative microfilm rolls available in NAI. |  |  | 1,10,000 sheets to be repaired, 1280 books/ volumes to be bound, 720 rolls to be microfilmed, 60,000 exospores to be completed, 28,000 meters printing to be done. 50,000 copies to be supplied to scholars. Scanning of 7,500 images by Microfilm scanner. Scanning of 6,000 images by hybrid camera. Digitalization of Manuscripts – 300 images. | 10139 sheets to be repaired and done both manually as well as by machine by the departmental experts. Volume-216, books-104 and misc. items 2781stitched. Files/volume-216, books- 104 and misc. items 5489 bound. 732 rolls prepared. 33250 exposures completed. 27173 meters positive printing completed. 96588 copies of Xeroxes/photos/ microfilms etc. supplies to research scholars. 220134 scanning of microfilms/MSS images prepared. 7200 scanning by hybrid camera images prepared 300 digitalization of manuscripts images prepared. |  |  | Target is subject to availability of full staff strength |
| (iii) | Expansion of library and administration | Purchase of books Data Entry in to the computer Preparation of data input sheets. |  |  | Acquisition of books-600 Accessioning of boks/periodicals-700 Digitization of books-3000 Binding of books through outsource-6800 Preparation of data input sheets- 700 Data entry in the computer- 700 Classification of books/periodicals- 700 Processing of books- 700 Books cards prepared- 1500 Restoration of books- 30000 Receipt and recording of periodicals/ gazettes/reports- 2000 No. of scholars who attended the library reading room- 4000 Issue\return of books- 30000 Reference queries attended – 12000 Binding of books /lamination by the department- 300 | 2 BAC meeting were held in July 08 & Feb. 09 and members recommended books for purchase. 387 books were acquired. 371 books/ periodicals accessioned 728 books/periodicals classified 1005 data entries completed. 130 data input sheets completed. 639 book cards prepared. |  |  |  |
| (iv) | Expansion of Activities of School of Archival Studies | One Year Diploma Course in Archives and Record Management – 2007-08 and 2008-09. Short Term Courses in Archival Management and allied disciplines. |  |  | (a) One year diploma course 2007-08 to be completed and one year diploma course 2008-09 to be commenced and continued. About 40% to be trained. a. Short Term Course in Record Management-two courses to be conducted. Approximately 150 persons to be trained depending number of trainees joining the courses. | One year Diploma course in Archives and Records Management 2007-08 completed and Diploma course 2008-09 has commenced on 5 Nov. 2008 is in progress. Short Term Courses – 2 Record Management , 2 courses on care and conservation of books, MSS and Archives courses, 2 Reprography, 2 Servicing and Repair of Records, courses conducted and completed.1 Archives Management course to concluded. |  |  |  |
| (v) | Listing of records ref. Media including computerization of records | Listing of private papers. Listing of oriental records and preparation of catalogue/ reference cards of acquired documents. Data Entry of reference media of 25 lakh records in NAI by out sourcing. Upgradation of AIMS Software by NIC. |  |  | Descriptive listing of 960 letters\slips under descriptive listing of Persian correspondence, 960 documents under descriptive listing acquired documents and 1200 reference cards of acquired documents. Upgradation of AIMS Software. | Preparation of reference media/subject lists of Private Papers/microfilm rolls of following collection was taken up. Achieved Targets:- 1 K.M. Munshi Papers (in microfilm) i 22203 entries (online) ii 23943 entries (manually) 2 Kasturbhai Lal Bhai Papers 22781entries (on line) 77 descriptive listing (manually) 128 entries (on line) 2067 – checking of data entries. 38230 entries of records. 187335 entries of records.2 workshop of one week duration on Human Resource Development in Records Management, Conservation and Microfilming/ Digitization conducted at Patna and Dehradun. |  |  | The work got started on Aug.2008 by outsourcing by deployment of 10 persons contractually. Two days workshop organized by Bihar State Archives in collaboration with School of Archival Studies, NAI on Records Management and Conservation at Patna on 15-16 Dec. 2008. The output is low due to cross verification of print out with originals. |
| (vi) | Setting up of a Record Centre in Eastern Zone | Survey and Accession of noncurrent records Appraisal of Records Vetting of records retention schedule |  |  | Survey and acquisition of noncurrent records-2000 records Appraisal of Records- 2000 non current records Vetting of records retention schedule-2 offices | i) 375 files of Andrew Yule and Company records, Kolkata, were acquired. ii) 5 Palm Leaves in connection with Mayurbhanj Gazette was also acquired. iii) Acquisition of Public and oriental records – a) 384 records were acquired from Andrew Yule Company, Kolkata. b) 9 Volumes of Mayurbhanj c) Gazettes were acquired. 4317 files were acquired from Anthropological Survey of India, Kolkata. d)306 appraised files and 33 Palm leaves MSS were acquired. |  |  |  |
| (vii) | Scheme of financial assistance for preservation of manuscripts/ rare books to NGOs. | To financially assist individuals\ NGOs in the State \UTs in securing the value able documents |  |  | Grants Committee Meeting to be held and the amount recommended by the Committee to be released to the recommended Institutions. | Total amount of grant of Rs.30.90 lakh was released to 54 organizations during 2008-09. |  |  |  |
| (viii) | Scheme of financial assistance to State/ Union Territory Archival repositories and Museums. | To support the initiatives by the State / UT Archival Repositories/ Government Libraries and Museums in securing the valuable documentary heritage of the country. |  |  | One Grants Committee Meeting to be held and the amount recommended by the Committee to be released to the State Archives, Government Libraries/ Museums as recommended. | 18 organizations were given grants of Rs.23.88 lakh. In addition to this, 5 organizations were given financial assistance of Rs.17.63 lakh during the year. |  |  |  |
| 19. | National Museum | A premiere institution in the field of art and culture in India and involved in important work of acquisition, conservation, exhibition and educational activities | 8.04 | 10.00 |  |  | 6.25 | 6.21 |  |
| (i) | Photo-documentation of art objects and events | Coloured photo documentation of Museum’s collection, exhibits for exhibitions and publication purposes and events for publicity purposes, done as per demands. Miniature paintings Central Asian antiquities Manuscripts |  |  | A. Photo documentation of art objects & events will continue. However, Photo documentation of paintings, Harappan objects, Manuscripts, Jewellery, Bronzes & Gupta exhibits etc. would also be taken up. | 9535 black and white prints and 3521 colour prints including 1118 black and white negative, 162 colour slides , 438 colour slides, 228 contact sheet, 40 passport and 26 proof sheets were prepared during the year. |  |  |  |
| (ii) | Display & modernization of Museum - reorganization of existing galleries. | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | Organization/ Modernization of the Museum is based on recommendations of the High Powered Committee constituted by the MoC. | Selection of the exhibits for Early Man Gallery has been made. Showcases prepared and exhibits displayed therein. Documentation of exhibits are in progress. |  |  |  |
| (iii) | Remodelling of the object in Plaster Casts | To make the artifacts more attractive and colourfull. |  |  | 2000 Plaster cast each in raw, finished and coloured categories to be modeled. | Raw cast of 1212 replicas were prepared in Plaster of Paris. 1233 replicas were raw finished and 1307 replicas were coloured. |  |  |  |
| (iv) | Restoration and Conservation of art objects. Restoration of Oil Paintings / Conservation of antiquities / art objects / training course in conservation, Acquisition of equipments for conservation / binding of manuscripts. | To protect the antiquities and art objects from decay. To train the Museum staff of National Museum and other museums/Institutions in latest technology in conservation. To keep laboratory well equipped with the latest equipments. |  |  | Examination & treatment of Artifacts- 1000 Conservation of manuscripts-100 Conservation audit (treatment while display) of central Asia Antiquities -60 3 months training course in conservation of paintings Programmes on Preventive Conservation for Curators of different Museum/Art Galleries - 1 International workshop on Conservation of Manuscripts in collaboration with ICCROM- 1 Preparation of condition reports of artifacts- 1 Purchase of conservation material and chemical as per the requirement, chemical analysis of Harappa objects and other metal objects, analysis of Harappan ceramics. Workshop in North-East- 1 Treatment of Paintings of Shri Chitra Art Gallery, Thirvananthapuram Treatment of Paintings of North Block/ Parliament House etc.. | 385 artifacts were given treatment and preserved. 191 MSS were treated for conservation /binding 75 objects for the exhibition entitled ‘Reflection of Indian Consciousness were cleaned and preserved 125 objects in the museum storage were examined and given preventive treatment. Conference at AMU held, workshop on preventive conservation of Arts objects at Itanagar & Guwahati. Museum artifacts were photo documented before and after conservation treatment, 1182 B&W prints were prepared. |  |  |  |
| (v) | Exhibition | To popularize the ancient Indian Art & Culture. To organize thematic exhibitions. To organize exhibitions under Cultural Exchange Programme |  |  | Exhibitions to be sent abroad under MoU Garden and Cosmos: The Royal Painting of Rajasthan Shiva Nataraja: The Sublime Dancer, Switzerland. Early Indian influences in South-East Asia, Singapore. | Two photographic exhibitions one on ‘Outside In A Tale of 3 Cities…The 70’s & 80’s another by Shri Pablo Bartholomew and Shri Bharat Sikka were organized. Days of Iranian Culture in India, Hampi, Zenkoji Shonin, and Reflections of Indian Consciousness exhibitions were organized in National Museum. |  |  | Garden and Cosmos: The Royal Art of Jodhpur at Seattle, USA; and Shiva Nataraja : The cosmic Dancer at Rietburg, Switzerland exhibitions were organized in abroad. |
| 20. | National Council of Science Museums | To popularize Science and Technology by organizing exhibition, seminars, training programmes for Science Teachers, students, young entrepreneurs, technicians etc. | 18.00 | 19.00 |  |  | 19.65 | 22.26 |  |
| (i) | Setting up of new galleries, upgradation and updation of exhibits, new circulating exhibitions, new mobile science exhibition units, new training facilities, educational programmes, strengthening of infrastructure and existing facilities of 27 science centers located at various parts of the country. | To modernize, upgrade and popularize the science and technology in the country. |  |  | Galleries to be set up: ‘Nuclear Power’ at NSC, Mumbai; ‘Heritage’ at RSC, Calicut; ‘Communication’ at BITM, Kolkata; ‘Fun Science’ at SSC Patna; ‘Popular Science’ at NBSC, Siliguri; ‘Nanotechnology’ at VITM, Bangalore; Children’s Gallery at BITM, Kolkata. Galleries to be completed: ‘Wonder World of Materials’ at RSC, Lucknow; ‘Popular Science’ at RSC Tirupati; ‘Man & Machine’ at NSC, Mumbai; ‘Invention’ at RSC, Nagpur; ‘Fun Science’ at RSC, Nagpur; ‘Fun Science’ at RSC, Bhopal; S&T Heritage at NCSD; ‘Electrotechnic’ at VITM. Travelling Exhibitions: Two new exhibition to be developed Travelling Exhibitions on ‘Biodiversity’, ‘Illusion’, Human Genome’, ‘An Eye in the Sky’, The Story of Poles’ etc. to be circulated. | Galleries namely, ‘Electronics; at DSC, Tirunelveli; ‘Transport’ at BITM, Kolkata; ‘Fun Science’ at VITM, Bangalore & SSC Patna; ‘Human Biology’ at NSC, Delhi; and ‘Hall of Computing’ were inaugurated during the year. ‘River’ and ‘Measuring Our Planet’ at BITM, Kolkata; ‘Our Bodyguards’ at NSC, Delhi; and ‘Global Changes’ at RSC, Bhubaneswar were inaugurated. Major educational programmes including Science Expo-2009 at RSC, Lucknow; ‘Science & Society’ at NSC, Delhi; seminar on ‘Water Crisis on Earth’ at BITM, Kolkata and many more programmes were organized during the year. |  |  |  |
| (ii) | On going new projects – SRSC, Solapur; | To inculcate scientific temper in public at large and students in particularly of that area |  |  | To set up Science Centres in the States of Maharashtra, | The work of SRSC, Solapur is almost complete. |  |  |  |
| (iii) | New Projects in NE states – RSC, Guwahati | To inculcate scientific temper in public at large and students in particularly of that area. |  |  | This project will be taken up as per Annual Action Plan being finalize for 2008-09 | The project RSC, Guwahati has been completed in 2008-09. |  |  |  |
| 21. | Science Cities | To popularize Science and Technology at selected centers in the country. | --- | 12.00 |  |  | -- | 6.00 |  |
| (i) | On Going Projects- RSC Raipur and RSC Ranchi | To inculcate scientific temper in public at large and students in particular. |  |  | These projects will continue during the Annual Plan 2008-09. | The construction work is in progress. |  |  |  |
| (ii) | New RSCs at: RSC, Pilikula (Mangalore); RSC, Coimbatore; RSC, Jaipur. | To inculcate scientific temper in public at large and students in particular. |  |  | These new projects will be taken up during 2008-09 subject to fulfillment of conditions under Science Cities norms\guidelines. | The work of RSCs at Pilikula (Mangalore); Coimbatore and Jaipur have already been commenced. |  |  |  |
| (iii) | Setting up of Science City, Bangalore | To inculcate scientific temper in public at large and students in particular. |  |  | This project will be taken up during 2008-09 subject to fulfillment of conditions under Science Cities norms\guidelines. | The project could not be taken up during 2008-09 due to non-identification of land by the State Govt. |  |  |  |
| (iv) | New Projects\ Proposals in Pipeline | To inculcate scientific temper in public at large and students in particular. |  |  | Proposals from Govt. of Kerala Andhra Pradesh, Assam and Himachal Pradesh under Preliminary stage 3 Projects for development of Oceanarium, Science Exploration Hall and Large Format Film- under process | These proposals are still in pipeline. |  |  |  |
| (v) | Setting up of Pushpa Gujaral Science City, Kapurthala, Punjab. | Construction of : Exhibitions Galleries Convention Hall Pyramid Structure Evolution Gallery Galleries Under Development: Energy Park Evolution Gallery( Dinosaurs Park) Digital Planetarium Upgradation of space Gallery Upgradation of health and Biotechnology Upgradation of Dinamotion Gallery (Fun Science) Virtual Reality Gallery & Cyber Space Science of Sports |  |  | The construction work of various galleries will be taken up alongwith development of galleries mentioned in the column (3) | Civil, public Health and Internal electrical works completed. External electrical works in progress. Construction of Conventional Hall and Administrative Building were completed. Dome structure of Evolution Gallery & Pyramid Structure building are under progress. Digital Planetarium and upgradation of Space Gallery completed. Rest of the works are almost near completion. |  |  |  |
| (vi) | Gujarat Science City at Ahmedabad | To develop a scientific temper, nurture and stimulate scientific faculties, promote innovative and experimental, activities, showcase breakthroughs in S&T, establish countrywide network |  |  | During 2008-09, its phase I activities will be completed like to attract about 5 lakhs visitors including school children , college students and other people. | Remaining work under phase I have already been completed. |  |  |  |
| 22. | Anthropological Survey of India | Committed to research activities on human population from bio-culture perspectives. Its activities include collection, preservation, maintenance, documentation and study of ethnographic materials as well as of ancient human skeletal remains. | 11.50 | 8.50 |  |  | 14.64 | 7.84 |  |
| (i) | Documentation and Dissemination | To maintain Anthropological Libraries in 7 Regional Centres and Central National Library at Kolkata. At present Survey possesses museum artifacts stored in all the seven zonal museums and central museum at Kolkata. |  |  | Libraries: Establishment of National Library for Anthrological Sciences at Saltlake Kalkata. Development and upkeep of existing regional libraries in the survey, Completion retro-conversion and digitization and interlinking with National Library Museums: Collection, conservation documentation, research, and maintenance & procurement of a mobile exhibition van. | Modernization of libraries in the survey continues. Work of retro-conversion and digitalization of all the libraries is under process. Number of books, national & international journals, papers etc. procured. Conservation & documentation of museum specimens continues. Development of all the museums of the survey is in process in terms of more interactive display of anthropological museum specimens and artifacts. Number of visitors visited zonal anthropological museums. |  |  |  |
| (ii) | Induction of DNA technology | Maintenance of Infrastructure already developed at Kolkata, Mysore, Nagpur, Shillong and Port Blair. Development of laboratory facilities with DNA technology up to PCR level and DNA Banking at Dehradun and Udaipur. |  |  | The management and augmentation of DNA laboratories. Induction of state of the art technologies in Tissue Culture (cell lines) High through put genotyping (DNA chip microarray) technology and core phenotypic facilities. Ancient DNA facility to be constructed at Mysore will be equipped with state of the art instruments. | Annual maintenance of the DNA labs is under process. Requirement of using relevant chemicals, reagent, consumables, gadgets etc. for analytical work in all the survey’s laboratories continues. Procurement of equipment in labs for research work continues. |  |  |  |
| (iii) | DNA Polymorphism of the Contemporary Indian Populations & Ancient Skeletal Material | Study and DNA analysis of the contemporary DNA samples |  |  | DNA analysis of the contemporary DNA samples will continue on the samples collected from different field investigations during the 10th Plan would continue in the 11th plan period. | Procurement of consumables accomplished for lab analytical studies. Fieldwork continues on scheduled locations communities, for collection of blood samples and data. Analysis of DNA sequencing is in process by deputing project staff from its Southern Regional Centre, Mysore to CCMB, Hyderabad for lab work of ancient DNA extraction from Roopkund Skeletal remains. |  |  |  |
| (iv) | Narmada Valley Excavation | The extensive excavation in Narmada Valley in search of Palaeo-anthropological materials, before submergence. |  |  | Narmada Valley exploration work which has been started in the year 2005-06 will continued in the year 2008-09 for extensive search studies. The field camp at Hosangabad (MP) establish for the exploration work. | Analytical research of the collected fossils from the Narmada river-bed continues in the Palaeo-anthropological Laboratory. During the period ‘Palaeoanthropology workshop and orientation programme’ was also organized. |  |  | In scientific research of this kind risk factors can not be predicted . Pending deployment of manpower through outsourcing on contractual basis for project research work, target could be affected. |
| (v) | NEW SCHEMES 1. People of India: Cultural Diversity (Five components) | a) Intangible & Tangible Cultural Heritage: Oral Traditions, Folk Taxonomies, Social Structure & Bio-cultural Adaptations with Gender Perspectives. b) Establishing a National Centre for Community Knowledge at the new building at Udaipur. c) National Centre for Visual Anthropology: Kolkata d) Man & Environment e) Bio-cultural Linkages with border area countries. |  |  | a) Formulation of programme\Schedule\Guidelines area of studies and continuation of first phase of fieldwork, as well as , initiation of Pilot Study in new locations concentrating SC\ST communities. b) Establishment of Centre and to procure equipment for digitization work. c) Initiation of establishing the centre for visual anthropology in the new building of the Head Office of the Survey in Kolkata. d) This project is meant for SC/ST, which requires extensive fieldwork to frame the All India schedule. e) Reconnoiter tour for collection of first hand information for the project. | a)Survey organized a workshop on “Syncretism in India: Multidisciplinary Approach” from 6-8 May 2008 in the Arunachal Institute of Tribal Studies, Rajiv Gandhi University, Itanagar. Deployed scholars from A & N Regional Centre, Port Blair are engaged in library work to collect the secondary data on Ongee community. Scholars are engaging to complete their annotated bibliography on their reconnoiter tours. b) Layout plan & concept document for developing the design of establishing a National Centre for Community Knowledge at the new building at Udaipur is under process. c) Deployed personnel completed tour to East Midnapur district of West Bengal wo study of coastal fishermen of West Bengal under the project “Fishing Technology (Coastal Areas) to enable to visual documentation under this project. d) Analysis of data collected from 24 villages from the core area ‘Achanakmar-Amarkantak Biosphere Reserve Study’ is in progress. |  |  | In scientific research of this kind risk factors can not be predicted . Pending deployment of manpower through outsourcing on contractual basis for project research work, target could be affected. A senior research scholar from North East Regional Centre has conducted a part of the Pilot survey before extensive field investigation. The survey organized a workshop on Cultural Linkages of Border Areas of North East India and Folk Narratives & Human Origin on 26-27 August 2008 at its NER Centre, Shillong. |
|  | 2. Bio-cultural Adaptations (Two components) | a) Community Genetics and Health in North – East India b) Genetics & Health: Family Study |  |  | a) A thorough and illustrative scheduled work is to be conducted for which the specialized scientists both outside-medical clinic and the survey’s representatives will be involved together for preparation of baseline for execution of the programme in different tribes, communities and other village and urban dwellers. b) The consortium has been formed for conducting international collaborative study involving ‘gene chip’ technology which will be initiative. | a) Formulation of programme schedule, procurement of consumables, reagents, chemicals etc. for lab analyzing work to continue. The survey conducted awareness campaign in the Holy Child higher Secondary School, Demthring, Shillong, followed by blood sample collection. After analysis of 311 blood samples collected with CBC automated cell counter the genetic cards are being made ready to be distributed among the students, |  |  | In scientific research of this kind risk factors can not be predicted . Pending deployment of manpower through outsourcing on contractual basis for project research work, target could be affected. |
| 23. | Nehru Memorial Museum and Library | Responsible for collection of books, newspapers, unpublished references, private papers/ photographs film takes, and also translation of important papers relating to Pundit Jawaharlal Nehru. | 7.40 | 4.00 |  |  | 7.92 | 9.20 |  |
| (i) | Promotion of Research/ Award of Fellowships. | To offer three levels of fellowships namely Senior Fellowship, Fellowships and Junior Fellowships and to institute, award scholarships and monitory assistance. |  |  | Working on different research projects and the findings of the fellows/ research papers created by them are being published in the form of monographs. During 2008-09 all the 32 fellows will be in position as only half of the positions have been occupied during 2007-08. | It is a regular feature to continue the ongoing research scheme namely “Promotion of Research in Modern Indian History and Contemporary Studies”, “Perspectives in Indian Development and “Indian and Changing Trends in world Economy and Polity”. During 2008-09, about only half of the positions were occupied. |  |  |  |
| (ii) | Publication Programme | To undertake to promote publication of books, monographs, periodicals and papers incorporating the research of the studies carried out at the NMML. |  |  | A project has also been taken up to publish the selected writings of C. Rajagopalachari. Recently Jawaharlal Nehru Memorial fund has requested NMML to take over publication projects of selected works of Jawaharlal Nehru. It has been agreed to this proposal. | The publication of basic research documents is a continuous effort. Also undertaken a project to publish the selected writings of C. Rajagopalachari. Also initiated taking over publication project of selected works of Jawaharlal Nehru from JN Memorial Fund. |  |  |  |
| (iii) | Seminars and Lectures | To organize lectures, seminars, symposia and conferences to promote and encourage the study of Modern Indian History. |  |  | Proposing to organize four seminars two at the national level and another two at the international level. Tuesday seminars and other lectures will also be organized as usual. | Organization of Seminars/lectures is an ongoing programme and seminars as mentioned in col.5 were organized. |  |  |  |
| (iv) | Oral History Division | To record the reminiscences of eminent persons who have played an important role in national development and to preserve the recording and the |  |  | Proposes to interview atleast 20 persons in the year 2008-09 and finalize at least 25 transcripts. Video recordings of interview will also be done. | It is a continuous process and this institute interviewed about 20 persons in the year 2008-09 and finalized the transcripts. |  |  |  |
| (v) | Development of Library a) Acquisition of books, Periodicals/ Resource Material | To maintain a Library of books, pamphlets, newspapers, periodicals, microfilms, still photographs, motions pictures, sound recording and other materials bearing on the History of Modern India with special reference to the Freedom Movement. |  |  | The Library will continue to acquire books, with a focus on Modern Indian History and related Social Sciences in addition to material on microfilm and photographs. | Addition of new books and periodicals is an ongoing process and during 2008-09 new books/ periodicals were added to its library. |  |  |  |
| (vi) | Nehru Planetarium Activities | We have taken over the Nehru Planetarium in August 2005. This is the only planetarium in the Capital and its programmes stimulate scientific interest among the children. |  |  | The civil structures of the planetarium need major repair including installing a new AC plant purposed to renovate the exhibition area. | It’s a ongoing process of regular maintenance work and minor repair work which were undertaken during the year including installation of a new A/C plant. |  |  |  |
| 24. | Indian Museum, Kolkata | Engaged in reorganization and renovation of galleries housing unique treasures of Indian and foreign art representing centuries of cultural ethos and tradition. | 5.00 | 8.50 |  |  | 5.80 | 3.89 |  |
| (i) | Modernization, development, renovation and upkeep of galleries of art, Archaeology, and Anthropology Sections | The objectives include refurbishing, modernization & renovation of different galleries and reserve collections with updated arrangements and techniques. |  |  | i) Reconstruction, renovation of galleries - 18 nos. ii) Setting up of new galleries - residual work - 2 nos. iii) Equipment purchase – 1 cases iv) Electrification of go-down – 1 case v) Showcase – redesigning – 1 case vi) Air-conditioning of gallery – 1 nos. vii) Fire proof arrangement – 1 nos. viii) Documentary film – 1 no. ix) Field collection – 200 nos x) Catalogue préparation-1nos. | Renovation works is in progress. Updating Arch., Art, Anth. Gallery Maintenance and upkeep of Long Arch. Gallery, Coin Gallery, Decorative Art gallery, Painting Gallery, Anthropology Gallery. Physical verified: i)Archaeological objects-3720 Coins-2960 Art objects-1126 Anth. objects-2741 |  |  |  |
| (ii) | Strengthening and modernization of security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. | To strengthen the security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. |  |  | i) Engagement of Security Agency & State Armed Police throughout the year. ii) Replacement of existing fittings, fixtures etc. - 10 nos. iii) Maintenance & purchase of upgraded & sophisticated security gadgets – 18 nos. iv) Illumination development of total campus area v) Upkeep of different electronic devices/fire/ burglary alarm, door frame and hand set metal detectors, CCTV etc. – 100 nos. vi) Purchase of computer -1 no. vii) Organization of training – 4 prog. viii) Construction of water tank– 1 scheme ix) Intermittent test of security system – 10 nos. x) purchase of vehicle – 1 no. | i)Engagement of State Armed Police guards ii)Engagement of Private security agency iii)Maintenance of CCTV iv)Upkeep and maintenance of different electronic devices. |  |  |  |
| (iii) | Programme of Education and Mass Communication Cultural Activities | Organisation of education activities and training programmes holding of temporary/ special & inter-state, in-house exhibitions, outreach programme through Museum on wheels (Museo Bus), organisation of National/ International seminar and workshop. |  |  | i) National / International seminars and workshop; ii) Mobile exhibition, temporary exhibition; iii) Mass Communication Cultural programme; iv) Annual and memorial lecture series; v) Training programmes – In-service training course and short course in museum studies, practical aspects of Museum methods; vi) Development of Auditorium & Exhibition Hall; vii) Preparation of leaflets, exhibition folders, invitation cards, handout etc. viii) Purchase of computer, wheel chairs for physically handicapped; ix) Reorganization & refurbishing of lecture room. | Organized cultural event, Acting Director attended the general conference of ICOM at Vienna, Austria also attended a seminar at NRLC, Lucknow and delivered lecture there. |  |  |  |
| (iv) | Reorganization of Scientific galleries (Zoology, Geology and Botany) - | To raise the standard of display and presentation of the scientific galleries and to bring them at level with that of the cultural galleries museum proposes to renovate and update the scientific galleries also with the expertise of the respective Surveys. |  |  | i) Extensive renovation of the Mammal Gallery ii) Reorganization of the Insect Gallery iii) Reorganization of showcase of Siwalk gallery iv) Introduction of intercom facility v) Maintenance of galleries under scientific survey | i)Zoological galleries present stuffed specimens as well as models of birds, reptiles, amphibians, mammals, fish, insects etc. ii)Botanical section highlight one gallery of the economic aspects of plant where specimens of medicinal plants, jute, tea, rubber etc. & process of extracting products have been demonstrated with the help of models and charts. |  |  |  |
| (v) | Special repairs and maintenance of Museum buildings (heritage) | To develop and structural conservation of Museum buildings and other infrastructural developments |  |  | Repair and maintenance of sewerage system, doors and windows, de-plastering, replastering and colour washing, construction of modernize ticket counter etc. | i)Main Museum building – Work on the renovation of the entrance of the main museum building is in progress. Renovation of Siwalik gallery is in progress. |  |  |  |
| 25. | Salar Jung Museum, Hyderabad | A museum of national importance houses rare and varied art collection from all over the globe acquired by Salar Jung I, II and III. | 6.00 | 8.50 |  |  | 8.30 | 7.94 |  |
| (i) | Project Building | Construction of additional floor over Western Block for expansion of Galleries. |  |  | Construction of additional floor measuring 2500 sq. mtr. For housing 4 new galleries. | The construction work of additional florr is under progress. Rs.1.36 cr. incurred in 2008-09. |  |  |  |
| (ii) | Developmental works (Existing Building) | Under taking various developmental works of the existing building including reorganization of Galleries, modernization of stores, conservation of manuscripts, library etc. |  |  | Replacement of flooring in verandas of first floor of main building. Miscellaneous works Re-wiring & Electrical Work Ivory Gallery. Carried forward works of galleries. Improvemental works like replacement of flooring, showcases, falls sealing etc. in the existing galleries. | The construction work is under progress. A sum of Rs.1.26 cr. has been incurred up to 31.03.2009. |  |  |  |
| (iii) | Upgradation of security | The security in the Museum is being upgraded by providing CCTV cameras, fire alarm system and fire hydrant system. |  |  | Amount required for upgradation of security of the museum for which the process has begun during previous year. | Upgradation of security in the museum has already been taken up by incurring Rs.1.83 cr. in 2008-09 |  |  |  |
| (iv) | Cultural and Educational Activities | Conduct of Special Exhibitions, Lectures, Workshops, Seminars and Mobile Exhibition etc. as part of the out reach activities |  |  | Educational activities like summer art camp, children week, museum week, 15 special exhibitions, seminars, workshops, special lectures, mobile photo exhibition etc. | All the activities mentioned in col.5 were taken up by the museum during the 2008-09 and incurred an amount of Rs.0.21 cr. |  |  |  |
| (v) | Computerization | Computerization of artifacts and office automation. |  |  | Digitization of all the objects and the networking to the reserved collection. | Digitization work of all object has been taken up by the museum. |  |  |  |
| 26. | Indira Gandhi Rashtriya Manav Sangrahalaya, Bhopal | A museum conceived as a growing movement to depict the story of human kind in time and space highlighting human biological and cultural evolution | 2.20 | 6.50 |  |  | 2.80 | 7.37 |  |
| (i) | Infrastructure Development | Develop infrastructure facilities for achieving the objectives of documentation, display and dissemination of rich and diverse cultural patterns of India through Education and Outreach activities and Operation salvage. |  |  | Museum Site Development (Works): (i) construction of 100 bedded dormitory accommodation (ii) Second phase of boundary wall (iii) internal road in the campus (iv) Cine video and Photo documentation building (v) children’s park. Indoor museum complex: Upgradation of existing exhibition galleries, develop new exhibition on the theme ‘India and the world’, construction of satellite display spaces. Open air exhibition: All the open air exhibitions Tribal Habitat Exhibition, Coastal & Desert Village exhibition, Exhibition on River Valley Cultures, exhibition on Hilly and Forested Village, Gallery on Island Cultures of India will be strengthen by adding new exhibits like traditional house from Tripura, Meghalaya, Manipur etc. | Construction of boundary wall/watch tower of 1.80 mt. ht, bore tube well completed and construction of sump tank & barbed wire fencing wall are under progress. A traditional house type of Maram community of Manipur and a new exhibits U-Hakpa consisting of huge woodcarving generated in camp at Manipur organized in collaboration with TMRC, Imphal. |  |  | Work for construction of Introductory Gallery for River Valley Culture emphasizing Narmada Valley is continuing. |
| (ii) | Operation Salvage | Systematic action for Salvage and vanishing aspects of traditional material culture is a need because as a result of accelerated rate of change and rapid urbanization, traditional material culture, folk and tribal art objects as well as age old customs and traditions in many parts of India are fast disappearing. A systematic programme of Salvage of such material is being carried out by collection and documentation. |  |  | Documentation in World Heritage Site at Hampi and another in Konark, documentation of various aspects of oral traditions in ethno-musicology and performing arts, collection of alternative literature and identification and salvage of rare objects will continue. It will also organize Education Camps, and encourage remanufacture of rare and vanishing artifacts, survey of various Indigenous Conservation methods prevalent among different Indian communities, and upgradation of techniques of such eco-friendly practices, collaboration with advanced Research Institutes will continue, regional and national level workshops on tribal\Ethno Medicine will be organized. | During the period under review, the museum officials visited throughout India to document art and craft traditions and other aspects of material culture of local people. Project for documentation of intangible cultural heritage of the villages situated around Bhimbetka World Heritage Site is continued. Documentation of World Heritage Site of Hampi and Konark is under consideration. |  |  |  |
| 27. | Other Programmes (Museums) |  |  |  |  |  |  |  |
|  | National Research Laboratory for Conservation of Cultural Property, Lucknow | To develop the capabilities of different cultural institutions in the country in the conservation of cultural property and provide conservation services to Museum, Archives, Archaeology departments and other similar institutions. | 2.11 | 3.00 |  |  | 2.38 | 1.35 |  |
| (i) | Research in Conservation | To develop and standardize better methods of conservation |  |  | 10 projects including 3 continuing projects from the previous year will be undertaken. | Experiments were conducted in the ongoing projects. Data were collected. |  |  |  |
| (ii) | Conservation service | To provide conservation services to different museums, art galleries and related departments |  |  | 20 textile objects from State Museum, Lucknow 14 manuscripts and 28 loose folios from Rastriya Sanskrit Sansthan, Allahabad 135 objects of ivory, textiles, wood etc. belonging to Craft Museum, Lucknow 10 Coins belonging to AMU 4 Oil Paintings from Raj Bhawan, Lucknow | Thangka-2 Books-10 Objects-132 Coins-10 Oil painting-4 |  |  |  |
| (iii) | Development of infrastructure | To upgrade the conservation facility at RCL Mysore. To upgrade infrastructure in NRLC. Construction work of Training Institute at Lucknow. |  |  | Conservation of 30 big size oil painting of Mysore Palace. Conservation work of collections of Central excise, Goa like paper(23), Metals(56), wood (4), Skin fur(4), Stone(17) and other miscellaneous objects completed. 2 big zie oil paintings and 2 wall paintings of Meenakshi Temple, Madurai Completed. Conservation work of paintings in the State Museum, Goa started. Organized a special 10 week course on conservation of wall paintings from July, 08 to Sep, 08 in which 7 in-service candidates states of India participated. | Completed Completed In progress In progress Organized |  |  |  |
|  | ICOM-CC Triennial Meeting | To organize the Triennial Meeting in September 2008 for which NRLC is the model agency |  |  | XVth ICOM-CC Triennial Meeting will held in Sep. 2008. | To mutually have knowledge of various scientific studies for developing suitable conservation treatment from this international meeting . |  |  |  |
| (b) | Victoria Memorial Hall, Kolkata | Museum of contemporary art involved in collecting material and data relevant to a period depicting art history during the freedom struggle. | 2.70 | 7.50 |  |  | 4.14 | 3.00 |  |
| (i) | Preservation, Restoration and Conservation of Art Objects | To preserve the Cultural Heritage of Modern Indian History (Oil painting, Water Colour Aquatints, Miniature, Lithographs, Manuscripts, Coins, Medal, Arms & Armour etc.) |  |  | 24 Oil paintings Restoration of Paintings of N.E. States (as per request) Conservation of 12 antique frames. Technical assistance to others institutions on curative and preventive conservation Purchase of new equipment\ instrument and other materials for restoration lab. Laptop, stereomicroscope, optivisor etc. Visit to other labs in India. NRLC, Lucknow, Govt. Museum, Chennai. Conservation of Paper\metal objects Purchase of Conservation materials | 4 oil paintings and 136 paintings were completed. 2 antique frames were restored. 10 photographs received from Raj Bhawan were conserved. 12 marble busts at Raj Bhawan were conserved. 4 water colour paintings received from Bhaskar Bhawan was conserved and returned. 63 colour aquatints, water colours, pen and ink drawings etc. were objects completed. 17 MSS completed. Justice Hyde Report containing 385 sheets were completed and 10 books from library was completed. |  |  |  |
| (ii) | Domestic Exhibition | To familiarize the public at large about the richness of the collections and to communicate our past history, culture and aesthetics and atleast one traveling exhibition in any one of the Metropolitan cities in India. |  |  | Five exhibitions comprising of water colours of Samuel Davis depicting rural life in India, paintings on 18th Century birds and Animals of India by Arthur Davis and Robert Homes, works of Rabindranath Tagore, Jamini Roy, A.N. Tagore and other artists, works of Bonod Bihari Mukhopadhaya in collaboration with the NGMa, Travelling exhibition in metropolitan cities including North East Region. | Temporary exhibitions based on the reproduction of Jamini Roy’s Art work from the collection of VHM was held at Bishnupur, Bankura during the year. ‘Select View of Daniell’s Oriental Scenery’ was viewed at Ganga Festival 2008 at Ahiritola, Kolkata. |  |  |  |
| (iii) | Documentation, Cataloguing, Accession, Stock verification of art objects, photo-documentation etc. | To preserve and conserve the various important papers and photographs collected by the museum |  |  | Accessioning and Cataloguing of recently acquired artifacts and photo documentation. Photo documentation of museum objects digitization Verification and preparation of consolidated Accession Register. Technical assistance to other organizations Proposal for production of two documentary films on Begum Rokeya Sakhawat Hossain and Abanindra Nath Tagore. | 189 artifacts were done. Physical verification 13000 stamps and 400 oil paintings were done. |  |  |  |
| (iv) | Strengthening of Security | To safeguard the artifacts and the monument from vandalism and theft and to protect the cultural property |  |  | Installation of fire alarm & Firefighting system, Surveillance System(CCTV), 12’ barbed wire fencing on the perimeter wall and deployment of Calcutta Police/ CISF for guarding the campus and museum galleries as per recommendation of C.I.S.F | ECL was already requested to replace the camera which is not working. Deployment of 46 Kolkata Police is continuing. |  |  |  |
| (v) | Acquisition of art objects | To augment our existing collection of artwork through Art Purchase |  |  | Acquisition of Art objects (Kalighat Paintings, paintings of the artists of Bengal School – Abanindranath, Nandalal Bose, Jamini Roy and their students art work of other modern Indian masters. Other historical objects, objects of artistic and historical value relevant to the areas of concern of V.M. | No Art Purchase Committee meeting was held during the year. |  |  |  |
| (c) | Allahabad Museum, Allahabad | The main activities of the museum include acquisition of art objects, reorganization of galleries and reserves enriching the library and photography unit and publication | 1.60 | 1.80 |  |  | 2.00 | 0.99 |  |
| (i) | Renovation of building | Renovation of old sitting rooms of the Asstt.Keepers and other; Director residence in the museum; museum main gate and ticket etc.; Award of Annual Maintenance contract to CPWD civil and electrical |  |  | The various civil works detailed in column 3 will fulfill pressing needs of the Museum and will also give an attractive and impressive look to the museum building\premises | The work was got executed through CPWD within time bound frame. |  |  |  |
| (ii) | Library | To strengthen the library collection and also to acquire number of journals and volumes of sets possessed by the museum, to microfilm certain books and journals which are not available by sending a team consisting of Museum personnel and to acquire books and journals of importance to enrich the Museum library. |  |  | Routine work of classification, cataloguing and computerized book inventory; binding of books, cataloguing of Persian manuscripts by engaging an expert, purchase of Library Software; purchase of Library books. | Additional books were acquired after ensuring the new books do not already exist in the library. |  |  |  |
| (iii) | Modernization of galleries | The objectives include wood paneling, fabrication of new showcases\wooden blocks, modernization\reorganization work in various existing galleries of the museum. |  |  | Wood paneling in Minor Archaeological and Sculpture galleries. Fabrication of wooden blocks for partition in Coomaraswamy Hall and new showcases and renovation of old ones departmentally. | The work as mentioned in col.5 are under progress. |  |  |  |
| (iv) | Acquisition of Art Objects | To acquire art objects for the Museum through Art Purchase Committee in its meeting to be held at suitable intervals. |  |  | To augment Museum’s collection of antiquities with rare objects. First meeting of Art Purchase Committee to be held in Sep. 2008 and second meeting in Feb 2009. | Various antiquities were acquired on the recommendation of the Art Purchase Committee. |  |  |  |
| (v) | Exhibition and display | To encourage the budding artists of the country and to increase the knowledge of religion and culture of people of North Eastern Region |  |  | Reorganizing reserve collection of explored material, preparing showcases for Bronzes and Archaeological objects, exhibition of renowned sculpture artists Shri Gyan Singh and Shri Lallen Singh, exhibition of prize winning Painting\ Clay models prepared by participants of Painting Clay \modeling workshops, installation of Thangka gallery and Touch Screen information Kiosk | A number of exhibitions were held as indicating col.5 in Allahabad Museum and other educational institutions in a phased manner. |  |  |  |
| (vi) | Chemical conservation laboratory | To provide conservation services in the museum. |  |  | Reutine work of fumigation, anti-termite treatment; conservation of coins, 500 manuscripts, 100 paintings; purchase of chemicals and other materials; organization of workshops on Care and Maintenance of Art Objects and Museology and Conservation etc. | Work relating to conservation was carried out as and when necessary on demand from Sectional In charges. |  |  |  |
| (d) | National Museum Institute of History of Art, Conservation & Museology, New Delhi | To provide education and training in the specialized areas of art, history, conservation and restoration of artifacts and their display and upkeep in museum. | 0.21 | 4.00 |  |  | 0.26 | 1.60 |  |
| (i) | Academic Programme | Teaching & training leading to award of M.A & Ph. D degree in three disciplines namely History of Art, Conservation and Museology. Conducting short term courses in India Art & Culture, Art Appreciation & Bhartiya Kalanidhi on once a week basis for 5 months for the awareness of Art Conducting Seminars\Workshops\conferences on the topics related to History of Art, Conservation & Museology which require special attention. Holding of special lectures of eminent scholars in three disciplines. |  |  | To admit a maximum of 55 students in M.A. degree course as follows: M.A. (HOA)-25 M.A (Museology)- 15 (iii) M.A (Conservation)- 15 Ph.D As per capacity of respective supervisor\faculty members To admit a maximum of 300 students in short term courses One International Seminar and 3 National Seminars\workshops\ conferences 12 special lectures | 25 students in MA (HOA), 15 students in MA (Museology), 15 students MA(Conservation) were admitted in the institute. In addition to this, 14 students for undertaking Ph.D were also enrolled during the year. 200 students in short term course were also admitted. 1 international seminar and 3national seminars/ workshop/ conferences were conducted during the year. 12 special lectures were also held. |  |  |  |
| (e) | Scheme for financial assistance for ‘Promotion & Strengthening of Regional & Local Museums’ | To promote the strengthening and modernization of existing museums at the regional, state and local level. In addition to this setting up of one district museum under the scheme to be taken up. | -- | 12.00 | It has been decided to include setting up of one district museum in the existing scheme. Draft EFC has already been circulated for comments. However about 50 museums will be benefited for the grants under the scheme. | Grant amounting to Rs.7.68 cr. released to 27 museums/ organizations for their modernization and upgradation. | -- | 7.68 |  |
| (f) | Scheme for Modernization of Museums in Metro Cities | In order to bring some of the Museums in the Country at par with the best in the World. | --- | 7.00 | Modernization of two museum one at Egmore Museum, Chennai and other at Chhatrapati Shivaji Vastu Sangrahalaya, Mumbai is proposed. | Grant of Rs.7.00 cr. Released to Chatrapati Shivaji Maharaja Vastu Sangrahalaya, Mumbai | -- | 7.00 |  |
|  |  | Total (Archaeology, Archives, Museums) | 278.35 | 227.30 |  |  |  |  |  |
| 28. | National Library, Kolkata | To serve as a repository of all reading and information materials produced in India as well as abroad concerning India | 16.00 | 7.00 |  |  | 15.56 | 6.87 |  |
| (i) | Collection Building & Book Production Statistics | To collect books and other printed materials published in India, Acquisition of Foreign Books and Periodicals |  |  | Foreign books- 3500 Foreign journals-680 Indian publication to be acquired -40000 | 22100 Indian publications, 1920 foreign books were acquired/purchased and purchased 580 titles of foreign journals. |  |  |  |
| (ii) | Retro-conversion Project & Digitization of old, Rare publications | Retro-Conservation, Digitization and Modernization of Laboratory, Preservation Computer Units |  |  | Retro-conversion of 4 lakh records targeted. 14 lakh pages to be digitized | The project was initiated for retro-conversion of 25 lakh bibliographic records out of which 4 lakh records completed. More than 25 lakh pages was scanned. |  |  |  |
| 29 | Delhi Public Library | To provide free library and information services to the people of NCT of Delhi and also to provide mobile library services in rural area of Delhi. | 8.00 | 4.25 |  |  | 10.37 | 3.50 |  |
| (i) | Collection Developments | The basic objective of DPL is to provide free library and information services to people of Delhi. In order to achieve this objective, DPL proposes to strengthen its collection development in all the service units. Besides this updating of Reference Collection of Central Library and Sarojini Nagar will also be taken up by acquiring new reading materials. |  |  | Around 4000 titles (60,000 Multiple Copies to be purchased for the DPL system in English, Hindi, Urdu, Punjabi, Besides audio & video cassettes also. | 6530 titles (66124 multiples copies of Hindi, Eng. Punjabi, Urdu Books) and 700 DVD titls (2100 multiple copies of Hindi & Eng. DVD) were purchased. |  |  |  |
| (ii) | Conservation and Preservation | Binding care and repair of books and other reading materials are continuous activity of DPL. Preservation of documents is a compulsion in a library for posterity purpose. |  |  | Around 20-25 thousand new books are to be bound through commercial bookbinders. | 4361 books bounded |  |  |  |
| (iii) | Modernization and IT Development | Modernization of library activities is the continuous process of DPL. It is proposed to augment the computer system of library, which requires more computer, server, scanner, operating system, ISM etc. for creating of database in other Indian languages. |  |  | It is proposed to setup internet club in three libraries having ten terminals-Patel Nagar, Sarojini Nagar & Central Library. During the plan it is proposed to add 500 DVD’s in English & Hindi for the DVD corners to be setup in the three libraries. Retro-conversion of existing CDS ISIS. English & Hindi database in MARC format through outsourcing. | 56 computers and other accessories for automation of library activities were purchased |  |  |  |
| 30. | Raja Rammohun Roy Library Foundation | To promote and support public library movements in the country. | 2.30 | 26.50 |  |  | 2.80 | 30.00 |  |
|  | Matching Schemes: a) Assistance towards building up of adequate stock of books b) Assistance towards organization of mobile libraries and rural book deposit centers c) Assistance towards storage of books d) Assistance towards seminars, workshops and book exhibitions e) Assistance to public libraries towards increasing accommodation f) Assistance towards acquisition of TV-cum-VCP sets for educational purpose/Computer for library application g) Special scheme of Networking of Public library Non-matching Schemes: a) Assistance to voluntary organizations providing public library services b) Assistance to children libraries of children section of general public libraries c) Assistance to state central libraries and district libraries through central selection of books d) Assistance to centrally sponsored libraries –affiliated libraries under Visva-Bharati e) Assistance towards organization of seminars, conferences etc. of an all India level Professional body like ILA, etc. f)Assistance to public libraries towards centenary celebrations g) Assistance towards establishment of Children's corner Assistance to DYRCs New Scheme to be implemented if approved | Replenishment of book stock of libraries Providing library facility to remotest corners Providing storage materials Providing awareness, orientation to library professionals Construction of Library building Supply of audio-visual aid and supply of computers for automation Networking of Public Library To encourage voluntary zeal towards providing library service To promote reading habit amongst children Replenishment of book stock with recent costly books Replenishment of book stock with recent costly books To encourage National Professional Organizations To encourage old libraries To attract children users Development of District Youth Resource Centre Establishment of Knowledge Centre at Block Level |  |  | Libraries – 9000 Book – 35,0000 Libraries – 80 Libraries – 3500 Organization –80 Libraries – 140 Libraries – 100 Libraries – 2 Libraries-200 Libraries-125 Libraries-476 Books – 15,0000 Libraries-37 Organizations –5 Libraries-40 Libraries-70 Libraries-296 Libraries-1041 | FA granted to a number of libraries as indicated below. Libraries – 9105 Libraries – 90 Libraries-3423 Oraganization-90 Libraries – 136 Libraries -97 -- Libraries-233 Libraries-133 Libraries-479 Libraries-37 Organizations –7 Libraries-40 Libraries-60 Libraries-39 -- |  |  |  |
| 31. | Other Libraries |  |  |  |  |  |  |  |  |
| (a) | Central Reference Library, Kolkata | To implement (a) Compilation and publication of the Indian National Bibliography (in Roman script and respective language scripts) which is a bibliography of current Indian Publications in Indian languages recognized by the Indian Constitution and in English and (b) Compilation and Publication of Index Indiana. | 1.15 | 0.50 |  |  | 1.54 | 0.44 |  |
|  | Indian National Bibliography, Index Indiana & other activities- Language Bibliographies, Bengali, Tamil, Hindi, Malayalam, Urdu | Compilation & Publication of INB monthly issues 2008 Compilation & Publication of Annual Volume 2007. Compilation & Publication of Index Indiana Apprenticeship Training programme North East Region development programme Regional data collection centers at Delhi, Chennai, Mumbai and Guwahati. |  |  | 12 Monthly issues of 2008 INB Manuscript of INB 2007 Annual Volumes 250 copies of INB Annual Volume 2006 8 batches of 40 students to be trained in Librarianship, 3 Training/ Workshop/Seminar/ Programme Assamese, Urdu and Hindi bibliography, Putting the INB data on the net. | 250 copies of Annual Vol. of INB 2005 Manuscript of 2006 INB Vol. to be ready 12 monthly issues of INB, 2007 100 copies of Index Indiana 1999-2000 100 copies of Tamil Bibliography, 250copies of Bengali Bibliography published |  |  |  |
| (b) | Khuda Bakhsh Oriental Public Library, Patna | This Library has been evolved out of a personal collection of Maulvi Mohd. Bakhsh who was a man of letters with a great passion of books. It houses over 20000 manuscripts and some rare printed books. | 1.68 | 1.69 |  |  | 2.34 | 1.06 |  |
| (i) | Acquisition: Purchase of Books, manuscripts, microfilms, Video & Audio Cassettes | To acquire books, manuscripts, microfilms, Audio & Video CDs for use of readers |  |  | Purchase of 4682 books, 5 manuscripts and 69 periodicals, 28 Newspapers, 169 Audio & Video cassettes | Acquisition of 5000 books and manuscripts |  |  |  |
| (ii) | Research & Publication: Publication of rare material , Printing of Catalogue, Research seminars, Lectures & Cultural programmes, Khuda Bakhsh Research Fellowships and Publication of Quarterly Journal. | To bring out critical editions of manuscripts, publish books of rare value, lectures by distinguished scholars. To acquaint the outsiders with the hidden treasure descriptive catalogue. Organization of seminars, lectures of distinguished personalities. Fellowship and Scholarships to renowned scholars. |  |  | Publication of 20 books. Printing of 2 volumes of catalogue and 2 volumes of Hand lists. organize National Seminars, Annual Lectures, Extension Lectures, Popular Lectures. Senior Fellowship – 3 Junior Fellowship – 7 Publication of 4 issues of Journals. | Publication of 20 books Printing of 2 vols. Of Descriptive catalogue of Manuscripts and 2 hand lists(Arabic & Persian) 6 seminars, 1 Annual Lecture, 8 Ext. lectures, 12 P.letures, 3 Exhibition, 1 Mushaira were organized. |  |  |  |
| (iii) | Conservation & Preservation : Preservation Laboratory and development of books preservation & reprographic facilities | Preservation Lab. For routine maintenance, curative as well as preventive and preservation. To keep the books in the good condition. |  |  | Routine, preventive and curative treatment of books and manuscripts. 100 manuscripts and 300 printed books bound on contract basis. | To keep the literature in good condition. |  |  |  |
| (iv) | Cultural Exchange: Exchange of visits with counterpart abroad & (b) strengthening of security | To invite scholars/librarians from abroad under CEP and to visit countries to see their collection. |  |  | Director’s visit to one of the countries holding rich collection of Arabic & Persian manuscripts is proposed. (b) Security arrangements will be strengthened. | Efforts are underway to invite one Librarian from U.S. library of Congress Washington D.C. |  |  |  |
| (c) | Thanjavur Maharajas Serfoji’s Saraswati Mahal Library, Thanjavur | A priceless of repository of culture and knowledge, it was conceived as the Royal Palace Library in the 16th century. | --- | 0.80 |  |  | -- | 0.72 |  |
| (i) | Publication of books from the manuscripts in Sanskrit, Tamil, Marathi etc. | To translate, transliterate the manuscripts and to bring out books. |  |  | 50 books | 50 books were published during the period. 41 books for various branches were purchased. |  |  |  |
| (ii) | Conservation | To apply citronella Oil to Palm leaves and to preserve the Paper manuscripts/ Valuable Old books etc. |  |  | To clean and apply 600 leaves Manuscripts per day and to clean and preserve 20 books daily. | Cleaning of 135000 leaves of manuscripts, & 2040 books were conserved/mended. |  |  |  |
| (iii) | Micro Film | Microfilm of Manuscripts and rare books for preservation. |  |  | 600 frames daily | 600 films daily , 35 film rolls utilized , 437 MSS micro filmed, 437 number of index prepared on microfilms. |  |  |  |
| (iv) | Research activities | Visiting and consulting other libraries for reference work. |  |  | It is a long standing process of every year. | A training course on Tamil manuscriptology was conducted, 4 candidates are enrolled of Ph.d course. |  |  |  |
| (d) | Central Tibetan Library | Aim to acquire and conserve Tibetan books and manuscripts and to provide intensified reference service as well as Centre for Tibetan manuscripts, paintings and object of Arts. | -- | 0.55 | The ongoing activities of the Library continued to provide research facilities including documentation and written material for regular courses on Buddhist philosophy and Tibetan tradition. | Library has been undertaking various programmes for dissemination of all aspects of Tibetan civilization and also Buddhist philosophy in India. | -- | 0.52 |  |
| (e) | Rampur Raza Library, Rampur | The main objective of the library to acquire and conserve Indo-Islamic manuscripts, miniatures, books and other objects of arts and science in the library and to serve as a centre of reference and research and also act as a centre of Arts for International importance. | 1.30 | 2.40 |  |  | 1.31 | 2.95 |  |
| (i) | Publication & Printing | Publication of books of text of Arabic, Persian and Sanskrit manuscripts. |  |  | Publication of books, journals, technical reports and painting. | 12 books were published |  |  |  |
| (ii) | Preservation and Renovation of two Heritage Buildings. | Two historical palaces of Raza Library viz Hamid Manzil and Rangmahal are monuments of archaeological importance. They involve scientific repairs of archaeological or special nature. |  |  | 2 buildings namely Hamid Manzil and Rang Mahal. | Colour wash and repair of both buildings were done. Semi golden paint in Darbar Hall of Hamid Manzil also has been done. |  |  |  |
| (iii) | Acquisition of Books, MSS Scholarships and awards Seminars/workshops/exhibitions Preservation and conservation of the collections | Acquisition of rare mss books and art objects for meeting the demands of research scholars Organizing Akademic and cultural activities for interaction of scholars, akademicians To protect prices less collection of the library |  |  | 50 rare mss 2500 books and 120 art objects 5 scholarships and 3 awards 2 seminars, 2 workshops, 4 exhibitions and 2 lectures about 4500 pages of rear MSS art objects | 527 printed books 31 manuscript 27 art objects were purchased. 6 Scholarships awarded. Exhibitions, 2 Mushaira, Kavi Sammelon lectures were organized. |  |  |  |
| (f) | National Mission for Manuscripts | Aims at cataloguing, conserving and collecting the invaluable manuscripts from all over the country and to strengthen manuscript resource centers, manuscript conservation centers and digitization of catalogues and prestigious manuscripts. | --- | 9.50 |  |  | -- | 8.33 |  |
| (i) | Networking with Institution and Private repositories across the country through MRC | To identify, document, digitize the important and valuable Manuscripts. |  |  | 5 lakh manuscripts documentable | This work is under progress. |  |  |  |
| (ii) | Networking through MRCs- | Documenting the available manuscripts in MPCs. |  |  | 10 MPCs to be identified to entrust work. | Work completed |  |  |  |
| (iii) | Networking through MCCs | Conservation and training |  |  | To run the existing 33 MCCs. | Continuing process |  |  |  |
| (iv) | Networking MCPC | Conservation and training |  |  | To identify 50 MCPC | completed |  |  |  |
| (v) | Creating resource pool of skilled conservators | Regional workshops @ Rs. 3 lakh for 10 such workshops in the year 2007-08. |  |  | To conduct 10 regional workshops @ Rs. 3 lakh per each such workshop. | Various regional workshops conducted during the year. |  |  |  |
| (vi) | Digitization of Important manuscripts | To continue 2nd phase of digitization to digitize 20,000 rare manuscripts |  |  | To continue 2nd phase digitization for additional Qty of 20,000 manuscripts. | The work has been undertaken. |  |  |  |
| (vii) | National Survey | To carryout National Survey to identify the manuscripts |  |  | To make National level Survey in 7 states. | Work is near completion |  |  |  |
| (g) | Setting up of a National Mission on Libraries, leading to the formation of a Commission | To pointedly address the problems of Public Libraries and to upgrade the infrastructure and technological environment of the Public Libraries within a time frame | --- | 1.00 | Token provision has been made to initiate the spade work. For its implementation the matter has been taken up with Planning Commission for IPA. | The EFC Memo had been sent to Ministry of Finance for an EFC meeting. MoF has suggested to revise the scheme within the approved outlay of 11th Plan i.e. 180 crore. |  | 0.04 | A task force has been constituted to draft the EFC Memo within the approved outlay of Rs.180.00 crore. |
| (i) | State Central Library, Mumbai Modernization/ computerization/ Digitization/Up gradation of State Central Library | To acquire books and periodicals under the provision of press and registration of Books Act, 1867 and the delivery of Books Act, 1954 and preserve them for posterity To digitize rare books and manuscripts: Computerization/ Retro-conversion of DBA. | 0.30 | 0.20 | In the first phase 10 lakh pages of old / rare books/ manuscripts shall be digitized. Approx. 4 lakh DBA books are to be computerized. | 10000 books, 500 periodicals and 3000 newspapers received in DBA Section were technically processed and provided library services to 1 lakh readers. | 0.28 | -- |  |
| (j) | Conemara Public Library, Chennai | It is one of four recipient of Public Libraries under the provisions of the Delivery of Books and Newspapers (Public Libraries) Act of 1954 to receive all materials published in India free of cost. It serves as a UNESCO information center and receives all the publications of UNESCO. It is also a depository for Asian Development Bank Publications. | 0.30 | 0.60 | Standard works excluding pamphlets, children books etc Newspapers Periodical titles etc. The work of Gazette Notification, bulletins, maps, children’s books etc. will be accessioned, processed and maintained. | 9401 standard books acquired. Seminars and computer training for the staff were held. 200717 pages scanned and 5000 books bound. | 0.30 | 0.60 |  |
| 32. | Provision for Project/ schemes of N.E. Region and Sikkim | -- | 60.00 |  |  | -- | ** |  |
| a | Project/ Schemes for promotion of Art and Culture | To promote, disseminate and protection of art and culture in NE States | -- | 37.09 | Organizing various programmes in the field of art and culture in various cities of the North Eastern States. | A number of cultural programmes were organized in collaboration with State Govt./ Institution/ Universities | -- | ** | **expenditure incurred in NER has been included under respective schemes/ organizations |
| b | Archaeology, Archives and Museums | To promote cultural activities in the fields of Archaeology, Archives and Museums | -- | 18.31 | Development of Museums in North East Region and providing financial support to NGOs in N E R in the field of Archival activities. | A number of cultural programmes/ activities were organized in fields of Archaeology/ Museum & Archive | -- | ** | **expenditure incurred in NER has been included under respective schemes/ organizations |
| c | Libraries | To promote Library activities in the NER | --- | 4.60 | Development of Library activities in North East Region. | Many activities were undertaken in the field of Library |  | ** |  |
|  |  | Total ( provision for NER) | --- | 60.00 |  |  |  | ** |  |
| 33 | Building projects of attached / subordinate offices |  |  |  |  |  |  |  |
| 1. | National Gallery of Modern Art | (i) NGMA’s new Wing , New Delhi | --- | 20.00 |  | Work completed | -- | 8.86* |  |
|  |  | ii) Manikavelu Mansion, NGMA, Bangalore |  |  | Capacity creation for the galleries. | Work completed |  |  |  |
| 2. | National Archives of India |  | --- | 1.80 |  |  | -- | 0.29 |  |
|  | (i) | Upgrading diesel generator set and A/C plant for NAI. |  |  | Creation of additional office accommodation and storage for records. | Work is still to be undertaken |  |  |  |
|  | (ii) | Completion of remaining works such as Air Conditioned Plant, ducting at NAI, Jaipur. |  |  |  | The work is under progress. |  |  |  |
|  | (iii) | Construction of functional building of record center, Bhubaneswar |  |  |  | The work is under progress. |  |  |  |
|  | (iv) | Proposal for acquiring 0.21 hectares of land adjacent to Record Centre, Pondicherry. |  |  |  | Land still to be acquired. |  |  |  |
|  | (v) | Addition and alteration of works of NAI Main/ Annexe building, Record Centre Jaipur and Pondicherry and Regional Office Bhopal. |  |  |  | The work is under progress. |  |  |  |
| 3. | Anthropological Survey of India | --- | 4.50 |  |  | -- | 1.25 |  |
|  | (i) | Procurement of additional land for museum and construction of Office building at Salt Lake, Kolkata |  |  |  | The project is still to be undertaken. |  |  |  |
|  | (ii) | Procurement of land and construction of Museum at Central Regional Centre, Nagpur. |  |  |  | The project is still to be undertaken. |  |  |  |
|  | (iii) | Construction of residential quarters guest house and Museum of International Standard etc. at Udaipur |  |  |  | Work is under Progress |  |  |  |
|  | (iv) | Construction of residential quarters and guest house of North West Regional Centre, Dehra Dun. |  |  |  | Work is under progress |  |  |  |
|  | (v) | Procurement of additional land and construction of an International standard guest house DNA lab. At the SRC, Mysore. |  |  |  | Work is under progress |  |  |  |
|  | (vi) | Construction of Office Building and museum at SRC, Jagdalpur |  |  |  | Work is under progress |  |  |  |
| 4. | National Research Laboratory for Conservation of Cultural Property, Lucknow |  | --- | 3.00 | Construction of : i. Training Institute in conservation at Lucknow. | Work is under progress | -- | * | *included under NGMA Head |
| 5. | National Museum |  | --- | 2.00 |  |  | -- | * | *included under NGMA Head |
|  |  | Dismantling of ASI structure and start of construction of III Phase of National Museum Building. Upkeep , strengthening and development of museum building |  |  | Work still to be taken up. | The upkeep and maintenance work is under progress. |  |  |  |
| 6. | National Library |  | --- | 0.82 |  |  | -- | -- |  |
|  |  | i. Construction of readers’ hostel |  |  | Work still to be taken up. | No work/project was taken up |  |  |  |
|  |  | ii. Construction of Type-II & III Quartes. |  |  |  |  |  |  |  |
|  |  | iii. Construction of Garden Superintendent Office-cum-Godown. |  |  |  |  |  |  |  |
| 7. | Archaeological Survey of India | Construction of building and staff quarters for ASI at Dharwad, office building at Nagpur, Mysore, construction of Institute of Archaeology at Greater NOIDA, linear building at 24, Tilak Marg, New Delhi. Purchase office complex at Raipur. Construction of office building for ASI at INA, New Delhi, construction of staff quarters for ASI at Aihole and 10 new projects to be carried out during 2008-09. | --- | 14.00 | Work is under progress | The work is under progress. | -- | 12.70 |  |
|  |  | Total (Building Projects) | --- | 46.32 |  |  | -- | 23.10 |  |
|  |  | Grand Total (Art and Culture) | 425.00 | 600.00 |  |  | 518.61 | 517.50 |  |