| 1. |  | a). Secretariat Social Service | To modernize the accommodation for efficient functioning of the Ministry and also provide Information and Technology support. Maintenance of the office equipments and procurement of stationery. | 15.00 | 1.00 | Replacement of old and obsolete computers/photocopier in the Ministry. Digitization of old records lying in the Sections/Units for making clutter free working environment. Modernization of office accommodation. Renovation of 7 rooms (P&B, S&F Account cell, record room etc.) | Purchased 10 computers (9 desk tops and one laptop), 6 photocopiers. Other office equipments too have been purchased on need basis. | 13.66 | 0.45 | Normally, non plan grant is used for administrative and establishment expenses. Proposal for purchase of new computers in pipeline |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | b). Central Secretariat Library (CSL) | To provide information and research services to Academicians, Research Scholars and Policy Planners. It is the main reference library for all purposes. | 1.95 | 2.40 | To replace out dated server, new high end server to be installed. Automation of circulation through bar coded tags to be introduced, training programmes for new technological developments to be conducted, purchased of books, selves and trolleys, improvement infrastructure and face lifting of R.K. Puram branch library, digitization work of GOI Gazettes/Notifications | Installation of Mike system in the conference hall, fire alarm system, modernization/ renovation of CSL second floor hall. 1473 titles books in English and in Hindi and 1800 titles in regional languages, 70000 old and absolute title books identified and created on the computer. | 0.44 | 1.05 | Normally Non Plan Grant is used for administrative and establishment expenses |  |  |
| 2. |  | Zonal Cultural Centre | Aims at the promotion of Grass-root Culture and Cultural Kinships which transcend territorial boundaries and to arouse and deepen awareness of local culture. | -- | 14.00 | Includes 30% provision towards pro-women, and 20% provision for ST population |  | -- | 16.28 |  |  |  |
| (i) |  | National Culture Exchange Programme | Exchange of artists, Musicians, performers, & sculptors etc. between different regions within the country for the promotion of rich cultural heritage of India. |  |  | About 385 programmes would be organized benefiting a large number of artistes | More than 220 programmes organized benefiting a large number of artistes deployed at fairs, festivals, cultural events to dissimilate the cultural diversity across the country. |  |  |  |  |  |
| (ii) |  | Documentation of vanishing Art Forms | Documentation of various folk & tribal art forms particularly the vanishing art forms for their proper preservation. |  |  | Various folk & tribal art forms, work of great masters of member states would be documented as per advice of Programme Committee and research oriented projects would be taken in hand for publication | More than 96 documentation works have been taken up till 31.12.2009. |  |  |  |  |  |
| (iii) |  | Lok Tarang Folk Dance Festival | This festival is organized for Republic Day Celebrations during January each year for the promotion of our rich cultural heritage & national integration. This year it would be held during Commonwealth Games Delhi, 2010. |  |  | This festival provides a unique performance opportunity for the folk artists from various parts of country at the national level. | Organized in January every year, but this year, the Lok Tarang Folk Dance was organized in the month of October, 2010 during Commonwealth Games. |  |  |  |  |  |
| (iv) |  | Kurukshetra Utsav | Celebrated on the occasion of Geeta Jayanti Samaroh at Kurukshetra-a Sacred place related to Mahabharta |  |  | Very suitable occasion for the promotion of Indian art & culture. Classical & folk artists perform benefiting large number of people. Besides this a large number of craft persons are given opportunity to display & sell their products | The NZCC in collaboration with the Kurukshetra Development Board and Government of Haryana organized ‘Kurukshetra Utsav-Geeta Jayanti Samaroh – 2010’ at Kurukshetra from December 13 to 17, 2010. |  |  |  |  |  |
| (v) |  | Guru Shishya Parampara | For the promotion & preservation of our Fast vanishing art Forms |  |  | Not only Gurus but shishyas are also benefited. About 20 gurus with 100 shishyas would be benefited during the year. Art forms are decided in consultation with State Governments from time to time. | More than 53 units/Kendras to benefited Shisyas under this scheme during the year 2010-11 (upto December, 2010) besides the continuing units of previous year. |  |  |  |  |  |
| (vi) |  | Theatre Rejuvenation | Providing an opportunity to the theatre artists to stage plays & other theatre activities. Also interacting with each other on the Common platform |  |  | About 114 theatre groups would stage their plays and more than 1000 artists and a large number of people would be benefited. Workshops to promote theatrical skills will also be held. | This year, ZCCs have conducted various programmes viz. theatre shows, theatre festivals and workshops festival. Under this scheme, more than 108 plays have been staged. |  |  |  |  |  |
| (vii) |  | Young Talent Artists Scheme | To recognize & encourage young Talented artists in various folk Art forms |  |  | About 83 folk art forms would be selected & competitions would be held involving sufficient number of upcoming artistes & public. | To recognize and encourage young talented artists invariours art forms of the Zone, about various folk art forms will be selected and competitions will be organized involving sufficient number of incoming artists and public. For this purpose, an advertisement will be* |  |  | * got published in the newspaper and other cultural organizations and educational institutions will be also be contacted. |  |  |
| (viii) |  | Shilpgram | Established Shilpgrams are playing very significant role for the promotion & preservation of Art & Culture and providing platform to the talented artisans. The main objective is to boost its activities. |  |  | A large number of artistes & artisans are benefited. A large number of people are made aware of our rich cultural heritage. | Conducted 46 programme and regular craft exhibition cum sales. |  |  |  |  |  |
| (ix) |  | Festival of the North East – OCTAVE | The objective of the proposed festival of the North East is to help the people in general and artists from the North East in particular to have a closer interaction with main land. This will help in bridging the so-called gap between the NE and mainland. |  |  | Around 400 artistes from North East including folk artistes, musicians, craftsmen etc. will be performing in a series of programmes. | The North East Festivals ‘Octave’ have been held at Aurangabad, Hyderabad, and Bangalore. |  |  |  |  |  |
| 3. |  | Sangeet Natak Akademi, New Delhi | The Akademi acts at the national level for the promotion and growth of Indian music, dance and drama; for the maintenance of standards of training in the performing arts; for the revival, preservation, documentation and dissemination of materials relating to various forms of music, dance and drama and for the recognition of outstanding artists. | 7.10 | 11.50 | The Akademi devotes to the furtherance of the performing arts of India, and seeks to achieve this by arranging performances by renowned veterans as well as by talented artists of the younger generations through training programmes, award of scholarships and documentations. |  | 4.97 | 21.38 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Survey, Research, Documentation & Dissemination Publication and UNESCO – Convention on Intangible cultural Heritage – Implementation Project | Preservation and collection of recordings of rare traditions of Performing Arts, development of theoretical and academic knowledge of performing arts and publishing literature on performing arts. |  |  | 200 hrs of audio and video recordings, 10 audio CDs, 10 video CDs, 2200 photographs, 60 hrs of audio and video dubbing to be released. 3000 photographs to be added. Mapping project in 4 states. One national conference, Two regional seminars are proposed & 6 books, 4 journals and 12 news bulletins, and 1 Annual Report. 5 scholars for encyclopedia will be engaged. Survey for cultural mapping in 5 states,* | 28 hrs of audio and 342 hrs of video of recordings, 4945 photographs, 1 CDs released. 1 book, 3 journal |  |  | *making dossiers of 5 Elements, including 10 films on them, for Akademi’s candidature for Representative List. Organizing Indian presentation in ICH festival at UNSECO Headquarter in Paris. |  |  |
| (ii) |  | National Museum of Performing Arts Purchase of land and construction of building Archive of Performing arts & Library and Archive Specialized Library on Performing Arts | Development of Akademi exists museum musical instruments, puppets, masks and other art objects into a national level museum of performing arts by acquiring a separate building / campus. To develop an exclusive archive of audio video and photographic records of performing arts of Akademi including a parallel archive in South Akademi by acquiring rare collections scattered in the country, besides the existing rich collection of Akademi’s own archive. To expand Akademi’s existing specialized library on performing arts and digitalizing its entire holding and make it available on line. |  |  | Land from DDA expected for NMPA upgradation of available space in the Rabindra Bhawan for the display of puppets, masks and other artifacts. Digitization of existing archival holdings, setting up subject-wise archives in SNA Centres at Guwahati, Thiruvananthapuram etc. Digitization of 22000 clippings, 2200 monograph record, and 5500 photographs. | Allotment of 5 acres of land in Delhi by DDA for NMPA will be allotted during 2010-11. Training centres for instruments making started at Kolkata and Meerut. Center for acquisition of rare musical instruments has been setup at Kolkata for Eastern Region. So far we have acquired – musical instruments. Ongoing project for archival Digitalization of clippings and photographs completed. |  |  |  |  |  |
| (iii) |  | National Institutes and Centres of Akademi for Specialized fields/ forms of Akademi : Kathak Kendra, Akademi, Kutiyattam Centre, Kerala, Chhau Centre, Baripada / Jamshedpur, Other National Projects, Jawaharlal Nehru Manipur Dance Academy, Imphal and Sattriya Centre, Guwahati | To create Kathak dancers of professional standing through well specialized training course, To upgrade and develop Akademi’s project support to Kutiyattam, Upgradation and development of the ongoing project support to Chhau Dances of Eastern region, Development of training programmes in traditional land folk theatre forms of Akademi - Yakshagana of Karnataka, Bhagwat Mela of Tamilnadu, To create Manipuri dancers of professional standing through well specialized training course, Development of Akademi project support to Sattriya Dance and allied music and theatre traditions. |  |  | 3-4 new production of dance seminar on Kathak, The ongoing project of Kutiyattam involving a number of projects training, production, research and performance directly benefiting institutions 200 artistes and scholars. Ongoing project of Support to Chhau Dances involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. Setting up/ developing projects Centre for Music, Gwalior, Centre for Puppetry N. Delhi, Centre for Odissi Dance & Music Bhubaneswar and on Traditional Theatre Varanasi. Regular activity of training and performance was held 3-4 new productions of dance dramas in a year, 2 or 3 festivals, performance in different states, * | Done 3 new productions by Repertory. Imparting Kathak training to 316 students. It is ongoing programme. Promotion of ancient art form from ‘Kutiyattam’ with financial support to Gurukulams all over Kerala. Presently imparting training to 58 trainees. Also organized outreach programmes in different areas within and outside Kerala. Regular training activities held in Baripada, Rairangpur, Seraikella in Chhau Dances, music and mask making. Centre for Puppetry started in Delhi To be achieved: Traditional Puppet Festival of Karnataka in February 2011; Done – New production. Ongoing Training programme. Sattriya Centre started at Guwahati in August 2008. Training support to Sattriya Dance & Music continued |  |  | * Ongoing project on Sattriya Dance involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. Festivals of Sattriya Dance, Borgeet and Ankia Bhaona, seminar on different subjects. |  |  |
| (iv) |  | Festivals, Workshops and National Exhibitions 1SNA Festivals, Workshops & Exhibitions 2.Collaborative Programmes with State Akademis, Organizations, Central Govt. Organizations & Major Cultural Institutions and Sponsored Programme (New Scheme) 3. Regular Programme in Meghdoot Theatre Complex | To preserve, promote and development of performing arts traditions in live practice on regional and national levels and support exchange of ideas, concepts and techniques nationwide. |  |  | 16 festivals on Natya Parampara, series of brhaddesi, Nritya Lok, traditional theatre etc. in different cities. 25 programmes in collaboration with State Govt./Akademics and with central organizations in field of performing art. Fortnightly programmes of puppetry traditional theatre, film etc. | Promotion and Dissemination of music, dance and drama through these seminars and festivals will go a long way in strengthening country’s cultural tradition. |  |  |  |  |  |
| (v) |  | Awards, Honours and Prizes : SNA Fellowships and Awards (Akademi Ratna Sadasyata and Puraskar) Bismillah Khan Yuva Puraskar, Yuva Puraskar , | To recognize excellence and sustained contribution in performing arts and support eminent old artists. The Akademi awards fellowships and Akademi award (Fellowship is restricted 30 living person) Ustad Bismillah Khan Yuva Puraskar has been constituted for the young artists of below 35 years old. The award carries purse money of Rs. 25, 000 |  |  | 33 Akademi Awards and 5 Fellowships to be given. 33 Yuva Puraskar to young artists. | Presentation of annual fellowships and awards by Hon’ble President of Akademi alongwith a week long festival on music, dance and drama held in Oct.10. Puraskar distribution ceremony and festival of award wining artists held in Set. 10 |  |  |  |  |  |
| (vi) |  | # Cultural Exchange Programmes # 1 Inter – State Cultural Exchange Programme 2. Indo-Asian Cultural Exchange Programme (New Schemes) | National Integration through cultural exchanges |  |  | 20 exchanges involving 30 States/Uts Programmes involving cultural exchange with abroad. | 1 CEP involving two state/Uts held. Preliminary visit to Brazil for finalizing FOI. International Art festival organized in Delhi. |  |  |  |  |  |
| (vii) |  | # Training and Performs Support – Training and Preservation of Traditional, Folk & Tribal Performing Arts, # Promotion and assistance to Young Artists. Preservation of Puppetry, support to Children’s Theatre. |  |  |  | To hold 50 training programmes in different forms of performing arts. 5 festivals of young musicians/dancers in North, South, East and West & Central Zones. 4 festivals of young directors in different states, 2 theatre workshops, production subsidies.* | 20 ongoing Training programmes in Nagaswaram, Pallavi, Pakhawaj, Sundari, Dhrupad, Sopana Sangeetam, Shehnai, Sarangi, Mayur Veena, Naqqara, Porattunatakam, Nattuvangam, Firikkal dance, Prahlad Natak To be achieved Rang Pratibha in Feb 2011. Scheme could not started. |  |  | * Financial assistance to 30 institutions to be given for festivals and exhibition on puppets and also for various programmes. Financial assistance to 50 children theatre groups. |  |  |
| 4. |  | Lalit Kala Akademi | Promotion of visual and plastic arts | 6.15 | 7.00 | Normally, non plan grant is used for administrative and establishment expenses |  | 4.31 | 7.39 |  |  |  |
| (i) |  | Promotional activities in the field of visual & plastic art. Art Development/Art Promotion Cultural Exchange Proramme, Incoming Exhibition, National Exhibition of Art, Art Communication & | The main objectives of the Academy are to provide infrastructural facilities to the artist’s community for the development of art activities of the country especially in the field of contemporary art. |  |  | National Exhibition - 1 Exchange of Delegation Programmes under CEP-5 Outgoing Exhibition- 5 Incoming Exhibition - 4 Mobile Exhibition- 3 Camps and Workshops- 10 | Publication books-6, regional prog.-15, lecture-4, National art festival-1, National Art Conclave-1, |  |  | The Akademi proposed to built two Regional Centre one each in Kolkata and Shillong. |  |  |
|  |  | Dissemination, Archives & Slide Expenses, Lecture & Seminar, Camps & Workshops H.Q. Grants to SA & Arts Organization , HQ Art Gallery & AC Expenses, Outgoing Exhibition, Special Exhibition, Survey of Folk, Tribal & traditional Art, conservation & Restoration , Art Festival other than North East Programmes , XIX Commonwealth Games, Programmes & Infrastructural Facilities , 150th Anniversary of Rabindranath Tagore- programme, Fellowships & Scholarships Publication & Documentations Regional Centres North East Prog. Establishment of New Regional Centres Kolkata, Grahi. |  |  |  | Lectures& Seminars-9 Exhibition in LKA Gallery- 250 Grant-in-aid to art organizations-25 Conservation/ Restoration art works- 150 12th Triennial India-1 XIX Commonwealth Games Pro. & Infrastructural Facilities Exhibition of SAARC Countries -1 Catalogue-1 Book on “Krida”-1 150th Birth Anniversary of Rabindranath Tagore –Pro. Exhibition of Tagore’s works-1 Publication of Tagore’s Essays-1* | Mobile Exhibition-3, Seminar-1, Renovation outer ambiance Rabindra Bhavan : work in progress & completed within 2-3 months. |  |  | Negotiation with the respective State Govt. is at final stage. * Scholarships - 40 Fellowship - 1 Publication- 25 Regional Prog.-30 Lecture-45 National Art Festival -1 North East Exh. under Octave-1 Capital work-3 Proposed renovation & II phase of Garhi Studios, New Delhi & Regional Centre, Kolkata. |  |  |
| 5. |  | Sahitya Akademi | To undertake publishing & promoting Indian literature in 24 languages. | 6.30 | 10.50 | Normally, non plan grant is used for administrative and establishment expenses. |  | 4.41 | 9.94 |  |  |  |
| (i) |  | Upgradation of Libraries and Information Services | To provide readers/ intellectuals the complete range of books and update basic information about writers and literary activities in India at one place, make documentary films on eminent writers and scholars in the field of literature with modern archive unit of visuals. |  |  | Purchase of books in 24 languages will continue. The retro-conversion of bibliographic data in respect of different language sections is proposed. Upgradation of the Akademi’s English web site and the Hindi web site will be launched. Development of Archive Unit by adding modern equipments will continue. Ten Documentary films on writers will be made. Initial work of cataloguing of audio tapes of various* | Purchase of books in 24 languages including foreign publications continued. The retro-conversion of bibliographic data in different languages taken up in order to their priority. Efforts will be made to create more and more catalogues. The catalogues will be made available on Akademi’s Hindi and English websites. |  |  | *programmes/seminars is in the process. 10 documentary films on writers will be made. The work on revised version of Who’s Who of Indian Writer has already been started. |  |  |
| (ii) |  | ### Publication Schemes | The scheme to full fill the basic objective of the Akademi dissemination of Indian Literature and making available to multilingual societies of Indian Literary masterpieces from other language into their own language, histories of literature, monographs on Indian Writers, translation of important Indian and foreign classics, anthologies of poetry, short-stories, one-act plays, literary essays etc. |  |  | To publish around 400 books in all the 24 languages recognized by the Akademi. The publication of bi-monthly journals Samkaleen Bharatiya Sahitya (Hindi) and Indian Literature (English) and a half yearly journal Sanskrit Pratibha (Sanskrit) to continue. Publication of revised editions of Encyclopedia of Indian literature, new series of National Bibliography of Indian literature 1954-2000 to be completed. The other programmes under publication scheme will continue.* | A mew publication series named ‘Katha Bharati’ in collaboration with Central Institute of Indian languages has been launched. The second series of National Bibliography of Indian Literature (1954-2000) covering all books of literary merit and abiding values of Bengali, Dogri, Kannada, Maithil, Malayalam, Manipur, Nepali, Oriya, Rajasthani, Tamil and Telugu have already submitted their entries. |  |  | * The entries in the remaining languages are expected by the end of this financial year. It is proposed to take up the printing work in four phases. The authors/writers paid royalty on the basis of actual sale of books. |  |  |
| (iii) |  | Literary functions and programme Modernization and improvement of administrative functioning | To celebrate centenaries of great writers, hold regional, national and international seminars, writers camps, workshops, symposiums etc., provide writers a forum for their periodical gathering by organizing meet the author, men and books etc. |  |  | The Akademi will organize literary programmes in various fields. The programmes will include writers’ workshops, centenary celebrations, symposiums, Memorial meets, seminars etc.. Akademi would hold more than 400 programmes in the above categories throughout the country. | Akademi hold various Literary Forum Meetings, Men & Books, Asmita, Kavi Sandhi, Kavya Sandhya, Mulakat, Kath Sandhi, Celebration of centenaries of important writers, organizing of seminars at regional, national and international levels, writers camps and workshops at national and international levels organized* |  |  | *Computerization of the Akademi as a whole upgraded with latest technology, specifically in the areas of library services, database bibliography, cataloguing, indexing and accessioning. |  |  |
| (iv) |  | Awards to writers | To enable young and old writers in Indian language to visit other parts than their own, send Indian writers and host foreign writer delegation under Cultural Exchange Programmes, to give award to literary works which merit appreciation and encouragement in all 24 Indian languages recognized by the Akademi, give honorary fellowships to eminent writers in recognition of their contribution to Indian Literature. |  |  | Young writers will be given Travel Grant under the scheme of the Akademi to visit other parts of the country than their own. The Akademi will participate in different Cultural Exchange Programmes. The Annual Awards will be given to writers in 24 Indian languages recognized by the Akademi. The payment of Royalty and remunerations to authors/ copyright holders will be made. Grant under the scheme for writers in Residence will continue. The living fellows, eminent writers etc. will be offered financial aid under the scheme. | The scheme provides grant to 100 young writers to enable them to visit their counterparts in different parts of the country. The foreign writers/delegations will be hosted under Cultural Exchange Programme with whom India has bilateral relations. The Indian writers/delegation shall also visit the foreign countries on reciprocal basis. It is expected to host nearly ten writers’ delegation and around ten Indian writers delegation shall visit foreign countries. Akademi also will actively participate in various Indian Festivals, collaboration and Books Fairs at various countries. * |  |  | * The annual Sahitya Akademi awards in 24 Indian languages will continue. Akademi’s assistance to other literary institutions and the State Akademi shall be continued on the basis of Akademi’s programmes and activities. |  |  |
| (v) |  | Promotion of Akademi Publications\ Book Exhibitions | To advertise Akademi publications through literary journals, organize and participate in book exhibitions at regional, national and international level. |  |  | To achieve a sell target of Rs.3.00 cr., the Akademi will participate in various book exhibitions at National/ Regional / International levels. A part from this, it will also participate in provisional city/town book exhibitions. Also to organize book exhibitions during seminars/literary functions. | The Akademi has participated book exhibitions, book fairs/melas at district/city/town level. The book exhibitions are also the part of centenary celebrations/seminars/literary functions held by the Akademi. Akademi shall participated in around 90 books exhibitions at different levels.* |  |  | *Akademi also likely to take participate in the International Book Fair where India is a Guest of Honour Country. |  |  |
| (vi) |  | ##### Translation schemes, ##### Regional Literature Studies Projects, ##### Development of Languages, Fellowship: Coomara Swamy and Premchand, ##### National Bibliography of Translation in Indian Languages, ##### Encyclopedia of Indian Poetics, Great Books of India etc. | Translation is the basic activity of the Akademi. Translation centre “SABDANA” to make arrangements for training of translators and train the practicing translators by conducting workshops, to do the inter-lingual research and translation, prepare a register of translators and identify titles for translations and their publications into other Indian languages and into foreign languages. |  |  | The Translation Prizes in 24 languages recognized by the Akademi will continue. The work on the scheme” Katha Bharati” launched with Central Institute of Indian Languages (CIIL), Mysore will continue. More data will be provided to CIIL, Hyderabad for incorporation on their web site. . The Centers will conduct Translation Workshops in languages recognized by the Akademi as well as un-recognized languages .New Translation centers will be launched in Western and Northern regions. | The Translation Centre “SABDANA” is source of encouragement and training to the practicing translator to undertake inter-lingual research, translation of foreign classics into Indian. Bangalore Centre has already published quiet a few medieval texts in translation in English and South Indian Languages. The translation prizes to best translation in 24 languages shall continue. * |  |  | *It is estimated to translate and publish around 30 books. The translation of Children literature from one language to another shall also continue to make available the works of one language to the readers of another language. |  |  |
| 6. |  | Festival of India | To organize major cultural festivals in selected foreign countries for achieving better understanding and cooperation | 4.10 | -- | By holding art/museums exhibitions, literary seminars, theatre / performances / seminars / workshops. | Awareness about Indian cultural richness to other countries, creating opportunities to Indian artists to project their created cultural talents in these countries and also understanding of their countries’ cultural traditions. Shared histories for performances of Mondalin Maestro U. Srinivas and his team. | 1.15 | -- |  |  |  |
| 7. |  | Indira Gandhi National Centre for the Arts (IGNCA) | IGNCA was established to commemorate the memory of the Former Prime Minister Late Smt. Indira Gandhi. It is envisioned as a centre for research, academic pursuit and dissemination in the field of the arts. | -- | 25.00 |  |  | -- | 21.25 |  |  |  |
| (i) |  | Promotion of Multidisciplinary Research and Critical Dialogue among diverse Arts. | Enlarge its programme of research and publication of fundamental texts, reference works, glossaries, dictionaries, encyclopedia, comparative history of Indian arts, thesaurus of fundamental terms, inter-dialect and inter-disciplinary glossaries and dictionaries, explore relationships of arts and science, dimensions and explore relationship between arts of India and the world. Special focus on the North-East and its cultural dimensions. |  |  | Studies on the following dimensions: (a) Multiple levels of Identity and their manifestation in Arts (b) Language and Cultural Diversity (c) Wisdom Tradition, Ecology, Resource Management and Sustainable Development (d) Religious Identities, Confluence of Traditions and Composite Cultures (e)Inter-cultural Dialogue (f)Contribution of Women to Indian Art and Culture | (a) Research and Field studies (b) Audio-video documentation (c) Conference, seminars and workshops (d) Exhibition and multi-media events (e) Production of films, CDs, audio-video recordings |  |  |  |  |  |
| (ii) |  | Resource augmentation and modernization | Augment the repository of primary source material - written, oral, auditory, audio-visual and pictorial of the IGNCA, to serve as the national centre for the arts and culture and support research and publication activities of its other in-house divisions, Upgrade and install modern management and technological tools and systems, Enhance reproduction of source materials in different me, Upgrade technology and set-up permanent galleries for display and exhibition. |  |  | # (a) Purchase of # (i) Books (ii) Journals (iii) Rare books (iv) Personal collections (b) Collection of slides through in-house digital photography. and Purchase of slides (c) Microfilming of Manuscripts (d) Acquisition of Cultural archival material (e) Modernization of (i) Digital Library Information System (ii) Annonated Bibliography Index (iii) Reprographic unit (iv) Audio-visual equipments (f) Cultural Informatics (g) Creation of Galleries | (i) Addition of books, periodicals, journals in the Library (ii) Modernization of the Library services State-of-art equipments in Reprography, Computer centre and media production (iii) Digitization of manuscripts, internal repository etc. (iv) Collection of archival material from the North-East (v) Creation of Galleries |  |  |  |  |  |
| (iii) |  | Cultural Cartography & Modernization of equipments in IGNCA | Map ecological and cultural profile of diverse communities of India along with specific aspects of art and crafts traditions prevalent among them. |  |  | (i) Creation of a cell (ii) Research and field study (iii) Preparation of Atlas Procure photocopiers, fax machines, tables, almirahs, establish workstations, and provide Information Technology tools and equipments. | Installation of modern equipments Enhancement of work output and better working conditions |  |  | Ongoing programme and will be completed before 31st March, 2011 |  |  |
| 8. |  | National School of Drama, New Delhi | Promote Theatre and to conduct theatre training programme | 6.80 | 13.00 | Normally non- plan grant is used for administrative and establishment expenses. |  | 6.80 | 23.40 |  |  |  |
| (i) |  | Theatre workshop and part time courses in regions and locally and other training courses for faculty and staff. | To benefit a vast majority of theatre enthusiasts in various states with diverse languages and cultural backgrounds and to create theatre awareness in them. |  |  | Intensive Theatre Workshop- 2, Collaborative Theatre Workshop- 40, Assistance to Theatre Workshop- 10, Part Time Course- 2, Refresher Course- 2, Short term Workshop- 8, Intensive Theatre Workshop- 12, * | 40 theatre workshops were conducted and 20 are scheduled in the Jan.-March,11 quarter in different parts of the country. The target for 2010-11 will be achieved by March 11. |  |  | * Acting Theatre Workshop-2 Technical Theatre Workshop- 2, Theatre Music Workshop- 2, Theatre Design Workshop-2 |  |  |
| (ii) |  | Organizing of training courses/ Children Theatre Workshops in Delhi and outside Delhi | To develop personality and give exposure to children in terms of their expressions and confidence. |  |  | Children theatre Workshops in Delhi/ Outside Delhi- 42, Production Oriented Children Theatre workshop- 36 , Theatre workshop with SC/ST Children-2, Short Term Theatre Workshop- 4 | 15 workshops in Delhi and Outside Delhi were held and rest of the workshops are scheduled in Jan. – March 11 quarter. |  |  |  |  |  |
| (iii) |  | Organizing of collaborative programme of traditional group in villages and theatre festival/ exhibition. | Providing 3-year Advanced Dramatic Training Course and to acquaint the students from theatre from existing in different regions of the country. |  |  | 2nd Year Students production – 4, 3rd Year students production – 4, Final year production – 5, 1st year & 2nd year students scene work Summer intensive workshop- 1, Winter workshop -1, Display Exhibition-8 & Theatre Performances-64 | Programmes with traditional groups, students, fellow productions, summer festival, Display exhibitions were held. winter festival is scheduled for Feb.11. 4 overseas productions were held. few productions and exhibitions are to be held in Jan.-Feb.11. |  |  |  |  |  |
| (iv) |  | Promotion of Folk, Tribal Arts and Educational Tours | To familiarize the students with the existing folk and tribal art relating to theatrical and music forms. |  |  | Workshop with Traditional Group-1 & Educational tour for 1st 2nd 3rd years students-5 | 2 productions oriented workshops were conducted with the design students and with the students of 2nd year. 3 educational tours for the students were also organized. |  |  |  |  |  |
| (v) |  | Formation of Repertory Company of Adults performing for children | Aim to promote theatrical performances for children. |  |  | Production of new/old plays for children-2, Summer Theatre workshop-2, Children workshop- 2, Sunday Club workshop performances-2, Workshop & Play in schools-40, Teacher’s workshop - 2 Other Festival Exhibition- 1 | Summer theatre workshops -12 for children were organized at centres in Delhi and centres in Guwahati. 1 summer workshop alongwith summer theatre club was organized in Guwahati for the benefit of children & theatre teachers. * |  |  | * Performances of plays in school. Festival Jashne Bachpan was held. performance of new plays 2, shows I auditoriums-40 |  |  |
| (vi) |  | Extension of Repertory Company National Theatre Festival & Parallel theatre Festival National children Theatre Festival and Bal Sangam/ Jashne-achpan | Dissemination of Indian plays in India and Outside the country. |  |  | Performances of play in Delhi-100, Outside Delhi-50, Shows of new productions-24, shows in summer festival-1, Shows in winter festival-1, Participation in BRM collaborative performance with groups- 25 | Performances in Delhi & Outside Delhi-48, Summer Festival collaborative prog.-7 with groups, action initiated for development of Hindi mobile theatre shows of new productions were held 3. Festival scheduled to be organized in Jan.11. Festival was held successfully Oct.10 |  |  |  |  |  |
| ### 9. |  | ### National Gallery of Modern Art (NGMA) | ### To create an understanding and sensitivity among the Indian public towards visual and plastic arts in general and to promote the development of contemporary art in particular. | ### 3.85 | ### 7.00 | Normally non- plan grant is used for administrative and establishment expenses. |  | ### 2.86 | ### 8.33 |  |  |  |
| (i) |  | Upgradation, Modernization and maintenance of museum | To promote development of contemporary art at par with international level. |  |  | ### Maintenance of a well organized museum of Modern Art with excellent display of art objects at par with International Standards at New Delhi, Mumbai and Bangaluru. 15 special exhibitions, to organize atleast 500 films on art to be screened in the auditorium. 180 conducted tours to be organized. Art Sketch Club is held every Sunday at the museum premises. Summer Art workshop to be organized. 5 seminars on Art practices conducted by eminent artists,. 10 Catalogues and 15 posters of Special exhibitions to be released. Museum shop at NGMA, Mumbai and Bangalore and Delhi will be well stoked..* | 8 special exhibitions were displayed at Delhi, Mumbai & Bangaluru on Indian contemporary artists and foreign artists under CEP. 570 film shows on art held, 210 tours of school groups conducted, 11 lectures on art and art practices by eminent artists were organized at NGMA Bangaluru. Different types of souvenir mugs, carry bags, fridge magnets, 10 ypes of greeting cards, 4 portfolio of eminent artists, 2 catalogues, 6 types of reproduction of art works were produced for sale . Collection of 20000 reference books on art is being maintained for the benefit of students. |  |  | * Modernization of Art Reference Library, documentation and digitization of art collections to be undertaken. Conservation and Restoration of Art works and cleaning and conditioning of reserve collection are to be undertaken during the year. ### About 100000 of art lovers are expected visit the museums. |  |  |
| 10. |  | Asiatic Society Kolkata | Declared as an institution of national importance. To launch research projects on language, literature, culture and socio-economical aspects | 7.70 | 8.00 | ### Normally, non plan grant is used for administrative and establishment expenses. |  | 5.75 | 2.40 |  |  |  |
| (i) |  | Development of Library System | To establish build, maintain institutions for promotion of research in humanities and sciences |  |  | Acquire books, journal etc. its preservation and maintenance to cater readers with books and references. Book Acquisition-2500 vol. Subscription to serials-300 titles* | The targets fixed for various activities have been continuing upto Dec. 10 3820 male and 4060 female readers were served by providing library facilities. |  |  | *Cataloguing and documentation of - 4000 Books and 6000 journals Binding/Mending- 2600 books & Journals to be undertaken |  |  |
| (ii) |  | Development of Museum & User facility | To preserve manuscripts which has a rich collection of archival records, coins inscriptions and very valuable lithographs. |  |  | Cataloguing of MSS -4000 books & journals, Documentation of MSS, archival Material etc.– 6000 books and journals. | 118 Indian and 72 foreign visitors/research scholars visited in the library. |  |  |  |  |  |
| (iii) |  | Conservation & Preservation of rare books, MSS & Other document | To take effective measure for the preservation of brittle and fragile manuscripts, rare books and other ancient objects kept in the Museum and Library of Society. |  |  | Restoration of 30000 sheets of Manuscript in forms of film, plate etc., 2500 Lithographic prints/sheets to be restored. | Preservation of rare-books, MSS, paintings was taken up and documentation of rare books/MSS carried out. |  |  |  |  |  |
| (iv) |  | Publication Programme | To bring out the publication of high academic standard for which the society is known to the world of scholars. Particular emphasis is made on the publication of books under the Bibliotheca Indica series. |  |  | Publication of 15 Books, 4 Journals, 10 M. bulletins & 4 Booklets to be brought out during the year. | Publication of 8 books , 3 journals and 7 monthly bulletins were taken up. |  |  |  |  |  |
| (v) |  | Augmentation of Research | Research work in different areas, imparting training, conduction seminars, lectures, workshops etc. |  |  | Research in work in different areas, imparting training and conducting seminars and workshops – 50 project, 15 seminars, 35 lectures 5 exhibitions/workshops | 36 projects on various subjects were taken up. 11 seminars, and 4 lectures were conducted upto Dec., 10. |  |  | Continuous Process |  |  |
| 11. |  | Centre for Cultural Resources and Training, New Delhi | Aims to improve the quality of life through the medium of Academies working in the field of linking education with culture. | 3.13 | 10.00 | Normally, non plan grant is used for administrative and establishment expenses. |  | 2.18 | 11.99 |  |  |  |
| (i) |  | Propagation of Culture among school students | To conduct a variety of in-service Teacher Training Programmes such as Orientation Training Programmes, workshops, Seminars, Refresher course etc. in different parts of the country for school teachers, teacher educators etc.organisation of educational activities for school students and children belonging to governmental and non-governmental organizations. Workshops for children of resettlement and basti colonies and for physically challenged students. |  |  | 4000 Teachers/ Teacher Educators to be trained in various training Programmes. 4000 Teachers to be trained through Trainers. 30000 Students to be trained under Community and Extension Programmes. 200 Cultural Clubs to be setup in various states in the country.* | 2651 Teachers/Teacher Educators have been trained in various Training Programmes. 1175 Teachers trained through Trainers. 25309 Students have been trained. 179 Cultural Clubs have been setup in various states in the country. 40 Lectures on Indian Art and Culture to be organized. 18 Publications including reprints have been published. 623 Educational kits produced. |  |  | *40 Lectures on Indian Art and Culture to be organized. 20 Publications including reprints to be published. 1000 Educational Kits to be produced. |  |  |
| (ii) |  | Cultural Talent Search Scholarship Scheme (CTSS) | Aims at providing facilities by awarding scholarship to study the performing and other arts to outstanding young children in the age group of 10-14 years. |  |  | 500 Scholarships to be awarded under Cultural Talent Search Scholarships Scheme 4 Cultural festival to be organized for scholarship holders. | 473 Scholarships have been awarded covering all parts of country including the north-east. 3 Cultural festival have been organized for scholarship holders. |  |  | the awardees are selected on the recommendations of Central Selection Committee and Regional Selection Committees. |  |  |
| 12. |  | Financial Assistance for Professional Groups and Individuals for specified performing art projects. (Dance, Drama and Theatre Ensembles) | To promote the Guru Sishya Parampara and support organizations / individuals working in the field of Performing Arts. | 1.55 | 25.00 | There are no fixed targets individuals/organizations involved in Cultural activities and are assisted on the basis of receipt of proposals and recommendations of the Expert Committee. | 480 individuals /organizations have been assisted. | 0.13 | 16.62 | Includes 30% provision towards pro-women, and 20% provision for ST population |  |  |
| 13. |  | Gandhi Peace Prize | Government of India announced institution of an annual international Gandhi Peace Prize for social, economic and political transformation through non-violence and other Gandhian methods as a part of celebration of 125th birth anniversary of Mahatma Gandhi. | 1.55 | -- | The recipient of this prize is selected by the Jury headed by Hon’ble Prime Minister in accordance with the prescribed code of procedure. | The nomination for GPP are on the final stage of it declaration. (No GPP is given for the last 3 years. Synopsis on each nominee are prepared and compiled in a booklet, which is then put up to the Jury for selection of an awardee.) | 0.00 | -- |  |  |  |
| 14. |  | National Culture Fund (NCF) | NCF objective is to develop Public Private Partnerships for the protection, conservation and development of heritage. | -- | 0.01 | Various proposals have been received for seeking financial assistance through different organizations/individuals including BharatBala Productions Pvt. Ltd., OSIAN’s Art Society, M/s. Darpana, Prasiddha Foundation, ONGC, INTACH etc. for holding various festivals celebration, film productions and many others categories of events under Tangible and Intangible Cultural Heritage. | New Projects signed - Ahom Monuments, Sibsagar Assam for Renovation and development on 29.06.2010 - National Museum, New Delhi and NSC, Delhi for Replacement of plastic case around the chariot at the entrance of National Museum, New Delhi with reinforced glass covering on 29.06.2010 - SBI, Kolkata in respect of Hazardurai Place, District Mushirabad for Conservation, Environmental Development , Providing amenities for tourist, Illumination of the monument and Providing professional advice for museum display for Hazardurai Palace on 13.07.2010 - Production of a film on Kishori Amonkar, Classical Singer by Shri Amol Palekar on 21.09.2010. - For Film on Smt. Mrinalini Sarabhai, classical dancer. MoU signed between NCF and M/s DARPANA, Ahmedabad.* | -- | 0.00 | Projects sponsored by PPP Fund Rs. 10.00 Rs. crore Corpus Fund of NCF is Rs. 19.50 crore. Interest is placed in Secondary Corpus Interest earned from Secondary Corpus used for Admin and Establishment * 6. MoU signed between NCF and M/s India Photo Archive Foundation, New Delhi on 25.10.2010. |  |  |
| 15. |  | Centenaries/ Anniversaries Celebration | To celebrate the Centenary/Anniversary of important personalities and events |  |  |  |  |  |  |  |  |  |
| 15.1 |  | Celebration of 2550th Anniversary of Mahaparinirvana of Lord Buddha | To highlight salient aspects of the life and times of Lord Buddha and to acquaint the people particularly the young generation with the great soul, who successfully diverted the attention of masses towards Ahimsa for the betterment of human. | 0.45 | -- | Programmes organized in the memory of Lord Buddha and funds were provided to the projects associated with Lord Buddha for strengthening the infrastructure to propagate the teachings of Lord Buddha. | The funds were released for the programmes approved by NIC. | 0.45 | -- |  |  |  |
| 15.2 |  | Celebration of Birth Centenary of Lal Bahadur Shastri | In order to create a Chair in the Institute of Defence Studies and Analysis, N.Delhi in the name of Shri Lal Bahadur Shastri. | 0.05 | 2.00 | Opening of two new technical institutes for men & women separately will be taken up during the period. | An amount of Rs.2.00 cr. has been released for the said purpose. | 0.00 | 2.00 |  |  |  |
| 15.3 |  | Celebration of 150th anniversary of 1st war of independence, 1857. | Undertaking the residual work as approved by the NIC. | 1.00 | 10.00 | The programmes as approved by NIC for establishment of Chair are to be undertaken. | Funds released for the establishment of five commemorative Chairs to the respective Universities as a part of commemoration approved by NIC | 0.42 | 9.00 | Completion of the projects depends upon the availability of funds. |  |  |
| 15.4 |  | Financial support to Khalsa Heritage Project | To highlight salient aspects of the important events relating to Khalsa Heritage in order to infuse in the public, particularly the young, the spirit of these great events. | -- | 8.00 | Funds for Khalsa Heritage Project are released to Punjab Govt. as 1/3rd share of Central Govt. (Plan) as reimbursement of the amount spent on the project on quarterly basis. | The matching grant is given to the Govt. of Punjab as a share of Central Govt. | -- | 2.43 |  |  |  |
| 15.5 |  | Ter-Centenary of Guru-ta-Gaddi | Aims to provide infrastructural development of Anandpur Sahib and Talwandi Sabo as a part of Ter Centenary Celebration of Guru-ta-Gaddi of Shri Guru Granth Sahib. | 0.01 | -- | This grant is being given to Govt. of Punjab for the infrastructural development of Anandpur Sahib and Talwandi Sabo. Various projects have been undertaken at Nanded. | Infrastructural development of Anandpur Sahib and Talwandi Sabo as a part of commemoration. | 50.04 | -- | Rs.83.20 cr. as a ‘cash outgo’ was approved in the 1st Supplementary 2010 |  |  |
| 16. |  | Other Schemes/Institutions |  |  |  |  |  |  |  |  |  |  |
| (a) |  | Central Institute of Higher Tibetan Studies, Sarnath | Established with a view to educating the youth of Tibet and Himalayan border areas of India | 6.90 | 5.80 | Normally non plan grant is used for administrative and establishment expenses |  | 4.83 | 4.06 |  |  |  |
| (i) |  | Development of Library | ## 1. To Preserve Tibetan culture and tradition. ## 2. To restore ancient Indian sciences and literature preserved in the Tibetan languages. |  |  | Purchase of 1500 books, and computer/ equipments will be purchased. | Purchased 1000 books and computer equipments etc. |  |  |  |  |  |
| (ii) |  | Publication and Printing. | To provide printed material on Tibetan culture for scholars and others |  |  | 12 books to be published. | 9 books published upto Dec.,10. |  |  |  |  |  |
| (iii) |  | Rare Buddhist Text Research, Establishment of Language & Laboratory, Promotion of Intellectual contact, exchange of scholar conferences and seminars | To offer the alternative educational facilities to the students of Indian border area who formerly availed the opportunity of receiving higher education in Tibet |  |  | 1st and 2nd Bi-annual journal to be published and 2 sites to be visited for research purposes. Various other programmes will be carried out for promotion of Buddhist/Tibetan languages and culture. | One bi-annual journal was published and one site was visited, 4 books under process for translation and restoration, 1 national seminar was organized. |  |  | Re-editing work of MBSST Darbhanga Institute under process. |  |  |
| (b) |  | Central Institute of Buddhist Studies, Leh | To develop multifaceted personality of the students through inculcation of the wisdom of Buddhist literature as well as to familiarize them with modern subjects to acquaint them with collection,conservation, translation, publication of rare manuscripts and research works relevant to Buddhist Studies etc. | 4.20 | 8.50 |  |  | 2.94 | 5.95 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Construction of Building | Construction of auditorium, Guest House, 20 Residential Quarters and Building for DPS, Zanskar. |  |  | Construction of physical infrastructure for CIBS and DPS Zanskar. | Construction of physical infrastructure for CIBS and DPS Zanskar is under progress. |  |  | Construction is going through CPWD and State PWD in a phased manner |  |  |
| (ii) |  | Provision for existing Gonpa/ Nunnery school. Publication of rare books/manuscripts, preservation of traditional Ladakhi arts and culture. Compilation of Encyclopedia of Himalayan Buddhist Culture. | To support educational activities in the number of Gonpas by providing teachers and stipend to the students. |  |  | Plan activities for 50 feeder schools in different monasteries of Ladakh and a branch at Zanskar Kargil to preserve and promote monastic system of education. These works will be undertaken during the year. | Plan activities for these feeder schools have been continuing. Conferment of Deemed to be University status to CIBS. Provided fellowships for research scholars. Acquisition of books, preservation of Ladakhi arts and culture, organization of refresher courses etc. are being undertaken. |  |  | 9 years graded courses of Acharya, Shastri and Madhyama will be continued and extendable by one year for Ph.D. |  |  |
| (c) |  | Gandhi Smriti and Darshan Samiti | To propagate the life, mission and thoughts of Mahatma Gandhi by organizing various socio – educational and cultural programmes. | 4.20 | 10.00 | Normally, non plan grant is used for administrative and establishment expenses. |  | 2.77 | 7.11 |  |  |  |
|  |  | Promotional Activities 1. Regular programme with educational institutions a) Taking Gandhi to Schools b)Gandhi Summer School 2.Programmes for youth 3.Programmes for Women 4.Commemorative programmes 5.Regular Programmes in GSDS | To plan and carry on activities for the promotion of Mahatma Gandhi’s ideals and of national causes identified by him. |  |  | a)Children programms with educational institutions to reach out more than 20,000 students in India and abroad. b)Gandhi Summer School in Delhi and other states as well as for disadvantaged children. Youth to reach out more than 10000 youths. Programmes for women to cover about 5000 women. Programme for awareness to reach out 10000 people. About 2000 underprivileged children to be trained. | Various programmes for students/youth and women have been organized in different state of country for constructive works and taking forward the message of Mahatma Gandhi including empowerment of women and fight against violence on women. |  |  |  |  |  |
|  |  | Dissemination, Infrastructure, Programmes in NE | To undertake such activities as will lead to greater understanding of Mahatma Gandhi’s life, work and thoughts. |  |  | The following publication will be brought out – 1.Annual Report 2.The Yamuna, GSDS Children’s newspaper 3. Anasakti Darshan New books, equipments to be procured to strengthen Smiti infrastructure. | Through these publications the message of Mahatma Gandhi and other social issues were takenup reaching nearly 20,000 children/youth and other cross section of the society both directly and indirectly. |  |  |  |  |  |
| (d) |  | Nava Nalanda Mahavihara, Nalanda, Bihar | To revive past glories of the ancient university of Nalanda and to give post graduate studies and research in Pali language and literature and Buddhology. | 1.58 | 3.20 | Normally, non plan grant is used for administrative and establishment expenses. |  | 1.18 | 1.65 |  |  |  |
| (i) |  | Improvement & Development of Library Service | Developing the library with purchase of new books on Pali, Buddhism Philosophy, Ancient History, Culture and Architect, Hindi, English, Sanskrit etc. |  |  | Over 1000 of books are expected to be purchased on Pali, Buddhist Philosophy, Ancient History etc. | To provide better facilities for the research scholars in the various cultural fields. |  |  |  |  |  |
| (ii) |  | Development of Xuan Zang Memorial Hall | To provide creative works, as paintings, murals inside and outside the XZM and on landscaping etc. |  |  | Regular maintenance and development works to be taken up besides there is a proposal to construct a separate building for housing and preserving Xuan Zang relics. | To spread awareness of Xuan Zang. |  |  |  |  |  |
| (iii) |  | Cultural Exchange programme, workshops seminars & conferences | Promotion and dissemination of Buddhist thoughts by organizing seminars, workshop etc. on inter-institution exchange basis. |  |  | Academic and cultural material collected from workshops, seminars etc. is printed and is made available to scholars and researchers. | To promote cultural contacts by organizing workshops, seminars etc. |  |  | Proceedings of Living Buddhism in North East India will also come in 2010-11. |  |  |
| (iv) |  | (i) Annual foundation day & ceremony & special convocation (ii) Award of scholarship to the meritorious students of Mahavihara | To commemorate the foundation day of the NNM on the 20th Nov. each year and special convocation. To support the meritorious students |  |  | This is a regular feature of the Mahavihara to commemorate the foundation day. Indian and foreign students are to be benefited. | To revive past glories of the ancient university of Nalanda. To promote Pali language and Buddhology literature |  |  |  |  |  |
| (v) |  | Printing of old and new publication and documentation exhibition | Main objective is to print and reprint of the proceedings of the earlier seminars and other research oriented materials and to promote & dissemination of Lord Buddha’s teachings by holding exhibition & its documentation |  |  | Printing of Annual & Audit Repot, proceeding of the seminar & re-print of old books will be taken up. A exhibition on the theme of Nalanda & Buddhism will be exhibited. | Providing a good research material in Pali language and also Buddhology literature. |  |  |  |  |  |
| (vi) |  | Pali Hindi Dictionary Project | Scheme aims at preparing an exclusive Pali-Hindi Dictionary |  |  | Vol.II of Pali Hindi Dictionary is expected to come out in 2010-11. | It aims to assist the visiting scholars in understanding Pali language. |  |  |  |  |  |
| (e) |  | Maulana Abul Kalam Azad Institute of Asian Studies, Kolkata | To conduct research and training of life and works of Maulana Abul Kalam Azad with the study of social culture, political and economic movement in Asia from the middle of the 19th century. | 1.05 | 6.50 |  |  | 0.79 | 4.50 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Research project including North East/ fellowship and other promotional activities. | To carryout research activities and revelation of political, social & economic changes in India and other Asian countries. |  |  | 20 whole time resident fellow will undertake Research on various areas including North-East 30 project fellow will work for research projects based on the visits seminars etc. the institute will assist other bodies to organized seminars, a documentation centre from the Heritage building will be operated. | Produced about 10 books and 1 journal. National and international seminars and 1 Maulana Azad lecture and staging of the Urdu play “Maulana Azad “ by Peirrot’s Troupe in RTC, ICCR were held in collaboration with other institutes. |  |  | A weekly seminar programme continued through out the year. It provided financial aid to international and national institutions for organizing seminar. |  |  |
| (ii) |  | Publications \Acquisitions of Book | To publish the research work of the scholars in different subject fields. |  |  | Publication of 10 Books & one journal will be undertaken. | Publication of 3 books. 1 journal’s publication is under process. Publication of research MSS submitted by external project fellows were undertaken. |  |  |  |  |  |
| (iii) |  | Maulana Azad Museum | The Museum has made an impact on the people of Kolkata. Contributions of Maulana Azad to the Indian Independence movement along with a collection of memorabilia are on display for the visitors. |  |  | Strengthening and development of Museum by adding memorabilia, LCD TV, visual and archival materials on Maulana Azad and rare books concerned with life and time of Maulana Azad. | The museum maintained to make it in good order. Accessioning of rare books is under way. |  |  |  |  |  |
| (f) |  | Kalakshetra Foundation, Chennai | A Cultural institution of International repute established for preservation of traditional values in Indian Art especially in the field of dance and museum. | 4.10 | 3.00 |  |  | 2.87 | 2.86 |  |  |  |
| (i) |  | Theatre Upgradation and Museum | To provide an upgraded audio and lighting equipment at par with the international standard for Indian/ International audience. |  |  | Theatre upgradton and theatre sound equipment to be completed in Feb. 2011. and work on sound proofing will be taken up. | The civil works, sound equipment, theatre equipment, HVAC works are in progress. |  |  |  |  |  |
| (ii) |  | Festival and Craft Bazar. 58th Annual Art Festival, Kathakali Festival and crart Bazar. | To preserve, promote and development of performing art traditions in Bharatanatyam, Carmautic Music Kathakali. |  |  | 58th Annual Art Festival, which includes Smt. Rukmini Devi’s Dance- Dramas performance by the repertory company and 4 day Kathakali Festival are to organize. | In Dec. 2010, organized a Craft Bazaar in collaboration with Datakaari Haat Samiti, New Delhi,. Smt. Rukmini Devi’s Dance- Dramas performance by the repertory company was organized and also 4- days Kathakali Festival organized. |  |  |  |  |  |
| (iii) |  | Documentation of Dance Dramas. | To documentation of dance dramas on the theme of Krishna to be documented for Archival purposes. |  |  | Remaining 3 pats of Ramanayan series is being brought out. | Remaining 3 pats of Ramanayan series are being brought out by Feb.2011. |  |  |  |  |  |
| (iv) |  | Research & Documentation | To proceed further in furtherance of the activities in traditional Art form and also to train young generation to keep abreast of the development in this field. |  |  | As a part research work on Smt. Rukmini Devi’s dance drama and other contemporary music/dance art forms, collection of rare and precious books from various sources will be collected, training session including field trips of students. | The work is continuing. |  |  |  |  |  |
| (g) |  | Namgyal Research Institute of Tibetology, Sikkim | The Institute is an autonomous organization under the state govt. of Sikkim and gets regular grant- in- aid from this Ministry. The main objective of this institute is to spread the knowledge of Chhos(Doctrine of Buddha). | 0.42 | -- | The Institute has ongoing programmes of translating and publishing the seminal texts preserved in its archives. | The institutes continued its ongoing programmes during the period under review. | 0.32 | -- |  |  |  |
| (h) |  | a) Fellowship to outstanding artists in the field of performing, literary and visual arts. | ## This scheme provides financial support to outstanding artists in the fields of music, dance, theatre, visual art, literature and traditional art forms of folk and indigenous art. | 1.35 | 7.00 | 125 junior and 125 senior fellowships to be awarded. | 125 senior and 125 junior fellowships has been awarded. | 0.70 | 2.92 |  |  |  |
|  |  | b)Scholarship to young workers | This scheme seeks to give financial assistance to young artists of outstanding promise for advanced training within India. | 0.78 | -- | 400 scholarships to be awarded. | 354 scholarships has been awarded. | 0.00 | -- |  |  |  |
| (i) |  | - Financial Assistance to distinguished art persons - Setting up a National Welfare Artist’s Fund | To provide financial assistance to artists whose contribution in the field of art has been of great significance and who have attained an age of 58 years and above and are in indigent circumstances. | 2.20 -- | 4.50 5.00 | About 2600 old artists to be provided assistance under this pension scheme. Financial assistance will be given to renowned artists for their medical/health and other purposes. | Old artistes provided assistance under the scheme through LIC. Progress being as ascertained from LIC. This scheme is still to be implemented. | 2.00 -- | 9.49 0.00 |  |  |  |
| (j) |  | Delegation under Cultural Exchange Programme | Promotion of Cultural relations with other countries of the world on the reciprocal basis. | 0.80 | -- | The main purpose of this fund is to host cultural visits by foreign dignitaries organize meetings/ conferences under the cultural agreements. During the year 2010-11, new CEPs will be signed/executed under the Cultural Agreement with various countries. | Visit of Polish delegation for discussions. Visit of Indonesian delegation for discussion on CEP. | 0.04 | -- |  |  |  |
| (k) |  | Financial Assistance for Tribal/Folk Art | ## To promote and disseminate tribal art and culture. The scheme aims at creating awareness of richness of tribal /folk art through documentation and organizing cultural activities including festivals. | -- | 0.25 | There are no fixed targets individuals/organizations involved in Cultural activities and are assisted on the basis of receipt of proposals and recommendations of the Expert Committee. | The scheme was discontinued in 2008-09. However, in ongoing cases, 7 individuals/ organizations have been assisted. | -- | 0.01 | Advertisements have to be released in time so that meeting of Expert Committee are held in order to release funds in right sequencing. |  |  |
| (l) |  | Financial Assistance for the Preservation & Development of Cultural Heritage of the Himalayas | To promote, project and preserve the cultural heritage of Himalayas. | -- | 0.75 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 6 NGOs / individuals were given grant-in-aid upto Dec.10 under this scheme. | -- | 0.23 | The number of proposals to be approved by the Expert Committee will depend upon the quality of the project and capability of the organization |  |  |
| (m) |  | Financial Assistance for the Preservation and Development of Buddhist/ Tibetan Organizations | To promote and propagate the scientific development of Buddhist/ Tibetan culture and tradition and also research in the relative fields. | -- | 3.50 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 26 NGOs / monasteries were given financial assistance upto Dec.10 under this scheme. (The number of proposals to be approved by the Expert Committee will depend upon the quality of the project and capability of the organization) | -- | 1.61 | . |  |  |
| (n) |  | Scheme of Centenaries & Celebrations |  | 1.80 | -- | Financial assistance to be given to eligible applicants/NGOs for celebration of Centenary/ Anniversary | 8 NGOs/ Organization were sanctioned grant-in-aid. | 0.70 | -- |  |  |  |
|  |  | - 150th Birth Celebration of Guru Rabindranath Tagore - 150th Birth Celebration of Swami Vivekananada | To provide financial assistance to cultural organizations/NGOs for celebration of centenaries of renowned personalities of India. To disseminate art and culture including literary and religious contributions made by them among the masses. |  | (22.00) (8.00) | The programmes as approved by NIC for Chitravali, NFDC, TCGS online electronics variorum of Tagore works, Marg publication etc.. All the proposals approved by the National Implementation Committee (NIC) will be taken up for their implementation. | Funds released for Chitravali, NFDC, TCGS online electronics variorum of Tagore works, Marg publication projects etc. NIC approved 2 proposals on 03.09.2010. first installment of funds released. |  | 6.12 12.40 |  |  |  |
| (o) |  | Maintenance of National Memorials | To commemorate the role of eminent National Personalities who have contributed to and played a historic role in the history of the country. |  |  | Financial assistance is given to the voluntary organizations for maintenance of National Memorials | 2 NGOs were given assistance for development and maintenance of National Memorials. |  |  |  |  |  |
|  |  | Development of Sardar Vallabh Bhai Patel Memorials & Development & upkeep of Dr. Rajendra Prasad Memorial. |  | 1.70 | 15.00 | Grant to be released to the Trust for undertaking developmental works on Sardar Vallabh Bhai Patel Memorials. For upkeep of Dr. Rajendra Prasad Memorial, grant will be released to the Trust. | Grant of Rs.10.00 cr. has been released to the Trust for undertaking the said works. Still to be implemented. | 0.00 | 10.00 |  |  |  |
| (p) |  | Building Grants to Cultural Organizations | To give grants to voluntary cultural organizations working in the field of dance, music, fine arts, indology and literature for construction of building and purchase of material. | -- | 5.00 | There are no fixed targets individuals/organizations involved in Cultural activities and are assisted on the basis of receipt of proposals and recommendations of the Expert Committee. | 27 organization have been assisted. | -- | 0.82 | The scheme has been modified and reintroduced as the scheme of Building Grants, including Studio Theatres w.e.f. 07.01.11 |  |  |
| (q) |  | Financial assistance to Cultural Organizations with a national presence | To provide assistance Institutions/Organizations engaged in cultural activity at the National level. | 3.00 | 5.00 | The grant will be given to the prominent institutions like R.K. Mission. INTACH and SPICMACAY etc. | R.K. Mission was given grants for Plan and Non-Plan activities & INTACH, SPIC MACAY were given grants under Plan head. | 1.79 | 1.89 |  |  |  |
| (r) |  | Development of Cultural Organizations (Cultural Functions Grant Scheme) | To give grants to voluntary organizations of national fame engaged in cultural activities for holding conference, seminars and symposia on important cultural matters. | -- | 3.00 | Organizations to be awarded grants, as per the recommendations of the Expert Committee. | 400 cases approved under this scheme. | -- | 5.43 | The amount of grant has been enhanced from Rs.3.00 lakh to Rs.5.00 lakh per project. |  |  |
| (s) |  | Twang Monastery | To educate the monks and also act as a centre for Buddhist Cultural Studies for preservation the traditional Buddhist art & culture. | -- | 0.01 | Monastery will continue its ongoing programmes including maintenance of their museum. Dying arts of sand Mandala and Butter sculpture will be revived by providing training to the monks students. | The monastery continued it ongoing activities / programmes on Buddhist studies. | -- | 0.70 | The activities of this monastery are financed from the funds allocated for NE region. |  |  |
| (t) |  | Tibet House, New Delhi | The main aims and objectives of the Tibet house are to promote, preserve and protect the Tibetan culture, encourage the exchange the ideas and techniques between Tibetan and non-Tibetan artists and craftsmen. | -- | 0.50 | Tibet House will continue to implement their ongoing programmes including maintenance of Museum | Maintenance of museum and its library continued during the period under report. | -- | 0.38 |  |  |  |
| (u) |  | Central Institute of Himalayan Culture Studies, Dahung, Arunachal Pradesh | To preserve and promote the Buddhist cultural heritage of India. | -- | 0.01 | Under graduate, post graduate and doctoral programmes relating to Buddhist/Tibetan culture to be organized. The infrastructural and building related facilities are to be undertaken. | The academic programmes of the institutions continued in the period under report and funds to the tune of Rs.2.00 cr. are being released for their building construction. | -- | -- |  |  |  |
| (v) |  | #### Development of Jallianwala Bagh Memorial | ## In order to take up a comprehensive development of this Memorial, refitting its status and importance in the history of India freedom struggle. | 0.50 | 0.50 | Developmental programmes will be taken up to upgrade the Memorial. | Grant for development/maintenance of memorial is being given. | 0.00 | 0.00 |  |  |  |
| (w) |  | #### Scheme for safeguarding and other protective measures in the area of Intangible Heritage and Cultural Diversity (arising out of UNESCO Convention) | ## In order to meet the obligations arising from the UNESCO conventions on the safeguarding of intangible cultural heritage and cultural diversity. | -- | 0.50 | There are no fixed targets individuals/organizations involved in Cultural activities and are assisted on the basis of receipt of proposals and recommendations of the Expert Committee. | This scheme is still to be implemented by the Ministry. | -- | 0.00 |  |  |  |
| (x) |  | #### Plan scheme for promotion and dissemination of Awareness about Indian Culture and Heritage | ## To take up activities relating to promotion of cultural and heritage through performing arts and theatres. | -- | 0.01 | This scheme will be implemented through CCRT, after modifying this scheme. | The scheme will be implemented through Library Section of the Ministry in 2011-12. | -- | 0.00 |  |  |  |
| (y) |  | #### Cultural Heritage Volunteers (CHV) Schemes | ## To protect the young people from marginalization and neglect by ensuring their social inclusion and involvement in civic and cultural programmes. | -- | 0.01 | This scheme will be implemented through CCRT. The scheme is being modified. | The scheme is still to be implemented. | -- | 0.00 |  |  |  |
| (z) |  | #### Pilot scheme for Cultural Industries | ## In order to convert wide variety of creative expressions, traditional designs and endless variety of crafts into cultural industries products. | -- | 0.50 | The financial assistance will be given to ZCCs for carrying out pilot survey for cultural industries located in their zones. Other facilities for implementation of this scheme will also be provided. | Due to non receipt of UCs from 2 ZCCs, the further release of fund has been withheld. | -- | 0.00 |  |  |  |
| (aa) |  | #### Financial Assistance for setting up of Multipurpose Cultural Complex including those for children | ## To improve the quality of our life young people be made sensitive to what is aesthetically and morally good in society, to provide new avenues for young people and promote performing art and literature through MPCC. | -- | 3.00 | Releases were made for earlier cases. | Releases were made for ongoing projects only. | -- | 0.72 |  |  |  |
| (bb) |  | #### Flexible Engagements in Knowledge Institutions | ## It envisages lateral movement of scholars/academicians into the institutions to take up projects and research work related to main objective of the institutions and enrich them with a new creative edge. | -- | 1.50 | This is the new Plan scheme and will be implemented in 2010-11. | 13 scholars were awarded. | -- | 0.04 | * includes establishment / administrative expenses. |  |  |
| (cc) |  | #### Institutions & Individuals engaged in Literary Activities | ## To assist the organization of all Indian Characters engaged in the development of literary activities. | 0.10 | -- | Assistance will be provided to Institute/Individuals. | 2 institutions were given grant during the year i) Institute of Historical Studies & Numismatics Society of India. | 0.10 | -- |  |  |  |
| (dd) |  | #### International Cultural activities and grants to Indo-Foreign Friendship Societies | ## To foster closer friendship and cultural contacts between India and foreign country concerned, and strengthen goodwill for Indian culture through friendship societies. | 0.70 | -- | Grants are sanctioned on the specific recommendations for the Indian Mission concerned. The grants cover expenses of grantees on cultural activities. | Authorization given to 49 Missions for utilizing fund for issuing grant to friendship societies abroad for promotion of Indian culture abroad. | 0.21 | -- |  |  |  |
| (ee) |  | #### Indian Literature Abroad | ## To promote Indian languages to six UNO languages | -- | 1.00 | To promote Indian languages to six UNO languages | This scheme still to be implemented. | -- | 0.00 |  |  |  |
| (ff) |  | #### Setting up National Centre for Performing Arts | ## To host cultural shows for performing art | -- | 1.00 | A token provision has been kept to initiate the new scheme. | This scheme still to be implemented. | -- | 0.00 |  |  |  |
| (gg) |  | #### National Gandhi Heritage Site Mission | ## Development of Gandhi Heritage Sites and Establishment of Gandhi Heritage Sites Portal in Sabarmati Ashram Ahmedabad for restoration, maintenance, conservation and development and also for preservation of writings/publications etc. of Gandhiji. | -- | 5.00 | Gandhi Heritage Sites Portal is to be established in Sabarmati Ashram, Ahmedabad. | Rs. 4 crore Corpus fund released for the establishment of Gandhi Heritage Sites Portal. | -- | 4.00 |  |  |  |
| (hh) |  | #### International Federation of Arts Councils and Culture Agencies (IFACCA) | ## Ministries of Culture & Art Councils from over 60 countries are members of IFACCA. | 0.05 | -- | Annual contribution has to be given to join the IFACCA. | Contribution still to be given to the federation. | 0.00 | -- |  |  |  |
| 17. |  | Archaeological Survey of India | This organization is mainly involved in conservation, preservation and maintenance environmental developments of ancient monuments and sites. | 260.00 | 121.00 |  |  | 200.07 | 100.31 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
|  |  | Conservation & Preservation of Ancient Monuments: its up keep and maintenance including environmental development. | For conservation, preservation and maintenance of centrally protected ancient monuments and sites. |  |  | Structural conservation works at about 1600 centrally protected monuments for structural conservation, chemical preservation and horticulture operations based on the priorities, commitments and available manpower and financial resources. Special conservation, restoration and upgradation of historical monuments in Delhi for Common Wealth Games 2010. | Conservation works at about 1600 monuments which includes structural conservation, horticultural development of 150 centrally protected monuments and upgradation of science laboratory at Dehradun and set up of research/ conservation laboratory at Aurangabad. * |  |  | Natural calamities. * ASI has attended Special conservation, restoration and upgradation of 46 historical monuments in Delhi for Common Wealth Games 2010 was undertaken. |  |  |
|  |  | Providing basic amenities tourists | Development of basic amenities in Ancient monuments including provision of toilets, drinking water facilities etc. |  |  | Better visitor facilities and other amenities such as information center, public conveniences, modern ticket counters, better signage, drinking water facilities, etc. would be created at monuments, especially those inscribed on the World Heritage List and other important monuments. | Better visitors facilities and other amenities were provided at various monuments including World Heritage Monuments and Sites. |  |  |  |  |  |
|  |  | Excavation and Exploration. | ## Excavation of Archaeological Sites and Exploration of antiquarian Remains, under Village to Village Survey and Problem Oriented survey |  |  | 1. Excavation of Archaeological Sites and exploration of antiquarian remains. 2. Problem oriented survey. 3. Archaeological investigation using Ground Penetrating Radar System (GPR) in collaboration with IIT, Kanpur at the excavation site of Lathiya, Distt. Gazipur.. 4. Purchase of Machinery and Equipments, tools and plants. 5. Temple architectural survey. 6. Building Survey Project. 7. Financial assistance for excavation for Universities and Research Institutions.* | All the works mentioned col.5 are in progress as these are ongoing projects. |  |  | * 8. Financial assistance for publication. 9. Underwater Archaeology Wing. 10. Epigraphical Survey, photo documentation of inscriptions, etc. 11. Exploration of village to village survey. |  |  |
| - ( |  | Development of the Archaeological Site Museums. | Maintenance/Development of Archaeological Museums |  |  | 1. Phased modernization/ upgradation of more museums. 2. Opening of the museums. 3. Re-organization of the galleries in the museums. 4. Publication of brochures/popular literature. 5. Maintenance of museums. | ASI has been undertaking all works mentioned col.5 in a phased manner at all the appropriate sites/museums |  |  |  |  |  |
|  |  | (i) Publication (ii) Cultural Awareness | 1.Publications under Academic and Informative Series. Celebration of World Heritage and other important days by Circle & Branche offices of ASI for dissemination of knowledge and creating awareness among the masses on our rich heritage |  |  | NEW PRINT Academic 1. Indian Archaeology – A Review – two issues. 2. Memoirs Archaeological Survey India – four issues. 3. Coffee Table/Special Publications. Informative 1. Guide Books – four issues. 2. Special Publication “Coffee Table” (as and when material is received). REPRINT Academic - IAR – one issue. - MASI – two issues Informative - Guide books (other than WHS) – three issues. - Any other publication (out of stock) under special series. Celebration of World Heritage and other important days by Circle & Branch offices of ASI through holding photo exhibitions, quiz/ essay, painting competitions, workshops and other cultural events for school/college students. | NEW PRINTS Academic 1. Indian Archaeology-A Review – published 2003-04 and issues for 2004-05 and 2005-06 are in press. 2. Memoirs: Excavation at Antichak published, excavation at Kalibangan – The Harappans (1960061) – Part I and Udayagiri are in press. Informative 1. Guide Books on Taj Mahal in final stage of publication. 2. Guide books on Sarnath. 3. Special publication: Geoscientific Studies for the Conservation of Ajanta Caves published. 4. Coffee Table Publications: Monuments of Delhi (English) published. |  |  | Non-receipt of complete manuscripts along with illustrations. |  |  |
|  |  | National Mission for Ancient Monuments and Antiquities | a)Mission aims to undertake major activities like documentation of antiquities spread over site Museum of ASI, museums under the control of State Govts. and Universities b) Compilation of data on unprotected monuments and sites c) Digitization of archival drawings of various architectural institutions/organizations and organizing training programmes etc. |  |  | 1. Documentation of antiquities that are lodged in 42 site museums of ASI covering nearly 1 lakh antiquities 2. Documentation of antiquities that are lodged in sculpture sheds of 24 Circles of ASI covering nearly 50,000 antiquities 3. Documentation of antiquities that are lodged in Central Antiquity Collection of ASI covering more than 1 lakh antiquities 4. Documentation of antiquities that are lodged in 251 archaeological museums under the control of 29 States and 6 UTs 5. Compilation of data on unprotected built heritage and sites in 35 States and UTs from secondary sources i.e. both published and unpublished 6. Digitization and creation of data base of more than 4 lakh registered antiquities as lodged with data bank of ASI 7. Digitization of archival drawings that are available with 24 Circles, 6 Branches, 2 Temple Survey Projects and 1 Building Survey Project of ASI 8. Creation of data base of 3675 centrally protected monuments and sites* | 1) Two templates namely built heritage and sites and antiquities have been prepared. 2) About 80,000 listing containing information on unprotected built heritage and sites documented from secondary sources. 3) About 3,50,000 antiquities have been documented. 4) About 35,000 photo negatives of built heritage and sites digitized. 5) Regional training cum review workshop organized at Port Blair. |  |  | *9. Workshops of museum personnel under the control of States and UTs will be organized at 10 different cities of the Country 10. Out reach programmes on heritage awareness for school children will be organized in all the 29 State capitals and 6 UTs 11. Training programmes on heritage conservation and management will be organized for NGOs and concerned State officials in all the 29 States as part of capacity building programme. |  |  |
| 18. |  | National Archives of India | The custodian of non-current records of enduring value of Central Government Ministries / Departments / Offices and their predecessor bodies. The nodal agency for record management activities and their permanent preservation and use by the posterity. | 14.50 | 5.00 |  |  | 11.88 | 2.93 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Expansion of records Management Programme | i. Acquisition of Public Records ii. Appraisal of files iii. Survey and Inspection of Public Records iv. Vetting of Records Retention Schedule. v. Holding of Meeting of Archival Advisory Board vi. Compilation of 9th and 10th Report of DGA on Implementation of Public Records Act 1993. vii Organizing Orientation course in RM for DROs. viii. Inspection of DRR’s of Ministry/ Departments/ Offices. |  |  | Acquisition of 15,000 files\records. Appraisal of 15000 files of the records. 80,000 appraised records of various Ministries/ Departments transferred Vetting of 10 records retention schedule 1meeting to be held annually & follow up actions to be taken. Compilation of 11th & 12th DGA Report to be completed. 7 orientation courses to be conducted 16 DRRs to be inspected. | 6865 files acquired, 6861 records appraised, 28 Archival Assistants engaged in several Ministries for record appraisal. Appraisal of 200666 records, 96203 files transferred by 31.12.2010. Subject listed in AIMS package online 129631 files. |  |  | Physical checking 84026 files for Record Retention Scheduled vetted. 11th & 12th Meetings of Advisory Board held. 6 inspections were also carried out by NAI. 5 orientation courses were conducted. |  |  |
| (ii) |  | Expansion of repair and reprography | Repair of records, binding of books/ volumes/ preparation of security Microfilming, Preparation of Security Microfiche films, Positive printing of microfilms, Supply of copies (Xerox/ Photo/ Reader/ Microfilm to scholars as per their demand). Out sourcing of negative and positive microfilming/ out sourcing of positing microfilming of negative microfilm rolls available in NAI. |  |  | 1,10,000 sheets to be repaired, 80 books, 200 volumes and 1000 misc. items to be bound, 720 rolls to be microfilmed, preservation of 100 bundles of each Palm, Terat and Tulat leaf 60,000 exposoures to be completed, 28,000 meters printing to be done. 50,000 copies to be supplied to scholars. Scanning of 396000 images by Microfilm scanner. Digitalization of Manuscripts – 300 images. | 73643 sheets repaired, binding of 242 vols., 286 books, 966 misc. items taken up. Stitching of 171vols. 209 books and 1159 misc. items were taken up. For Conservation and repair of records and rare books in NAI, procedural formalities are being taken to out source the work. 671 rolls, 26250 exposures, 14432 metres of printing and 1,15,342 copies were undertaken. |  |  |  |  |  |
| (iii) |  | Expansion of library and administration | Purchase of books Data Entry in to the computer Preparation of data input sheets. |  |  | Accessioning of books/periodicals-700 Preparation of data input sheets- 700 Classification of books/periodicals- 700 Books cards prepared- 1500 | 1258 books acquired, 1482 books/periodicals accessioned, 1369 books classified, 4633 books card prepared. 1546 data entries made, 1036 books bound/laminated. |  |  |  |  |  |
| (iv) |  | Expansion of National Register or Private Records (NRPR) | Publication of NRPR volumes |  |  | Volume of 24 & 25 to be compiled & completed | Helping the scholars to have a tangible idea about the custody of documents/manuscripts in the custody of individuals and other voluntary organizations. |  |  | Subject to receipt of adequate no. of properly filled in proformas from States/UT Archives/RRSCs |  |  |
| (v) |  | Expansion of Activities of School of Archival Studies | - One Year Diploma Course in Archives and Record Management - Short Term Courses in Archival Management and allied disciplines. - Monthly Talks, Workshop/Seminars on Conservation, Records Management, Expansion of School Library |  |  | (a) One year diploma course in Archives and Records Management 2009-10 to be completed and diploma course 2010-11 to be started (b) a. Short Term Course in Record Management-two courses to be conducted. b. Reprography – 2 courses c. Servicing & Repair of Records – 2 courses d. Care & Conservation of Books/MMS/Archives – 2 courses e .Archives Management – 1 courses * | Creation of a work force of trained professionals in various disciplines of Archival Administration. Record Management, conservation etc to man various custodial institutions of Archival and documentary wealth of the nation. Creation of awareness on Conservation and proper Records Management in persons working in Govt. and other institutions. |  |  | *(c) 2 seminars are proposed to be conducted. An international Seminar on Business Archives, is proposed to be conducted. A one day interactive session of Professors of History from various Universities is also to be conducted. |  |  |
| (vi) |  | Setting up of a Record Centre in Eastern Zone | - Survey and Accession of non current records - Appraisal of Records - Vetting of records retention schedule. - Repair and preservation of records by INTACH, Bhubaneswar |  |  | Survey and acquisition of non-current records of Central Govt. Office in North Eastern Zone. 2000 files to be appraised Vetting of 2 record retention schedule 30 sheets per working day. | Acquisition of Public and oriental records-384 records were acquired from Andrew Yule Company, Kolkata. 9 vol. of Mayurbhanj Gazettes acquired. 4317 files acquired from An.SI, Kolkata. 306 appraised files acquired from Iron Steel Kolkata. 33 Palm leaf MSS were acquired from Gopinath Mohanty Memorial Trust. |  |  | 25642 sheets were stitched, 1413 sheet digitized. |  |  |
| (vii) |  | Scheme of financial assistance for preservation of manuscripts/ rare books to NGOs. | To financially assist individuals\ NGOs in the State \UTs in securing the valuable documents |  |  | Grants Committee Meeting to be held and the amount recommended by the Committee to be released to the recommended Institutions. | An amount of Rs.5.80 lakh was released as Ist and 2nd installments to 18 NGOs. Besides, Rs.10.42 lakh was also released to 15 NGOs. |  |  |  |  |  |
| 19. |  | National Museum | A premiere institution in the field of art and culture in India and involved in important work of acquisition, conservation, exhibition and educational activities | 7.75 | 10.00 |  |  | 6.51 | 6.81 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Photo-documentation of art objects and events | Coloured photo documentation of Museum’s collection, exhibits for exhibitions and publication purposes and events for publicity purposes, done as per demands. - Miniature paintings - Central Asian antiquities - Manuscripts |  |  | Coloured photo documentation of Museum’s collection, exhibits for exhibitions and publication purposes and events for publicity purpose, to be done as per demand. - Miniature paintings - Central Asian Antiquities - Manuscripts | Target mentioned in col. 5 is achieved. |  |  |  |  |  |
| (ii) |  | Display & modernization of Museum - reorganization of existing galleries. | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | - Jewellery Gallery - Central Asian Wall painting Gallery - Manuscripts Gallery - Bronze Gallery - Pre-Columbian and Western Art Gallery - Maritime Heritage Gallery - Anthropology - Pre-Columbian & Western Art * | Target mentioned in col. 5 is achieved. |  |  | - *Decorative Art - Special storage for wooden door collection - Modular Storage System for Textiles |  |  |
| (iii) |  | Re-modelling of the object in Plaster Casts Acquisition of Books for Museum Library & Educational Activities and Outreach Prog. | To make the artifacts more attractive and colorful. |  |  | Preparation of rubber moulds, raw cast of replicas in Plaster of Paris and raw finished and coloured as per approved list for the sale and gift purpose. | Target mentioned in col. 5 is achieved. |  |  |  |  |  |
| (iv) |  | Restoration and Conservation of art objects. Restoration of Oil Paintings / Conservation of antiquities / art objects / training course in conservation, Acquisition of equipments for conservation / binding of manuscripts. | - To protect the antiquities and art objects from decay. - To train the Museum staff of National Museum and other museums/Institutions in latest technology in conservation. - To keep laboratory well equipped with the latest equipments. |  |  | Conservation : - Chemical Treatment/Conservation of 1000 objects from Museum collection - Restoration / conservation and bindings of 50 manuscripts - Chemical Analysis of 200 Harappan/ Anthropology Metallic Objects - Conservation work of objects from outside institutions such as Parliament Houses, Rashtrapati Bhawan etc. as per demand. Teaching and Training - 3 months training course in conservation of manuscripts/ metal objects. - Programmes on Preventive Conservation for Curators of different Museum/Art Galleries (4days) on Metal and Wooden objects. Survey of National Museum Objects - Examination of Artifacts of different sections to fix priority of conservation of about 1000 objects in a year and also preventive conservation* | Target mentioned in col. 5 is achieved. |  |  | * Workshops & Conference Workshop on Conservation Artifacts at Lahaul Spiti. - Workshop on conservation of artifacts at Leh. - Workshop in North East Re-organization of laboratory - Procurement of equipments for Laboratory as per requirement Condition Reports Examination and preparation of conditions report of Artifacts selected for various exhibitions in India and abroad. |  |  |
| (v) |  | Exhibition Publications Strengthening of Museum Security | - To popularize the ancient Indian Art & Culture. - To organize thematic exhibitions. - To organize exhibitions under Cultural Exchange Programme - To bring out catalogue bulletins, guide books, art publication etc. To strengthen the security arrangements of the Museum |  |  | Special photographs display of Museum objects. Exhibition to be organized subject to the finalization of bilateral Agreement by the MoC Printing of invitation card, brochures. Reprinting of out of stock publication & galleries catalogues etc. Electronic surveillance and maintenance of CCTV system, security equipments. | Target mentioned in col. 5 is achieved. |  |  | AMC awarded to M/s ECIL |  |  |
| 20. |  | National Council of Science Museums | To popularize Science and Technology by organizing exhibition, seminars, training programmes for Science Teachers, students, young entrepreneurs, technicians etc. | 24.25 | 21.00 |  |  | 16.98 | 15.75 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | - Setting up of new galleries, - Upgradation and updation of exhibits, - New circulating exhibitions, - Educational programmes, - New mobile science exhibition units, new training facilities, - Strengthening of infrastructure and existing facilities of 25 science centers located at various parts of the country including Major Civil works - MS Course in Science Communication - to get professionally qualified personnel for popularization of Science. | To modernize, upgrade and popularize the science and technology in the country. |  |  | New galleries will be set at NBSC, Siliguri; DSC, Purulia; RSC, Bhubaneswar; RSC, Jaipur; VITM, Bangalore; RSC, Coimbatore. Additional galleries on ‘Image’ at SSC, Patna; ‘Fun Science’ at DSC, Dhenkanal; ‘Communication’ at BITM, Kolkata; ‘Hall of Mirrors’ at NSC, Delhi; ‘Fun Science’ at Science Centre, Burdwan. Major renovation of gallery works at various Regional Science Centres, DSC, will also be taken up during the year. Two new Travelling Exhibitions will be developed also popular science exhibit for Mobile Science Exhibition will be taken up apart from others travelling exhibitions continued to be circulated. Various major educational activities including Science Fair, Seminars, Festivals, Multi-media Show, Lectures, Science Quiz, Creative Ability Programmes etc. will also be held/developed. Various civil works including renovation, installation of lift, toilets, bore wall, ACs, artifact storage facility, etc. will be taken up. M.S. course in Science Communication will continue. | New galleries at VITM, Bangalore; VITM, Kolkata, DSC, Digha; have been completed and inaugurated. The work for the new galleries/ renovation is complete at NSC, Delhi; including Nehru Planetarium Project, RSC, Lucknow; whereas for remaining 18 museum centres the work will be completed very soon or by end of this financial year. 3 exhibitions including mobile science exhibitions will be taken up/ continue at VITM, Bangalore; CRTL, BITM, RSC, Nagpur and rural areas of the country. Laser shows, science fairs/seminars/ festivals, Science lectures, quiz etc .will be held at various science centres. |  |  | The entire work will be phased out to four quarters to maintain the progress of work, a planned and steady flow of expenditure. Civil works for face lifting of Science Centre at NSC, Delhi; was complete in Sep. 2010 in connection with CWG-2010. Upgradation of sub-station at KPSC, Kurukshetra construction of storage facilities including shed for DG, renovation of children gallery etc. to be continued at BITM, Kolkata. Other civil works continued at various science centres. |  |  |
| (ii) |  | Major Equipment Procurement. | To modernize and provide latest equipment to various RSCs. |  |  | New film for 3D Projection System and Large Format Projection System (LFPS), Spark Theatre, digital planetarium and Immersive Visualization System for various centres will be procured. | Large Video Wall LCD screen, Opto-mechanical Planetarium, 3 new films for LFFPS, 3 D projection system, Spark Theatre, sets of CPC Tele-scopes etc. were procured. |  |  |  |  |  |
| (iii) |  | Science Centres at NE States- RSC, Guwahati, SRSC, Jorhat, SRSC, Gangtok, Sukanta Academy, Agartala, Tripura (Catalytic support) and upgradation of SRSC at Mizoram, Manipur, Shillong, Arunachal Pradesh, Tripura Tribal Areas Autonomous District Council (TTAADC). | To inculcate scientific temper in public at large and students in particularly of that area. |  |  | Strengthening of infrastructure, expansion, upgradation and development of exhibits etc. in the following Science Centres- Guwahati, SRSC, Jorhat, SRSC, Gangtok, Sukanta Academy, Agartala, Tripura (Catalytic support) and upgradation of SRSC at Mizoram, Manipur, Shillong, Arunachal Pradesh, Tripura Tribal Areas Autonomous District Council (TTAADC). | The outcome indicated in column 3 will be achieved in 2010-11. New gallery on ‘Bio-machine’ was inaugurated on Sept 7, 2010. The work for SRSC, Jorhat is in full swing and is expected to be completed by Jan, 2012. Layout for construction of the upgradation of SRSC, Gangtok has given and construction work will start very soon. Development of exhibits for Sukanta Academy, Agartala, Tripura * |  |  | * Tribal Areas Autonomous District Council (TTAADC) is in progress. Action has been taken for other Science Centres Shillong. The 3D system will be installed at SRSC, Mizoram in Jan, 2011. |  |  |
| 21. |  | Science Cities | To popularize Science and Technology at selected centers in the country. | -- | 12.00 | Normally, non plan grant is used for administrative and establishment expenses. |  | -- | 7.74 |  |  |  |
| (i) |  | On Going Projects- RSC Raipur , RSC Dharwad; RSC Ranchi; and SRSC, Solapur, RSC, Coimbatore; RSC, Jaipur; RSC, Pilikula, Mangalore; PCMC, Pune; Regional Science city, Guwahati and 2nd Phase of RGSC, Mauritius. | To inculcate scientific temper in public at large and students in particular. |  |  | These projects for setting up of Science Centres mentioned in col.2 will continue during the year 2010-11. | RSC, Ranchi; was inaugurated on 29.11.2010 whereas RSC, Raipur is complete and likely to be opened very soon. For rest of the RSCs/SRSC/ Science Centres, work will continue in 20010-11 and also in 2011-12. |  |  | Work order for construction of PCMC, Pune already placed. |  |  |
| (ii) |  | New RSCs at, Pune, Assam (upgradation) and Mauritius (outside India) | To inculcate scientific temper in public at large and students in particular. |  |  | These new projects will be taken up during the year subject to fulfillment of conditions under Science Cities norms\guidelines. | The work is under progress. |  |  | These projects taken up subject to fulfillment of conditions under Science Cities norms\ guidelines. |  |  |
| 22. |  | Anthropological Survey of India | Committed to research activities on human population from bio-culture perspectives. Its activities include collection, preservation, maintenance, documentation and study of ethnographic materials as well as of ancient human skeletal remains. | 16.25 | 10.50 |  |  | 13.27 | 5.64 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Documentation and Dissemination Activity I – Special drive initiative for procurement of Hindi Language Publications. To maintain coordination between libraries of all regional centres. Activity II – Outsourcing libraries services in a planned way. Activity III – Maintenance of existing galleries. Museums | To maintain Anthropological Libraries in 7 Regional Centres and Central National Library at Kolkata and also maintenance of museum alongwith its strengthening and zonal fabrications. . |  |  | Scholars of this survey located at the regional centres and the Head Office: To maintain the resource in the form of library materials. Upgradation of the website of the Survey. Survey would be selling books of worth about Rs.1 lakh. The exhibition is likely to be visited by about 3-4 lakh visitors. Work of transferring 25 16mm visual documentary films into Beta-cam format and more than 1000 audiocassettes to continue. Strengthening museum collections with ethnography artifacts to continue. Various exhibitions will be mounted by the museum in NER and in any state. | Modernization of libraries in the survey, retro-conversion and digitization of all the libraries under the survey continued. A number of new books national and international journals, papers procured for all the libraries. Conservation and documentation of museums specimens and maintenance of journal museums, collection of museums specimen and other developmental activities of all the museum for more interactive display continuous. International museum day was observed at the sub regional centre Jagdalpur had office Kolkata Organized an exhibition on the theme ‘Andaman and it people’ at Chakdah (WB). * |  |  | *A one day workshop on ‘Museum of An.SI : Issues and Challenges’ held. southern regional centre, Mysore is celebrating 50th year golden year celebration. A national seminar on ‘Tribes and Analogous People: Contemporary Issues’ was held. Apart from these prog., many exhibition were organized. |  |  |
| (ii) |  | Fellowship programme | At present the Survey has the strength of 47 fellows which has purpose to enhance total fellowship to 67. As these are important component of man power development of resource in the country. |  |  | At present the survey has 47 fellows. It is proposed to enhance total fellowships to 67 and also increase the stipend. | The survey conducted a written test among the applicants for deploying vacant post of JRD and SRF. Deployed research fellows continued their engagement in field work for various projects. |  |  | Pending to achieve the target to enhance number of fellows in different categories. |  |  |
| (iii) |  | Manpower Training /Meetings of Advisory/Executive Committees/Experts Collaborative Schemes Information & Technology Publication | Implementation of various research projects requires meeting and training programmes involving outside experts. Besides internal meetings of the Executive council. |  |  | Implementation of various research projects requires meetings and training programmes involving outside experts. National Advisory Committee of the Survey meeting also need to be held at least twice during the current financial year. Training of administrative and supportive staff. Scholars/fellows of this survey to participate in training programme in various disciplines. | Many officers from regional and HQs of An.SI participated in National/ International seminars/ conferences/ committee/ workshops was deputed/ participated during the year. The survey participated or provided collaborative academic assistance* |  |  | *To different universities/ institutions for hosting national/ international seminars/ conference during the period under report. Survey’s website upgradation continuous. |  |  |
| (iv) |  | Induction of DNA technology System & Soft ware: High/Ultra High through put DNA/RNA analysis system. Bead based suspension array system for proteins and nucleic acids and other activities are taken up by the Survey. DNA Banking. Community Genetics & Health | Maintenance of Infrastructure already developed at Kolkata, Mysore, Nagpur, Shillong and Port Blair. Development of laboratory facilities with DNA technology up to PCR level and DNA Banking at Dehradun and Udaipur. |  |  | Induction of DNA technology in Survey as a part of modernization of physical anthropology laboratories is a continuous scheme. Survey has taken programme of creating state-of-the-art advanced facilities, survey is poised to implement national programs concerning genetics and health integrated with cultural practices of communities. | Annual maintenance of all DNA labs undertaken. Awareness prog. on haemeoglobino-pathic among local students organized by ANRC, Port Blair. DNA lab at Dehradun has been established..UV spectrophotometer is installed at DNA lab Udaipur |  |  | The survey is poised to implement national programmes concerning Genetic and Health Integrated with cultural practices of communities. |  |  |
| (v) |  | DNA Polymorphism of the Contemporary Indian Populations & Ancient Skeletal Material | Study and DNA analysis of the contemporary DNA samples. Human Genome Diversity Analysis . Workshops, Outsourcing manpower. |  |  | Baseline information that is being generated on Indian populations in terms of human genome diversity will be useful in medical applications. | Mitochondrial Genome Variations in Type II Diabetes: Lab work completed. Final report writing is in progress by the deployed researcher. Genome Wide Linkage analysis of Handigodu syndrome in Karnataka, South India: PCR & Sequencing of DNA samples of Handigodu syndrome affected patients are in progress. |  |  | In scientific research of this kind, risk factors can not be predicted |  |  |
| (vi) |  | Physical Growth & Development of Children in N.E India – A Public Health issue | To generate information about the health status of the children of the North East India in Particular. |  |  | Growth of children as public health issue is a mission mode project in North-East Area. Research team to undertake extensive field investigation. | Computerization and analyses of data collected from field investigations continues. Deployed research scholars initiated for next phase of fieldwork among the scheduled communities in the different parts of the North East region. |  |  | Engagement of manpower on contract is under process |  |  |
| (vii) |  | Narmada Valley Excavation | The extensive excavation in Narmada Valley in search of Palaeo-anthropological materials, before submergence. |  |  | Field exploration and excavation work to continue in Narmada Valley and its adjacent areas. To collaborate with European and African groups with extra mural funding to be pursued. Analysis of collected specimens to continue. | Analytical research of the collected fossils from the Narmada river-bed continues in Head Office, Kolkata. Setting up of a field camp is undertaken for Field explorations in Shivalik area. |  |  | First phase of field work has been started by the scholars of this survey in Shivalik area. |  |  |
| (viii) |  | NEW SCHEMES People of India: Cultural Diversity (Five components) a)Intangible & Tangible Cultural Heritage: Oral Traditions, Folk Taxonomies, Social Structure & Bio-cultural Adaptations with Gender Perspectives. b) Establishing a National Centre for Community Knowledge at the new building at Udaipur. c) National Centre for Visual Anthropology: Kolkata d) Man & Environment e) Bio-cultural Linkages with border area countries. | To scientifically documented and projected cultural diversity of the people of India for greater harmony among the communities Aims to highlighting the intangible cultural heritage of Western India Aims to provide methodological tool in anthropological research This project is earmarked for SC/ST which requires extensive findings to frame the all India scheduled for extending required field works. Reconnoiter tour for collection of first hand information for executing the project will be conducted |  |  | Reconnoiter survey, field investigations, data collection, report writing, editing in publishable form, publication of paper, and presentation in academic Seminars/ conferences to exchange views. To Disseminate the intangible cultural heritage of Western Indian through establishing a national centre for community knowledge. To establish a national centre for visual anthropological documentation and making of films. Procurement of equipment, production of 10 traditional knowledge situation and production of 4 documentaries. Reconnoiter survey, field investigations, data collection report writing editing in publishable form, and publication of paper, and presentation in academic seminars/ conferences to exchange views through extensive research in scheduled biosphere reserves. Reconnoiter survey, field investigations, data collection report writing editing in publishable form and publication of paper. Village studies in NE including photograph documentation and mapping. Workshops to be organized. | Field investigations carried out by the deployed scholars in different scheduled locations/communities. Genealogical Records and Traditional Knowledge system in the sacred centers of India, under this project, first phase fieldwork completed on Kamakhya temple, Haridwar, Puri and report writing is under process. b) The work is under process. c) Equipment procured , 3 doc. Films prepared for UNESCO, training-cum-orientation prog. on visual anthropology held. d) Analysis of data collected from 24 villages from the core area is under progress. Deployed research personnel completed second phase of field investigation in Tamil Nadu.for Gulf of Mannar Bisphere Reserve. e) Senior research scholar from NER centre conducted a pilot survey before extensive field investigation. |  |  | Engagement of manpower on contract is under process. Deployed researchers from regional centres of the survey completed field works in Assam, Bastar , Narayanur, and South Andaman. Workshops were organized at Udaipur, Vidyasagar University, W.B. |  |  |
| (ix) |  | # People of India: Bio-cultural Adaptations (Two components) a.)Community Genetics and Health in North – East India b)Genetics & Health: Family Study | To address an important public health issue in the communities of North East and creating an institutional mechanism. Aim to study Bio-cultural risk factor for life style diseases |  |  | To Initiate a collaborative program in North-East on the issue of G6PD deficiency and hemoglobinopathies. To initiate field studies at Mysore and Walatair, which will be implemented with a consortium of specialties and will be known as ‘Mysore Family Study’. Standardization of protocols, through workshops and training. | Field investigation carried out under the research project The Study of village Darang entitled “Community Genetics and Health in North East India: A Study on the War-Jaintias of Darang”. b) Collection of samples under MYFADS has been undertaken. 800 blood and urine samples and other data on Gangadikara Vokkaliga population have been collected. DNA extraction, quantification, biochemical analysis and sample preservation to continue. |  |  |  |  |  |
| 23. |  | Nehru Memorial Museum and Library | Responsible for collection of books, newspapers, unpublished references, private papers/ photographs film takes, and also translation of important papers relating to Pundit Jawaharlal Nehru. | 9.30 | 5.26 |  |  | 6.94 | 6.28 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Research & Publication - Award of Fellowships - Publications Programmes - Seminars and Lectures | To offer three levels of fellowships namely Senior Fellowship, Fellowships and Junior Fellowships and to institute, award scholarships and monitory assistance. To undertake publication of books monographs etc. To organize lectures, seminars, symposia and conferences to promote and encourage the study of Modern Indian History. |  |  | It is a regular ongoing research scheme namely “ Promotion of Research in Modern Indian History and Cotemporary Studies”, “ Perspectives in Indian Development (Social, Economic & cultural)” and “India and Changing Trends in World Economy and Polity”. Publication of basic research documents is a continuous process. Organization of seminars/ lectures is an ongoing programme. | The fellows were working on the different research projects under the 3 ongoing schemes. It published research projects/documents for the benefit of scholarly community. The project for publication of selected works of late Sh.C. RajaGopalachari is also continued.* |  |  | *Tuesday seminars and other lectures were organized. It proposes to organize 4 seminars in the last 3 months of the year. |  |  |
| (ii) |  | Development of Library Acquisition of books, Periodicals/ Resource Material Multimedia Library | To maintain a Library of books, pamphlets, newspapers, periodicals, microfilms, still photographs, motions pictures, sound recording and other materials bearing on the History of Modern India with special reference to the Freedom Movement. |  |  | The Library will continue to acquire books, with a focus on Modern Indian History and related Social Sciences in addition to material on microfilm and photographs. | The library continued to acquire new books in addition to material on microfilm and photographs |  |  |  |  |  |
| (iv) |  | Development of Museum | To maintain and upkeep of the Museum of Jawaharlal Nehru Personalia, memorabilia, mementos and other objects pertaining to his life and the Indian freedom movement. |  |  | General maintenance and upkeep of the museum. Regular activities like mounting new exhibitions, cultural events, the thematic film shows will be undertaken. On the occasion of Historical Milestone of Indian nation, various events will be organized in and around Commonwealth Games-2010. | The work is under progress. |  |  |  |  |  |
| (v) |  | Nehru Planetarium Activities Oral History and Manuscripts Division, Reprography Services, Children Resource Centres | Nehru Planetarium of NMM&L is the only planetarium in the Capital and its programmes stimulate scientific interest among the children. |  |  | For meeting the expenditure on Planetarium, the development and maintenance on day to day bases will be undertaken. The institution will continue to implement the ongoing works on these acts. | It has undertaken the upgradation of Planetarium with projected exp. of Rs.11.75 cr. It is likely to acquire equipments and upgrading the studio It continued to acquire personnel paper of eminent people, it proposes to finalize 25 transcripts as primary sources of Historical research* |  |  | *microfilming of newspapers and private papers acquired by the library, acquisition of raw microfilm, 2 microfilm cameras and 2 reader printers and computerized lamination machine. |  |  |
| 24. |  | Indian Museum, Kolkata | Engaged in reorganization and renovation of galleries housing unique treasures of Indian and foreign art representing centuries of cultural ethos and tradition. | ###### 5.95 | ###### 12.00 |  |  | 4.46 | 6.43 |  |  |  |
| (i) |  | Modernization and upkeep of galleries: Archaeology section, Anthropology Art section Numismatic & Epigraphy Wing | The objectives include refurbishing, modernization & renovation of different galleries and reserve collections with updated arrangements and techniques. |  |  | i) Reconstruction, renovation of 18 galleries ii) Setting up of 2 new galleries ( residual work) iii) Electrification of go-down – 1 iv) Air conditioning of gallery - 1 v)Equipment purchase – 1 vi) Showcase redesigning-1 vii) Fire proof arrangement-1 viii) Documentary film - 1 ix) Field collection - 200 x) Catalogue préparation - 1 | Renovation work is in progress. Art, Arch., Anthropological objects have been physically verified during the period under report. Maintenance and upkeep of the existing galleries is also undertaken. |  |  | Renovation work of the building is being done under supervision of CPWD. |  |  |
| (ii) |  | Strengthening and modernization of security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. | To strengthen the security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. |  |  | i) Engagement of Security Agency & State Armed Police throughout the year. ii) Replacement of existing fittings, fixtures etc. iii) Maintenance & purchase of upgraded & sophisticated security gadgets iv) Illumination development of total campus area v) Upkeep of different electronic devices/fire/ burglary alarm, door frame and hand set metal detectors, CCTV etc. vi) Purchase of computer vii) Organization of training viii) Construction of water tank ix) Intermittent test of security system - x) purchase of vehicle | Upgradation of surveillance system is under process. Engagement of State Armed Police guard and private security agency. Maintenance of CCTV and other electronic devices. |  |  |  |  |  |
| (iii) |  | Strengthening and modernization of Conservation Unit (Conservation Laboratory) | Scientific preservation of antiquities and restoration of art objects. |  |  | i) Conservation of sensitive materials – Textile, ivory, wood carvings, paintings, metal, stone, delicate artifacts etc. ii) Reorganization of mobile conservation Laboratory & its workshop; iii) Purchase of sophisticated instruments and equipments-X ray flurosence portable machine; (b) Thermo-hygro graph (Barigo); (c) UV Monitor; (d) Xerox machine. (e) D-70/80 Camera with accessories. iv) Reorganization of different laboratories (organic/ inorganic) v) Computerized documentation of conservation work; vi) Organization of refresher training courses on conservation, orientation course for museology students; vii) Organization of a Special long term project of laser conservation. | During the period under report, this unit rendered chemical treatment of objects. Conducted insecticide operation in different galleries and other parts of museum campus. |  |  | Rs. 20 lakh as Technical fees for consultant and project management for implementing the development work under upgradation of the Indian Museum. |  |  |
| (iv) |  | a) Programme of Education, Mass Communication and Cultural Activities, b)Publication & printing of Annual Report/ New Publication c) Development of Photography unit and photo documentation of collections d) Project for the Development of Audio Video studio | Organization of education activities and training programmes holding of temporary/ special & inter-state, in-house exhibitions, outreach programme through Museum on wheels (Museo Bus), organization of National/ International seminar and workshop. |  |  | i) National / International seminars and workshop; ii) Mobile exhibition, temporary exhibition; iii) Mass Communication Cultural programme; iv) Annual and memorial lecture series; v) Training programmes – In-service training course and short course in museum studies, practical aspects of Museum methods; vi) Development of Auditorium & Exhibition Hall; vii) Preparation of leaflets, exhibition folders, invitation cards, handout etc. viii) Purchase of computer, wheel chairs for physically handicapped; ix) Reorganization & refurbishing of lecture room. Reprint of old publications-4, printing of new publications-4, Training to officials in advanced printing technology Printing of Annual Report 2005-06 both in English & Hindi Versions and reprinting of picture post card. Purchase photo sensitive materials with accessories, setting up of image bank of photo achieves and maintenance of equipment. A preparation of documentary films on Archaeology, Art, Anthropology, Specimen etc. | a)Museum organized various temporary/ special and inter state in house exhibitions also undertaken various educational and mass communication cultural activities including seminars and workshops in the period under report. b) Participated in various book fairs in India. c)Restoration of old valuable documented negatives of antiquities, photographs taken, printing of photographs, digitization of artifacts etc., maintenance of equipments UPS, Cameras, light units, computers etc. d)Annual maintenance and repairing of audio/video equipments. |  |  |  |  |  |
| (v) |  | Development of Galleries under scientific surveys | To raise the standard of display and presentation of the scientific galleries and to bring them at level with that of the cultural galleries museum proposes to renovate and update the scientific galleries also with the expertise of the respective Surveys. |  |  | i) Extensive renovation of the Mammal Gallery ii) Reorganization of the Insect Gallery iii) Reorganization of showcase of Siwalk gallery iv) Introduction of intercom facility v) Maintenance of galleries under scientific survey | NID Ahmedabad is proposed to undertake the said work for which administrative clearance is being sought. |  |  |  |  |  |
| (vi) |  | Special repairs and maintenance of Museum buildings (heritage) | To develop and structural conservation of Museum buildings and other infrastructural developments |  |  | a)Main Museum building renovation of Damage and sewerage system including pipe lines thoroughly to be taken up of southern side of the building, repairing of doors & windows on 1st floor, de-plastering & re-plastering of ground floor and ceiling and construction a modernized ticket counter | Work on the renovation of the entrance of the main museum building and Siwalik gallery is in progress. |  |  |  |  |  |
| (vii) |  | Development of museums in Eastern & North-Eastern states of the country | To bring about greater and deeper understanding and appreciation of the country’s rich cultural heritage as a whole. |  |  | Formulation of the infrastructural development of the museums of the North-East region during 2008-09 are being re-assessed by a team of technicians, experts, Directors and other Sr. Officers of the Museum including members of the trustees of the Board of the organization. | Student from North-Eastern states have visited Indian Museum under Heritage tour from April to Dec. 10. |  |  | The estimate in this respect was not mentioned earlier. The estimate cost 10% of Rs.20.56 cr. of the BE for 2009-10 |  |  |
| (viii) |  | Art purchase and procurement of art objects and artifacts Exhibitions (Mobile, Special and museum workshops) | Collection in a museum is a life line of its growth. Over the years the museum aims to enrich its collection. To grow awareness amongst the people for those who are not in a position to reach the Museum. |  |  | Acquisition of antiquities, art objects and ethnological specimens to be collected under the jurisdiction of authorities. Different exhibitions including museo bus and mobile conservation laboratory are proposed to the taken up. | Acquisition of art objects is being taken up in the last quarter of the year. Various exhibitions including mobile exhibitions were organized by Museum. |  |  |  |  |  |
| 25. |  | Salar Jung Museum, Hyderabad | A museum of national importance houses rare and varied art collection from all over the globe acquired by Salar Jung I, II and III. | ###### 8.45 | ###### 10.00 | Normally, non plan grant is used for administrative and establishment expenses. |  | 6.34 | 7.50 |  |  |  |
| (i) |  | Project Building | Aims to provide additional space for the museum especially for expansion of galleries. |  |  | Construction of additional floor over western and eastern block for expansion of galleries. | The work is under progress. |  |  |  |  |  |
| (ii) |  | Developmental works (Existing Building) | Under taking various developmental works of the existing building including reorganization of Galleries, modernization of stores, conservation of manuscripts, library etc. |  |  | Developmental works of the existing building and reorganizations of galleries. | This work still to be completed but the work is still under progress. |  |  |  |  |  |
| (iii) |  | Upgradation of security | The security in the Museum is being upgraded by providing CCTV cameras, fire alarm system and fire hydrant system. |  |  | The security in the Museum is being upgraded by providing CCTV, cameras, fire alarm system and fire hydrant system. | Reimbursement of CISF security for 12 months fulfilled. |  |  |  |  |  |
| (iv) |  | Conservation of library books, Artifacts, MSS etc. Other Cultural and Educational Activities | Conservation of art objects /manuscripts available in the Museum Library |  |  | Usual exercise is taken up for conservation and preservation of the artifacts being displayed and also kept in store. Educational activities like summer art camp, museum week, special exhibition, seminars, workshops etc. to be organized. | The work has been completed as per target fixed under various misc. activities/ programmes. Special exhibitions and digitization work also attended to. |  |  |  |  |  |
| 26. |  | Indira Gandhi Rashtriya Manav Sangrahalaya, Bhopal | A museum conceived as a growing movement to depict the story of human kind in time and space highlighting human biological and cultural evolution | ###### 2.90 | ###### 9.50 |  |  | 2.03 | 6.72 | Normally, non- plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Infrastructure Development and Education & Outreach programmes | Develop infrastructure facilities for achieving the objectives of documentation, display and dissemination of rich and diverse cultural patterns of India through Education and Outreach activities and Operation salvage. |  |  | Museum Site Development (Works): (i) construction of dormitory accommodation for tribal artists and students group, Construction of Documentation Centre building, Construction of Indoor Museum Building: Settlement of bills, Construction of boundary wall, Development of Visitor friendly facilities and construction of presentation spaces/auditorium/ upgradation Open air exhibition: The museum will incorporate new house types as exhibits, develop exhibits from Mahanadi River velly, create an open air display space for presentation, construction of indoor presentation/performance space auditorium, upgradation of visitors facilities in all existing open air exhibitions etc. Organization Setup: The existing units will be strengthened with adequate manpower. Development of Exhibition Galleries in Indoor Museum: Development of facilities at regional centre Mysore: Children Festival: Do and Learn Education Programme: Temporary and traveling exhibitions: Interactive-disciplinary training course on Museum and Heritage Management: Seminars/Symposia, museum talks etc. will be undertaken on the themes relevant to the scopes of the museum. | Construction of boundary wall of 500 mt. in 2nd phase, construction work of a fountain near parking and a car parking near office is continuing. Maintenance and upkeep of the open air exhibitions of the museum is carried out. Traditional housetypes of Kom of Manipur, Deori, Rabha, Hajong and Moran communities of Assam were added as exhibit in the open air exhibitions. New exhibits were also added in the Traditional Technology exhibition. 13 special periodical exhibitions were mounted. 5 “Do and Learn” museum education programme, 6 performing art presentations, 1 art and cfaft workshop, a collaborative workshop cum training programme/seminar and celebration on International Day of World Indigeneous People were organized during the period. A five day in service workshop cum training course on conservation of wood, textile and other ethnographic objects for trainees from North East states and a national level capacity building training programme for professionals of ethnographic museums at Bhubaneshwar were organized. Sangrahalaya has mounted nearly 13 temporary and travelling exhibitions at Bhopal. Museum has organized nearly 10 do and learn museum education programmes, National Balrang-2010, nearly 5 workshops and camp and nearly 31 programme of performing art presentations and several other programmes at Bhopal. 6 museum popular lecture and a annual IGRMS lecture, 9 seminar/ symposium were organized. Published 3 books, 1 journal, 1 annual report 2008-09, 3 quarterly newsletters and several brochures, folders, booklets, posters etc. |  |  |  |  |  |
| (ii) |  | Operation Salvage | Systematic action for Salvage and vanishing aspects of traditional material culture is a need because as a result of accelerated rate of change and rapid urbanization, traditional material culture, folk and tribal art objects as well as age old customs and traditions in many parts of India are fast disappearing. A systematic programme of Salvage of such material is being carried out by collection and documentation. |  |  | i)Documentation of Intangible Cultural Heritage in the village around Bhimbetka World Heritage Site ii) Documentation of various aspects of oral traditions in ethno-musicaloges and performing arts iii) Identification and Salvage of rare objects iv)Collection of material culture objects v)conservation of specimens vi)Rock Art research | During the period staff of the museums conducted field work in different remote corners of India to collect and document cultural heritage of India and in the process, collected 86 objects and accessioned in the specimen store of museum belonging to various communities of India. Project for documentation of the Intangible Heritage Culture around the Bimbetka World Heritage site and two projects for translation of old manuscripts available in the Satras of Assam is continuing. |  |  |  |  |  |
| 27. |  | Other Programmes (Museums) |  |  |  |  |  |  |  |  |  |  |
| (a) |  | National Research Laboratory for Conservation of Cultural Property, Lucknow | To develop the capabilities of different cultural institutions in the country in the conservation of cultural property and provide conservation services to Museum, Archives, Archaeology departments and other similar institutions. | 3.14 | 2.20 |  |  | 2.25 | 1.05 | Normally, non- plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Research in Conservation | To develop and standardize better methods of conservation |  |  | 8 projects including 6 continuing projects from the previous year will be undertaken. | Ongoing research project were to be completed. Methods developed- Conservation treatment method for metal -Laser cleaning of art objects -Biological studies on coating materials for the conservation work of stone and monuments objects -Biological studies of Khajuraho group of monuments |  |  |  |  |  |
| (ii) |  | Conservation service/ Field Projects & Technical assistance | To provide conservation services to different museums, art galleries and related departments |  |  | - Regional Archives, Cochin-5 manuscripts,2 rare books,3 maps - Board of Revenue UP – 600 maps - State Museum, Trivandrum– 12 Oil Paintings - Raj Bhawan, Lucknow – Tiger skin-1 - Craft Museum, Lucknow – 10 Textiles - Raj Bhawan, Shimla-wooden boxes-2 Other museums / Institutions – as and when received. | Field projects provided conservation services and technical assistance to needy cultural institutions |  |  |  |  |  |
| (iii) |  | Training in conservation Library & Information | To impart training to conservators, curators and other museum professionals. Acquisition of New Books, Journals, Indexing & Cataloguing and its maintenance |  |  | - Workshop on Care and maintenance of Library materials in the Month of July, 2010. - Orientation workshop on Care and maintenance of Cultural heritage for two weeks in the month of August 2010. - Six month training course on conservation of Art Objects w.e.f. September 2010 to February 2011. - Workshop on Care and Maintenance of Ethnographical materials will be conducted in North – East Region at Dibrugarh in the month of May 2010. Purchase of books and journals. Indexing and Cataloguing Preparation of bibliography | Skill of students/ conservators, curators, Keepers and restoraters was developed. Library database updated and publications on conservation were made available to professionals and general mass. |  |  |  |  |  |
| (iv) |  | Regional Conservation Laboratory, Mysore | To render conservation services in the Southern region |  |  | - Conservation of art objects received from different department in the southern region. - Objects from other institutions to be attended as and when requests are received. - Establishment of facilities for conservation. - Conservation research programmes in collaboration with National Manuscript Mission. | Conservation works to be completed and new projects to be undertaken. |  |  |  |  |  |
| (b) |  | Victoria Memorial Hall, Kolkata | Museum of contemporary art involved in collecting material and data relevant to a period depicting art history during the freedom struggle. | 3.30 | 11.00 |  |  | 2.48 | 5.85 | Normally, non- plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Special repair and renovation work to be undertaken by CPWD/ASI Garden development Construction of an annexe building for auditorium-cum-administrative block | To undertake the repair works of the memorial building, roof and chemical cleaning of both external and internal portion. To proper upkeepment, garden and beautification of lawns. To provide additional space for mounting exhibitions for international standard and seminars libraries facility etc. |  |  | CPWD and ASI will continue the repair work on the basis of estimates. Repair to interior surface of the dumb, de-plastering or re-plastering of the galleries. Construction of ticket sell counters etc. CPWD has completed 50% of the work of landscaping and beautification of gardens. The remaining works will be taken up during the year. Construction of annexe building at the memorial complex including exhibition hall for hosting international/ national level exhibitions etc. | Work of electric transformer room through CPWD completed. For construction of canteen estimate from CPWD received and is and under process. For the remaining projects estimates from ASI received and also funds released , the work is under progress. For development of garden estimates received from CPWD and work is under progress. |  |  | The process for construction of Annexe building at the memorial complex is in progress for its administrative approval. |  |  |
| (ii) |  | Domestic Exhibition | To familiarize the public at large about the richness of the collections and to communicate our past history, culture and aesthetics and atleast one traveling exhibition in any one of the Metropolitan cities in India. |  |  | Curating 3 temporary exhibitions out of the reserve collection. 2 other exhibitions will be held in collaboration with other organizations and abroad. | Various temporary exhibitions were mounted by the memorial at Kolkata, Bhopal, New Delhi, etc. |  |  |  |  |  |
| (iii) |  | Publication | To bring out high quality publication and some authentic catalogue on our unique collections of works of European artists. |  |  | Reprinting & printing of Victoria Memorial Hall Publications and photo albums out of the Victoria Memorial Hall collections. | The sub committee on academic research and publication has cleared to publications during the period under report. |  |  |  |  |  |
| (iv) |  | Strengthening of Security | To safeguard the artifacts and the monument from vandalism and theft and to protect the cultural property |  |  | Installation of fire alarm and fighting system as per recommendation of CISF including smoking detector, installation of surveillance system (CCTV) Installation of 12ft. height’ barbed wire fencing on the perimeter wall. Deployment of 131 CISF/ personals | Security system upgraded , 2 battery operated pollution free cards procured. 1 bag scanner is under proposal for its purchased. CCTV camera and system repaired * |  |  | And is working properly alongwith 13 walki talkies |  |  |
| (v) |  | Setting up/ Modernisation of galleries and storage of art objects and installation lighting, climate control, visitors facilities etc. | To restructures, remodel all the galleries of the Memorial with proper display, lighting system and climate control. |  |  | 3 galleries with thematic and scientific display to be modernized. Certain stores with chemically controlled fixtures and modern storage equipments. | the matter is under process. |  |  |  |  |  |
| (c) |  | Allahabad Museum, Allahabad | The main activities of the museum include acquisition of art objects, reorganization of galleries and reserves enriching the library and photography unit and publication | 1.98 | 2.50 |  |  | 1.25 | 1.41 | Normally, non- plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Renovation of Building | Aim to provide additional space required for staff and visitors in a proper manner. |  |  | Renovation of the sitting rooms of the Asstt. Keepers etc. including mainly paintings of walls and roofs. Plastering at various point in the museum building. Construction of toilet on the first floor. Other repairing and cleaning works. | Certain portions of existing building were got to set a new look and required space and facilities for staff and visitors also is expected to increase. |  |  | Progress dependent on timely availability of funds |  |  |
| (ii) |  | Library Photography, documentation and strengthening thereof. | To strengthen the library collection and also to acquire number of journals and volumes of sets possessed by the museum, to microfilm certain books and journals which are not available by sending a team consisting of Museum personnel and to acquire books and journals of importance to enrich the Museum library. |  |  | Routine work of classification, cataloguing and computerized book inventory; binding of books, cataloguing of Persian manuscripts by engaging an expert, purchase of Library Software; purchase of Library books. | 48book on different subjects were acquired and accessioned, 700 books were classified and 700 books were catalogued. 15 issues/copies of journal/magazine subscribed, 6 daily newspapers were regularly received in the Museum. |  |  | 5339 readers attended the library and a number of books were consulted by the scholars. Various seminars, lectures, workshops, exhibitions were organized. |  |  |
| (iii) |  | Modernization of galleries | The objectives include wood paneling, fabrication of new showcases\wooden blocks, modernization\reorganization work in various existing galleries of the museum. |  |  | Wood paneling in Minor Archaeological and Sculpture galleries. Fabrication of wooden blocks for partition in Coomaraswamy Hall and new showcases and renovation of old ones departmentally. Framing and mounting of more than 500 paintings in miniature and modern paintings gallery. Modernization of Nehru gallery and other important works will be attended. | Modernization work was carried out to provide better knowledge of our ancient cultural heritage to the visitors. |  |  | Work renovation of showcases in galleries, polishing and painting works in the gallery will attract the visitors. |  |  |
| (iv) |  | Acquisition of Art Objects | To acquire art objects for the Museum through Art Purchase Committee in its meeting to be held at suitable intervals. |  |  | First & Second meetings of Art Purchase Committee may be held in Oct. 10 & Feb.11 respectively. | Second meeting of Art purchase committee will be held very shortly. |  |  | It will be ensured that no fake antiquities will be acquired. |  |  |
| (v) |  | Exhibition and display Organization of reserve collection. Modelling Section. Educational and other cultural activities Research Fellowship & Exploration and Chemical Conservation Laboratory. | To encourage the budding artists of the country and to increase the knowledge of religion and culture of people of North Eastern Region |  |  | Reorganizing reserve collection of explored material, preparing showcases for Bronzes and Archaeological objects, exhibition of renowned sculpture artists Shri Gyan Singh and Shri Lallen Singh. Exhibition of prize wining paintings of renowned artists including sculpture artists to be held. To hold photography exhibitions of masterpieces in the museum at different educational institutions and museums. | Exhibition entitled ‘Abhiruchi-2009’ ‘Sarjana-2009’ ‘Amar Shahid Chandrashekhar Azad:yaktiva Evam Krititva’ and poster exhibition was held. The museum organized a number of seminars, lectures, special lectures, workshops, and children week. |  |  | Conservation of a total number of 522 objects, 10 paintings, 300 MSS, 110 bronze metal and 25 archival documents were conserved |  |  |
| (d) |  | National Museum Institute of History of Art, Conservation & Museology, New Delhi | To provide education and training in the specialized areas of art, history, conservation and restoration of artifacts and their display and upkeep in museum. | 0.25 | 4.00 |  |  | 0.12 | 3.00 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Academic Programme Noida Project | Dissemination and advancement of knowledge in the fields of History of Art, Conservation and Museology. To establish it own building over 3 acres of land at Sector 62, Noida. |  |  | Conducting of courses by admitting students to M.A. courses (55 seats) and Ph.d courses (12 seats) and 3 short terms courses – two in English and one in Hindi (about 250 participants). | 10 students passed out M.A. degree and 6 students passed Ph.D. Short term courses are still under progress . 1 International symposium/ seminar/ workshops held. Construction could not be taken up due to non approval of SFC. |  |  | Duration for Ph.D is 5 years. The short term courses are for duration of 5 months. |  |  |
| (e) |  | Scheme for financial assistance for ‘Promotion & Strengthening of Regional & Local Museums’ | To promote the strengthening and modernization of existing museums at the regional, state and local level. | -- | 14.50 | About 50 museums will be benefited for the grants under the scheme. The financial limit under this scheme has been revised. | 46 museums/organizations were given grant for promotion & strengthening purposes. | -- | 10.36 | Release of funds depends upon the number of complete/ proper proposals received from different museums |  |  |
| (f) |  | Scheme for Modernization of Museums in Metro Cities | In order to bring some of the Museums in the Country at par with the best in the World. | -- | 6.00 | Modernization of two museum one at Egmore Museum, Chennai and other at Chatrapati Shivaji Vastu Sangrahalaya, Mumbai is proposed apart from National Museum and Indian Museum. | Grant released to Chatrapati Shivaji Maharaja Vastu Sangrahalay, Mumbai | -- | 1.83 |  |  |  |
| (g) |  | Vrindavan Research Institute, Vrindavan | To preserve cultural heritage of India | 0.17 | 0.43 | Various research, documentation activities on Braj culture and conservation of manuscript will be undertaken. | 7 publication from VRI manuscripts undertaken and survey and documentation of Braj Folk Culture continued | 0.13 | 0.32 |  |  |  |
| 28. |  | National Library, Kolkata | To serve as a repository of all reading and information materials produced in India as well as abroad concerning India | 21.50 | 15.00 |  |  | 16.25 | 8.35 | Normally Non Plan Grant is used for administrative and establishment expenses |  |  |
| (i) |  | Collection Building & Book Production Statistics | To collect books and other printed materials published in India, Acquisition of Foreign Books and Periodicals |  |  | Through D.B. Act/ purchase Foreign books- 3500 Titles-680 30,000 Indian publications have been targeted to acquire. | 23,970 Indian publications have been acquired 2176 foreign books have purchased and 680 titles of foreign journals have purchased. |  |  | Deposits under Delivery of Books and Newspapers Act, 1954 depend upon cooperation by publishers |  |  |
| (ii) |  | Retro-conversion Project & Digitization of old, Rare publications (Reader Service) | Retro-Conservation, Digitization and Modernization of Laboratory, Preservation Computer Units |  |  | Under Retro-conversion and digitization programme, it is targeted to create 4 lakh records of old and rare brittle reading materials. 14 lakh pages are to be digitized during the year. | It will preserve the old brittle reading books and upgrade the preservation, conservation and computer units of the Library for readers service. |  |  | Selection of firms , agencies to be done on the basis of open tender with subject to timely administrative approval. |  |  |
| (iii) |  | Strengthening of Administration | Furniture & interior decoration of Bhasha Bhavan etc. |  |  | Furniture for all the Division of Library in Bhasha Bhavan to be provided . | To improve the working environment for the staff and the visitors. |  |  | It is subject to timely administrative approval. |  |  |
| 29 |  | Delhi Public Library | To provide free library and information services to the people of NCT of Delhi and also to provide mobile library services in rural area of Delhi. | 10.70 | 5.00 |  |  | 7.49 | 4.08 | Normally Non Plan Grant is used for administrative and establishment expenses |  |  |
| (i) |  | Collection Developments | The basic objective of DPL is to provide free library and information services to people of Delhi. In order to achieve this objective, DPL proposes to strengthen its collection development in all the service units. Besides this updating of Reference Collection of Central Library and Sarojini Nagar will also be taken up by acquiring new reading materials. |  |  | Around 4000 titles (60,000 Multiple Copies to be purchased for the DPL system in English, Hindi, Urdu, Punjabi, Besides audio & video cassettes and reference books etc. | Around 16,000 books purchased upto Dec.10 |  |  | Delay in constituting a Book Advisory Committee. |  |  |
| (ii) |  | Conservation and Preservation | Binding care and repair of books and other reading materials are continuous activity of DPL. Preservation of documents is a compulsion in a library for posterity purpose. |  |  | Around 20-25 thousand new books are to be bound through commercial bookbinders. | Books were transferred to binders for binding by the Deptt/ . |  |  |  |  |  |
| (iii) |  | Modernization and IT Development | Modernization of library activities is the continuous process of DPL. It is proposed to augment the computer system of library, which requires more computer, server, scanner, operating system, ISM etc. for creating of database in other Indian languages. |  |  | DPL has started free internet access services by installing 15 terminals at Patel Nager, these terminals each in Sarojini Nagar & Central Library. DVD corners have also been set up in 3 libraries – Patel Nagar, Sarojini Nagar & Central Library. This service is proposed to be extended in 5 branches this year. | Free internet service extended to another 6 units viz.,Karol Bagh, Vinobha Puri, Janak Puri, Narela, R.K. Puram Sec. 8 and Shahadra libraries. |  |  |  |  |  |
| (iv) |  | Seminar/Lectures/ Training |  |  |  | Around 25 staff members to be trained during the year. | Officials were deputed to various trainings and seminars. AS per recommendation of 6th CPC, 64 group IV employees were given in house training. |  |  |  |  |  |
|  |  | New Schemes a. Opening of New Libraries |  |  |  | It is also proposed to open new libraries in the areas inhabited by weaker section of the society. | No new library could be set up during the period under review. |  |  |  |  |  |
| 30. |  | Raja Rammohun Roy Library Foundation | To promote and support public library movements in the country. | 2.90 | 30.00 |  |  | 2.03 | 28.45 | Normally Non Plan Grant is used for administrative and establishment expenses |  |  |
|  |  | Matching Schemes: a) Assistance towards building up of adequate stock of books b) Assistance towards organization of mobile libraries and rural book deposit centers c) Assistance towards storage of books d) Assistance towards seminars, workshops and book exhibitions e) Assistance to public libraries towards increasing accommodation f) Assistance towards acquisition of TV-cum-VCP sets for educational purpose/Computer for library application Non-matching Schemes: a) Assistance to voluntary organizations providing public library services b) Assistance to children libraries of children section of general public libraries c) Assistance to state central libraries and district libraries through central selection of books d) Assistance to centrally sponsored libraries –affiliated libraries under Visva-Bharati e) Assistance towards organization of seminars, conferences etc. of an all India level Professional body like ILA, etc. f)Assistance to public libraries towards centenary celebrations g) Assistance towards establishment of Children's corner | Replenishment of book stock of libraries Providing library facility to remotest corners Providing storage materials Providing awareness, orientation to library professionals Construction of Library building Supply of audio-visual aid and supply of computers for automation To encourage voluntary zeal towards providing library service To promote reading habit amongst children Replenishment of book stock with recent costly books Replenishment of book stock with recent costly books To encourage National Professional Organizations To encourage old libraries To attract children users |  |  | 9000 Libraries to be assisted with 3 Crore Books Libraries – 10 Libraries – 3500 Organizations –50 Libraries – 140 Libraries – 70 Libraries-260 Libraries-175 Libraries-479 Books – 15 Million Libraries-37 Organizations –5 Libraries-35 Libraries-100 | 8011 Libraries 8 Libraries Libraries-1846 Organizatons-22 Libraries-119 Libraries-57 Libraries-97 Libraries-75 Libraries-479 Libraries-37 Organizations-10 Libraries-21 Libraries-19 |  |  | State Govts. sometime failed to release contribution in time As a result finalization of proposals may be delayed State Govts. sometimes failed to send applications in time. As a result finalization of proposals may be delayed depends on the meeting of the Book Selection Committee. |  |  |
| 31. |  | Other Libraries |  |  |  |  |  |  |  |  |  |  |
| (a) |  | Central Reference Library, Kolkata | To implement (a) Compilation and publication of the Indian National Bibliography (in Roman script and respective language scripts) which is a bibliography of current Indian Publications in Indian languages recognized by the Indian Constitution and in English and (b) Compilation and Publication of Index Indiana. | 2.02 | 0.60 |  |  | 1.66 | 0.43 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
|  |  | Indian National Bibliography & Index Indiana Other activities | - Publication of INB Annual volume 2007 - Compilation of INB Annual volumes 2008 - Monthly issues of INB 2009 January to December. - Compilation & Publication of Index Indiana - Apprenticeship Training programme - North East Region development programme - Data collection centers at 5 state capitals at Chennai, Bangalore, Hyderabad, Pondichery & Thiruvananthpuram |  |  | a) 250 copies of Annual Volume of INB 2007. b) Manuscript of 2008 INB vol. to be ready. c) Monthly issues of INB 2009. d) Manuscript of 2009 INB vol. ready. 100 copies of index Indiana-2004-2009 6 batches of 30 students to be trained in Librarianship, 2 Training/ Workshop/Seminar/ Programme Putting the INB database on the net. 3 book fairs. | a)Achieved 250 copies of the publications brought out. b) achieved, the manuscripts of 2008 in press. c) 12 monthly issues of INB 2009 published. d) in press 100 copies of MSS being ready. 30 students already trained 1 seminar conducted at Imphal, Manipur Proposals with NIC Organized sale and exhibitions of CRL publications. |  |  |  |  |  |
| (b) |  | Khuda Baksh Oriental Public Library, Patna | This Library has been evolved out of a personal collection of Maulvi Mohd. Bakhsh who was a man of letters with a great passion of books. It houses over 20000 manuscripts and some rare printed books. | 2.02 | 1.50 |  |  | 1.30 | 0.00 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Acquisition: Purchase of Books, manuscripts, microfilms, Video & Audio Cassettes | To acquire books, manuscripts, microfilms, Audio & Video CDs for use of readers |  |  | Purchase of 5000 printed books, 50 manuscripts and 120 titles of periodicals. | Purchased 4185 printed books and 87 periodicals, 27 newspapers, 10 MSS. |  |  |  |  |  |
| (ii) |  | Research & Publication: Publication of rare material , Printing of Catalogue, Research seminars, Lectures & Cultural programmes, Khuda Bakhsh Research Fellowships and Publication of Quarterly Journal. | To bring out critical editions of manuscripts, publish books of rare value, lectures by distinguished scholars. To acquaint the outsiders with the hidden treasure descriptive catalogue. Organization of seminars, lectures of distinguished personalities. Fellowship and Scholarships to renowned scholars. |  |  | Publication of English translation of 3, Hindi translation of 1 and facsimile of 2 rare manuscripts Publication of 20 books. Printing of 2 volumes of catalogue , organize National Seminar 2, Annual Lectures 1, Extension Lectures 4, Popular Lectures 12, Cultural Programmes, Senior Fellowship – 3 Junior Fellowship – 7 Assigning research projects to scholars Publication of 4 issues of Quarterly Journals. | 9 books published one seminar, 1 annual lecture, 2 extension lectures, 3 popular lectures, 3 exhibitions and a few other cultural programmes were organized. 3 senior fellows and 7 junior fellows are working. Award of Tagore National fellowship. Five issues of journal brought out |  |  |  |  |  |
| (iii) |  | Conservation & Preservation : Preservation Laboratory and development of books preservation & reprographic facilities. Modernization and automation. Organization of events and exhibitions. | Preservation Lab. For routine maintenance, curative as well as preventive and preservation. To keep the books in the good condition. |  |  | Routine activities for preventive and curative preservation of books and manuscripts. Getting printed books and manuscripts bound on contract basis. Rescanning work of manuscripts will be taken up. | 59 MSS and 69 books repaired and bound. Curative treatment was given to 11423 folios of MSS besides fumigation of 524 MSS. 49 books and 63 MSS got bound.13553 folios of MSS and books laminated.* |  |  | * by contract binder. Pilot project of digitization of 10 lakh pages of MSS completed by NICSI. |  |  |
| (c) |  | Thanjavur Maharajas Serfoji’s Saraswati Mahal Library, Thanjavur | A priceless of repository of culture and knowledge, it was conceived as the Royal Palace Library in the 16th century. | -- | 1.10 |  |  | -- | 0.44 |  |  |  |
| (i) |  | Publication of books from the manuscripts in Sanskrit, Tamil, Marathi etc. | To translate, transliterate the manuscripts and to bring out books. |  |  | 14 New Books and 10 Reprints will be taken up during the year. | The work is under progress. |  |  |  |  |  |
| (ii) |  | Conservation | To apply citronella Oil to Palm leaves and to preserve the Paper manuscripts/ Valuable Old books etc. |  |  | 110000 leaves of manuscripts to be cleaned 2000 books are to be mended and preserved | A number of MSS have been chemically treated and conserved. |  |  |  |  |  |
| (iii) |  | Reprography | Microfilm of Manuscripts and rare books for preservation. |  |  | 1000 new Tamil manuscripts are to be microfilmed cleaned | The work is under progress. |  |  |  |  |  |
| (d) |  | Library for Tibetan works and Archives, Dharamshala, H.P. | Aim to acquire and conserve Tibetan books and manuscripts and to provide intensified reference service as well as Centre for Tibetan manuscripts, paintings and object of Arts. | 1.20 | -- | The institute was set up with a view to preserve and promote the rich heritage of Tibetan civilization and Indo- Tibetan learning. | The activities of this library continued to provide research facilities particularly in the Buddhist Philosophy and Tibetan art & culture. | 0.90 | -- |  |  |  |
| (e) |  | Rampur Raza Library, Rampur | The main objective of the library to acquire and conserve Indo-Islamic manuscripts, miniatures, books and other objects of arts and science in the library and to serve as a centre of reference and research and also act as a centre of Arts for International importance. | 1.18 | 4.05 |  |  | 0.83 | 0.93 | Normally, non plan grant is used for administrative and establishment expenses. |  |  |
| (i) |  | Publication & Printing | Publication of books of text of Arabic, Persian and Sanskrit manuscripts. |  |  | Publication of books, journals, technical reports and painting – includes publication of books on history and culture, catalogue, journals text of MSS monograph of painting, technical reports, Annual report, colour picture postcards preparation of coloured and slides, printings of various performas and certificates, requisition slips for books and MSS invitation cards. | 4 books have been published & rest of the books are under printing. |  |  |  |  |  |
| (ii) |  | Preservation and Renovation of two Heritage Buildings. | Two historical palaces of Raza Library viz Hamid Manzil and Rangmahal are monuments of archaeological importance, in need immediate repairs which was approved 37th meeting of Rampur Raza Library Board. |  |  | Most of the ornamental ceilings of the rooms of Hamid Manzil have been restored within last 8 years and rest will be restored in the financial year 2010-11. | This is continuing project and targets will be achieved by 31st March, 2011 |  |  |  |  |  |
| (iii) |  | Acquisition of Books, MSS Scholarships and awards Seminars/workshops/ exhibitions Preservation and conservation of the collections, Computerization and application of IT, Deployment of CISF, Training Programmes and Modernization of Darbal Hall Museum. | Acquisition of rare MSS books and art objects for meeting the demands of research scholars Organizing Akademic and cultural activities for interaction of scholars, Academicians To protect prices less collection of the library |  |  | 12 rare MSS 6 printed books, 177 books and 9 art objects 5 scholarships and 3 awards 3 seminars, 2 workshops, 2 exhibitions and 2 lectures Mushiara and Kavi Sammelon about 6000 pages of rear MSS art objects, books, paintings etc. | 238 books and 19 manuscripts have been purchased. 12 scholarships awarded. Nawab Faizullah Khan & Nawab Raza Ali Khan Ceremony, One Seminar and one exhibition have been organized. 1918 pages of MSS, 1230 printed books, 08 Maps* |  |  | *9 miniature painting with calligraphy on back side and 92 mss and book fumigated of Library. About 2 lakh pages digitized. 26 security guards deployed. |  |  |
| (f) |  | National Mission for Preservation of Manuscripts | Aims at cataloguing, conserving and collecting the invaluable manuscripts from all over the country and to strengthen manuscript resource centers, manuscript conservation centers and digitization of catalogues and prestigious manuscripts. | -- | 7.50 |  |  | -- | 5.13 |  |  |  |
| (i) |  | National Manuscript Library | To create National Manuscript Library |  |  | The entire digitize Manuscripts and other important as well as rare documents will be housed in the Library. | 20 lakh images were digitized |  |  |  |  |  |
| (ii) |  | Networking through MRCs- | Documenting the available manuscripts in MPCs. |  |  | 48 MRCs to be given grant for executing the work of documentation and other identified works. | 1st installment has been released. 1.49 lakh MSS documented. |  |  |  |  |  |
| (iii) |  | Networking through Manuscripts | Aims to provide training in conservation and allied fields |  |  | To run the existing 33 MCCs and to release grant @ Rs. 5.00 lakhs for each centre | Preventive, Conservation done 4.78 lakh MSS and curative conservation done for 0.64 lakh MSS. |  |  |  |  |  |
| (iv) |  | Conservation workshops and Training | To conduct preventive, rare support, curative workshop etc. on demand basis |  |  | To conduct zone wise workshops | 14 workshops were conducted & 395 candidates trained. |  |  |  |  |  |
| (v) |  | Research and Publication | To edit and publish the printed books |  |  | About 50 books/MSS to be edited and published along with Samiksika, Samrakshika and Tattvabodha | 2 books could be released. |  |  |  |  |  |
| (vi) |  | Digitization | To digitize important Manuscripts |  |  | This is continuing scheme to digitize MSS through the selected parties | 20 lakh images were digitized. |  |  |  |  |  |
| (vii) |  | National Survey and Post Survey | To carryout National Survey to identify the manuscripts |  |  | To cover 5 states for identifying and documenting MSS located in the survey | 2.6 lakh MSS identified and Post Survey conducted in 3 states documenting 25000 MSS. |  |  |  |  |  |
| (viii) |  | Manuscriptology and Paleography workshops and training | To promote the manuscriptology through Universities. |  |  | To conduct zone wise for level I/II/III workshops and training | 425 scholars trained in 9 workshops conducted. |  |  |  |  |  |
| (g) |  | Setting up of a National Mission on Libraries, leading to the formation of a Commission. | To pointedly address the problems of Public Libraries and to upgrade the infrastructure and technological environment of the Public Libraries within a time frame | -- | 10.10 | Token provision has been made to initiate the spade work. for National Commission on Libraries. | The scheme of National Mission on Libraries could not be implemented on account of similar objective of RRRLF. | -- | 0.00 |  |  |  |
| (h) |  | Asiatic Society, Mumbai | A premier research institution in the realm of philosophy, language, arts and social sciences in relation to Asia in general and India in particular. To maintain and enhance its role the Society maintains a library and a heritage museum of rare manuscripts and artifacts. | -- | 1.00 | Purchase of 600 printed books microfilming of 650 pages daily, digitization of 600 pages daily of rare books, conservation/ chemical treatment to 1200 books to be fumigated, 5800 pages de-acidified, 57900 pages tissued and 1800 maps to be fumigated. | Purchase of 64 printed periodical and 137 books of pre-modern & 387 books of modern subjects. Microfilming of 5900 pages, digitization of 5 DVDs on rare books/Journals | -- | 0.75 | Conservation of 710 books by fumigation, 37318 pages de-acidify, 35116 pages tissued and 1500 maps fumigated so far. |  |  |
| (i) |  | National Archives for Audio Visual Materials | This will act as central data bank on intangible cultural heritage and Nodal Agency for integrated knowledge and actual documented material. | -- | 1.00 | This is the new scheme and preliminary work for formulation of scheme and other related issues will be taken up during the year. | The details of the scheme is still to be worked out and likely to be implemented in 2011-12. | -- | 0.00 |  |  |  |
| (j) |  | State Central Library, Mumbai | To acquire books and periodicals under the provision of press and registration of Books Act, 1867 and the delivery of Books Act, 1954 and preserve them for posterity. | 0.30 | 0.20 |  |  | 0.00 | 0.00 |  |  |  |
|  |  | Modernization/ computerization/Digitisation /Up gradation of state central library | To digitize rare books and manuscripts: Computerisation/ Retro-conversion of DBA books |  |  | 17000 books, 800 periodicals, 500 newspapers receivable in DBA section to be technically processed and provided to the 2 lakh readers. | The library collected books/ reading material under D.B. Act for the readers, researchers and scholars. |  |  |  |  |  |
| (k) |  | Connemara Public Library, Chennai | It is one of four Depositories of Indian Publications under the Provisions of the Delivery of Books and Newspapers (Public Libraries) Act of 1954, as amended. To receive all materials published in India free of cost. It serves as a UNESCO information center and receives all the publications of UNESCO. It is also a depository for Asian Development Bank Publications. | 0.35 | 0.60 | Upgradation of library and to render Right Information to the Right User at right time. | 18676 books were received under DB Act. 16378 standard works were processed. | 0.25 | 0.42 |  |  |  |
| 32. |  | Provision for Project/ schemes of N.E. Region and Sikkim |  |  |  |  |  |  |  | ** exp. upto Dec. 2010 for the activities of NER has been included in the respective Plan Heads /Schemes. |  |  |
| 32.1 |  | Project/ Schemes for promotion of Art and Culture | To promote, disseminate and protect unique art and culture of NER. | -- | 53.24 | Organizing various programmes/schemes in the field of promotion of art and culture in the North Eastern States and also benefiting NGOs /individuals through departmental schemes. | Preserved the rare and old documents for posterity. | -- | ** |  |  |  |
| 32.2 |  | Archaeology, Archives and Museums | To promote cultural activities in the fields of Archaeology, Archives and Museums | -- | 15.66 | Development of Museums in North East Region and providing financial support to NGOs in NER in the field of Archival activities. Conservation and protection of various ancient monuments/sites located in NER. | Creating awareness of ancient culture of India in NER. | -- | ** |  |  |  |
| 32.3 |  | Libraries | To promote Library activities in the NER | -- | 4.60 | Development of Library activities in North East Region. | Inculcate reading habits through library movement. | -- | ** |  |  |  |
|  |  | Total ( provision for NER) |  | -- | 73.50 |  |  |  |  |  |  |  |
| 33 | Building projects of attached / subordinate offices |  |  |  |  |  |  |  |  |  |  |  |
| 1. |  | National Museum, New Delhi | Civil & electrical works in National Museum | -- | 2.00 | Civil & electrical works in National Museum | To provide better facilities in the galleries and official wing of National Museum. | -- | 6.15 |  |  |  |
| 2. |  | National Archives of India |  | -- | 6.45 |  |  | -- | 0.75 |  |  |  |
|  |  | (i) | Replacement of A/C plant for NAI Building. |  |  | Replacement of A/C plant for NAI Building. | Providing better facilities in disposing of voluminous work and also protecting the valuable records available in the Archives. |  |  |  |  |  |
|  |  | (ii) | Import of 4 Impregnator Laminators |  |  | Import of 4 Impregnator Laminators |  |  |  |  |  |  |
|  |  | (iii) | Construction of functional building of record center, Bhubaneswar |  |  | Construction of functional building of record center, Bhubaneswar |  |  |  |  |  |  |
|  |  | (iv) | Addition and alteration of works of NAI Main/ Annexe building, Record Centre Jaipur and Pondicherry and Regional Office Bhopal. |  |  | Addition and alteration of works of NAI Main/ Annexe building, Record Centre Jaipur and Pondicherry and Regional Office Bhopal. |  |  |  |  |  |  |
| 3. |  | Anthropological Survey of India |  | -- | 4.00 |  |  | -- | 0.09 |  |  |  |
|  |  | (i) | Construction of Office building at Salt Lake, Kolkata |  |  | Preliminary estimates for construction of building has been intimated by CPWD for taking up these projects. | Creation of additional office accommodation |  |  |  |  |  |
|  |  | (ii) | Procurement of land and construction of Museum at Central Regional Centre, Nagpur. |  |  |  |  |  |  |  |  |  |
|  |  | (iii) | Construction of residential quarters guest house and Museum of International Standard etc. at Udaipur |  |  | Work is under Progress |  |  |  |  |  |  |
|  |  | (iv) | Procurement of additional land & construction of Guest House Library, Museum and Conference Hall of North East Regional Centre at Shillong. |  |  |  |  |  |  |  |  |  |
|  |  | (v) | Construction of residential quarters and guest house of North West Regional Centre, Dehra Dun. |  |  |  |  |  |  |  |  |  |
|  |  | (vi) | Procurement of additional land and construction of an International standard guest house DNA lab. At the SRC, Mysore. |  |  | Work is under progress |  |  |  |  |  |  |
|  |  | (vii) | Construction of Office Building and museum at SRC, Jagdalpur |  |  |  |  |  |  |  |  |  |
| 4. |  | National Research Laboratory for Conservation of Cultural Property, Lucknow | Construction of Training Institute/auditorium in the campus of NRLC Guest House | -- | 2.50 | Work is under progress | For important activities of Laboratory, Training Instt.-cum-Hostel/Guest House at NRLCCP, Lucknow. |  |  | Completion of works depends on the efficiency of CPWD. |  |  |
| 5. |  | National Gallery of Modern Art | Furnishing of new Annexe buildings of NGMA at Delhi and Bangalore. | -- | 4.00 | Work is under progress |  |  |  |  |  |  |
| 6. |  | Archaeological Survey of India | Purchase of land for construction of office building for ASI at Nagpur , construction of Institute of Archaeology at Greater NOIDA,, Construction of composite office building on own land of ASI at Samantarapur, Bhubaneswar, Construction of building at 24, Tilak Marg, New Delhi, construction of new museum building at Lothal, Halebidu, Sanchi and at Surya Pahal (North East). | -- | 24.00 | Work is under progress | Accommodation problem of ASI staff shall be solved. | -- | 7.72 |  |  |  |
| 7. |  | Public Libraries | Central Reference Library The work relating to installation of A/C facilities in their office | -- | 0.05 | This work will be completed in 2010-11 | Providing working facilities in the office for efficiency in the official work. | -- | 0.00 |  |  |  |
|  |  | Total (Building Projects) |  | -- | 43.00 |  |  |  |  |  |  |  |
|  |  | Grand Total (Art and Culture) |  | 503.00 | 735.00 |  |  | 424.26 | 482.67 |  |  |  |

Note: Plan Exp. indicated in Col. 8 includes Exp. on North East Activities.