| 1. | a). Secretariat Social Service | To modernize the accommodation for efficient functioning of the Ministry and also provide Information and Technology support. Maintenance of the office equipments and procurement of stationery. | 15.00 | 1.00 | Replacement of old and obsolete computers/photocopier in the Ministry. Digitization of old records lying in the Sections/Units for making clutter free working environment. Modernization of office accommodation. Renovation of 7 rooms (P&B, S&F Account cell, record room etc.) | Purchased 37 computers, 11 Multifunctional Printers and 9 photocopiers. Other office equipments too have been purchased on need basis. | 17.32 | 1.27 | Normally, non plan grant is used for administrative and establishment expenses. Proposal for purchase of new computers in pipeline |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | b). Central Secretariat Library (CSL) | To provide information and research services to Academicians, Research Scholars and Policy Planners. It is the main reference library for all purposes. | 1.95 | 2.40 | To replace out dated server, new high end server to be installed. Automation of circulation through bar coded tags to be introduced, training programmes for new technological developments to be conducted, purchased of books, selves and trolleys, improvement infrastructure and face lifting of R.K. Puram branch library, digitization work of GOI Gazettes/Notifications | Installation of Mike system in the conference hall was completed, modernization/ renovation work of CSL second floor hall and R.K. Puram Branch Library completed. 6000 books and other documents were purchased. Preservation work of rare books is under process in NRLC. Maintenance of AC Plant, AMC of computers and other* | 0.94 | 1.57 | Normally Non Plan Grant is used for administrative and establishment expenses. *peripherals, software maintenance, etc. Acquisition, reference services and processing of books continued. |
|  | Promotion of Art & Culture |  |  |  |  |  |  |  |  |
| 2. | Zonal Cultural Centre | Aims at the promotion of grassroots culture and cultural kinships which transcend territorial boundaries and to arouse and deepen awareness of local culture. | -- | 14.00 | Organizing various cultural programmes under different schemes, cultural exchange programmes etc. | To strengthen, promote and showcase the cultural activities at national and international level. | 0.00 | 23.45 |  |
| (i) | National Culture Exchange Programme | Exchange of artistes, musicians, performers & sculptors etc. between different regions within the country for the promotion of rich cultural heritage of India. |  |  | About 520 programmes were proposed to be organized benefiting a large number of artistes. | 510 programmes organized benefiting a large number of artistes deployed at fairs, festivals, cultural events to disseminate the cultural diversity across the country. |  |  |  |
| (ii) | Documentation | Documentation of various folk & tribal art forms particularly the vanishing art forms for their proper preservation |  |  | Various folk & tribal art forms, great masters of member states were proposed to be documented as per advice of Programme Committee and research oriented projects were proposed to be taken for publication. | More than 135 documentation works were taken up during 2010-11. |  |  |  |
| (iii) | Lok Tarang Folk Dance Festival | This festival is organized on the sidelines of Republic Day Celebrations during January each year for the promotion of our rich cultural heritage & national integration. |  |  | This festival provided a unique performance opportunity for the folk artistes from various parts of country at the national level. Besides this a large number of school children participate in R.D. Parade. | The ZCCs participated in R.D. Parade 2010-11 successfully. |  |  |  |
| (iv) | Kurukshetra Utsav | Celebrated on the occasion of Geeta Jayanti Samaroh at Kurukshetra- a sacred place related to Mahabharata |  |  | Suitable occasion for the promotion of Indian art & culture. Classical & folk artistes were proposed to be performed benefiting large number of people. Besides a large number of craft & persons were proposed to be given opportunity to display & sell their products. | NZCC organized Kurukshetra Utsav – Geeta Jayanti Samaroh 2011, Maharaslila Darshan etc. during Dec. 2011. |  |  |  |
| (v) | Guru Shishya Parampara | For the promotion & preservation of vanishing art forms. |  |  | Not only Gurus but Shishyas were proposed to be benefited. About 100 gurus with 1560 Shishyas were proposed to be benefited during the year. | Around 100 Gurus from various arts forms alongwith their 1550 shishyas were benefitted under the scheme. |  |  |  |
| (vi) | Theatre Rejuvenation | Providing an opportunity to the theatre artistes to stage plays & other theatre activities. Also interacting with each other on a common platform |  |  | About 135 theatre groups were proposed to stage their plays and a large number of people were proposed to be benefited in promoting the theatre. | ZCCs conducted various programmes viz. theatre shows, theatre festivals and workshops. Under this scheme, more than 88 plays were staged. |  |  |  |
| (vii) | Young Talent Artists Scheme | To recognize & encourage young talented artistes in various folk art forms. |  |  | About 100 folk artists were proposed to be selected & competitions proposed to be held involving sufficient number of upcoming artistes & public. | A large number of artistes benefitted under this Scheme |  |  |  |
| (viii) | Shilpgram | Shilpagrams established by ZCCs are playing very significant role in the promotion & preservation of Indian art & culture & providing platform to the talented artisans. The main objective is to boost the activities in Shilpgram/ Kalagrams. |  |  | A large number of artistes & artisans were proposed to be benefited. A large number of people were proposed to be made aware of our rich cultural heritage. | ZCCs organized Shilpagram Festival and other cultural events in their respective Shilpagrams involving a large number of artisan and craftsmen. |  |  |  |
| (ix) | Festival of the North East – OCTAVE | The objective of the festival of the North East is to help the people in general and artistes from the North East in particular to have a closure interaction with the main land. This will help in bridging the so-called gap between the North East and the mainland |  |  | Around 1200 artistes from North East including folk artistes, musicians, craftsmen etc. were proposed to perform in a series of programmes to be organized. | The North East Festival was held at Solan (HP) during March 2011. |  |  |  |
| 3. | Sangeet Natak Akademi, New Delhi | The Akademi acts at the national level for the promotion and growth of Indian music, dance and drama; for the maintenance of standards of training in the performing arts; for the revival, preservation, documentation and dissemination of materials relating to various forms of music, dance and drama and for the recognition of outstanding artists. | 7.10 | 11.50 | The Akademi devotes to the furtherance of the performing arts of India, and seeks to achieve this by arranging performances by renowned veterans as well as by talented artists of the younger generations through training programmes, award of scholarships and documentations. |  | 7.70 | 35.95 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Survey, Research, Documentation & Dissemination Publication and UNESCO – Convention on Intangible cultural Heritage – Implementation Project | Preservation and collection of recordings of rare traditions of Performing Arts, development of theoretical and academic knowledge of performing arts and publishing literature on performing arts. |  |  | 200 hrs of audio and video recordings, 10 audio CDs, 10 video CDs, 2200 photographs, 60 hrs of audio and video dubbing to be released. 3000 photographs to be added. Mapping project in 4 states. One national conference, Two regional seminars are proposed & 6 books, 4 journals and 12 news bulletins, and 1 Annual Report. 5 scholars for encyclopedia will be engaged. Survey for cultural mapping in 5 states,* | 52 hrs of audio and 444 hrs of video recordings, 11031 black & white and color photographs. 3 journals and and Hindi journal - Sangana published in March 2011. Akademi submitted 9 nomination dossiers (Qawwali by SNA; Turban Tying by WZCC; Kalamkari Painting by AP Govt; Jangam Gayan by NZCC; Chettikulangara Kumbha Bharati Kettukazhacha by Kerala Govt; Ranmale by Govt of Goa; Gaddi Jatar by IGNCA; Durga Puja by National Library, Kolkata; Nautanki by NSD) to UNESCO in Paris on 31.3.2011. |  |  | *making dossiers of 5 Elements, including 10 films on them, for Akademi’s candidature for Representative List. Organizing Indian presentation in ICH festival at UNSECO Headquarter in Paris. Physical achievement is based on the works given due priority by the SNA. |
| (ii) | National Museum of Performing Arts Purchase of land and construction of building Archive of Performing arts & Library and Archive Specialized Library on Performing Arts | Development of Akademi’s existing Museum - musical instruments, puppets, masks and other art objects into a national level museum of performing arts by acquiring a separate building / campus. To develop an exclusive archive of audio video and photographic records of performing arts of Akademi including a parallel archive in South Akademi by acquiring rare collections scattered in the country, besides the existing rich collection of Akademi’s own archive. To expand Akademi’s existing specialized library on performing arts and digitalizing its entire holding and make it available on line. |  |  | Preparation of 3 catalogues, acquisition of 110 objects, organization of 3 workshop, training programmes in instrument and mask making. Indexing, cataloguing and digitalization. Digitalization of 22000 clippings, 2200 monograph record, 5500 photographs | Allotment of 5 acres of land in Delhi by DDA for NMPA will be allotted during 2010-11. Training centers for instruments making started at Kolkata and Meerut. Center for acquisition of rare musical instruments has been setup at Kolkata for Eastern Region. So far we have acquired - musical instruments. International Museum Day (18 May 2010); an exhibition of puppets during CWG 2010 IGNCA, Delhi; Puppet exhibition at Kalakshetra, Guwahati. Ongoing project for archival. Digitalization of clippings and photographs completed. |  |  |  |
| (iii) | National Institutes and Centres of Akademi for Specialized fields/ forms of Akademi : Kathak Kendra, Akademi, Kutiyattam Centre, Kerala, Chhau Centre, Baripada / Jamshedpur, Other National Projects, Jawaharlal Nehru Manipur Dance Academy, Imphal and Sattriya Centre, Guwahati | To create Kathak dancers of professional standing through well specialized training course, To upgrade and develop Akademi’s project support to Kutiyattam, Upgradation and development of the ongoing project support to Chhau Dances of Eastern region, Development of training programmes in traditional land folk theatre forms of Akademi - Yakshagana of Karnataka, Bhagwat Mela of Tamilnadu, To create Manipuri dancers of professional standing through well specialized training course, Development of Akademi project support to Sattriya Dance and allied music and theatre traditions. |  |  | 3-4 new productions of dance seminar on Kathak, platform to over 200 artists. The ongoing project of Kutiyattam involving a number of projects training production, research and performance directly benefiting institutions, 200 artistes and scholars. The ongoing project of Support to Chhau Dances involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. Setting up of Centre for Music, Support to Traditional Folk Theatre Form, Bhagavatamela of Tamil Nadu and Support to Yakshagana of Karnataka. 3-4 new productions of dance dramas in a year, platform to over 200 artistes and creating new audience for Manipuri Dance in the country.* | Done 3 new productions by Repertory. Imparting Kathak training to 316 students. It is ongoing programme. Promotion of ancient art form from ‘Kutiyattam’ with financial support to Gurukulams all over Kerala. Presently imparting training to 58 trainees. Also organized outreach programmes in different areas within and outside Kerala. Regular training activities held in Baripada, Rairangpur, Seraikella in Chhau Dances, music and mask making. Centre for Puppetry started in Delhi To be achieved: Traditional Puppet Festival of Karnataka in February 2011; Putul Yatra, Guwahati (22 April - 1 May 2011) Done – New production. Ongoing Training programme. Sattriya Centre started at Guwahati in August 2008. Training support to Sattriya Dance & Music continued. @ |  |  | *The ongoing project on Sattriya Dance involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. @ Chamdyacha Bahulya (24 & 25 July, 10), Tolu Bomalatta (29 & 30 Dec 2010); Production oriented Kathputli Workshop Jan-April 2010; Putul Utsav, Delhi (19-27 Nov 2010); Putul Parampara, Bangalore (1-5 Dec 2010) in collaboration with Karnataka Janapada Academy. |
| (iv) | Festivals, Workshops and National Exhibitions 1SNA Festivals, Workshops & Exhibitions 2. Collaborative Programmes with State Akademis, Organizations, Central Govt. Organizations & Major Cultural Institutions and Sponsored Programme (New Scheme) 3. Regular Programme in Meghdoot Theatre Complex | To preserve, promote and development of performing arts traditions in live practice on regional and national levels and support exchange of ideas, concepts and techniques nationwide. |  |  | 20 festivals and Workshops in different cities. 50 activities in collaboration with State Government/Akademies and with Central organization and major cultural institutions in the field of performing arts. | Nritya Sangam, Kochi Natya Parampara, Kanchipuram (Sangeet Sangam, Guwahati. Number of programmes organized in collaboration with State Akademies/ Cultural Departments and leading cultural institutions. Appan, Dalhousie. Desh Parva (Festival of performing arts of India), Kulvarnika, Paths of Indian Music, Deshaj, Natya Darshan, Nritya Rupa - Dances of India, Delhi.* |  |  | * Tagore 150th celebration events- Rabindra Pranati, Delhi, Enek Sereng Parab, Birbhum WB, Nritya Natya Shantiniketan & Kolkata, Natyotsava, Raipur. |
| (v) | Awards, Honours and Prizes : SNA Fellowships and Awards (Akademi Ratna Sadasyata and Puraskar) Bismillah Khan Yuva Puraskar, Yuva Puraskar , | To recognize excellence and sustained contribution in performing arts and support eminent old artists. The Akademi awards fellowships and Akademi award (Fellowship is restricted 30 living person) Ustad Bismillah Khan Yuva Puraskar has been constituted for the young artists of below 35 years old. The award carries purse money of Rs. 25, 000 |  |  | 33 Akademi Awards, 5 Fellowships Yuva Puraskar to young artists | Presentation of annual Fellowships and Awards by Hon’ble President of India followed by a week-long festival on music, dance and drama held at Delhi (28-9-10; 15 to 21 October, 2010). Puraskar distribution ceremony and festival of award winning artists held at Delhi (10-17 August, 2010); |  |  |  |
| (vi) | # Cultural Exchange Programmes # 1 Inter – State Cultural Exchange Programme 2. Indo-Asian Cultural Exchange Programme (New Schemes) | National Integration through cultural exchanges |  |  | 20 exchanges involving 30 states/UTs. 6 programmes involving cultural exchange with abroad. | 1 Exchange involving 2 states/UTs. Held. Preliminary visit to Brazil in December 2009 for finalizing Festival of India International Art * |  |  | *Festival in Delhi sponsored organized by Forum for Beyond Borders |
| (vii) | # Training and Performs Support – Training and Preservation of Traditional, Folk & Tribal Performing Arts, # Promotion and assistance to Young Artists. Preservation of Puppetry, support to Children’s Theatre. |  |  |  | To hold 50 training programmes in different forms of performing arts. 5 festivals of young musicians/dancers in North, South, East and West & Central Zones. 4 festivals of young directors in different states, 2 theatre workshops, production subsidies. | 20 ongoing Training programmes in Nagaswaram, Pallavi, Pakhawaj, Sundari, Dhrupad, Sopana Sangeetam, Shehnai, Sarangi, Mayur Veena, Naqqara, Porattunatakam, Nattuvangam, Firikkal dance, Prahlad Natak Sangeet Pratibha, Udaipur. Rang Pratibha and Nritya Saranchana held in February, 2011. 33 institutions/ practitioners supported in Ramlila Vedic Chant and Kutiyattam. 470 Cultural institutions recommended financial support and 152 applications received for NE. 2 research works supported. 2 projects grants to individual supported. Grant to 30 periodicals/ journals supported@ |  |  | @under publication grant. Infrastructure development activities for renovation of open theatre complex and exhibition gallery for Maghdoot Theatre complex. Work for Rabindra Rangshala, New campus kathak Kendra, Development of Rabindra bhawan area in progress. |
| 4. | Lalit Kala Akademi | Promotion of visual and plastic arts | 6.15 | 7.00 | Normally, non plan grant is used for administrative and establishment expenses |  | 6.69 | 10.14 |  |
| (i) | Promotional activities in the field of visual & plastic art. Art Development/Art Promotion Cultural Exchange Proramme, Incoming Exhibition, National Exhibition of Art, Art Communication & | The main objectives of the Academy are to provide infrastructural facilities to the artist’s community for the development of art activities of the country especially in the field of contemporary art. |  |  | National Exhibition - 1 Exchange of Delegation Programmes under CEP-5 Outgoing Exhibition- 5 Incoming Exhibition - 4 Mobile Exhibition- 3 Camps and Workshops- 10 | Exhibitions: National Awardees Exhibition-1 Women Gender Exhibition-2 Mobile Exhibition-2 Curated Exhibition-2 Camps and Workshops-5 Artists in Residency-4 National Art Week-1 Video Art Week-1 Lectures/Seminar/FilmShow/Documentary / Artists on Art/Other on Art -32 Seminar on Ramkumar Records Management Workshop-1 Coomaraswamy Memorial Lecture-1 Exhibition in L.K.A.Gallery-102 Grants-in –aid to art organisations-6 Library Books Purchase-88 &10 New periodicals Archives CDs/DVD Purchase-22 (National & International Artists) Conservations/restoration- art works-430 XIX Commonwealth Games Prog. Exhibition -3 150th Birth Anniversary of Rabindranath Tagore- programme Art Colliquium-1 Seminar Rabindra Pranati-1 Scholarship-40 Publications Books-7 Reproduction-5 Regional Programme-34 Lecture/Filmshow-25 |  |  | North East Programme National Art Festival—1 National Art Conclave-1 Mobile Exhibition-5 Seminar-2 OCTAVE-1 North East Art Festival -1 North East Art Camp -4 Regional Art Fair-1 Regional Camp-2 Renovation Outer ambiance Rabindra Bhavan: Work in Progress & completed within 2-3 months. |
|  | Dissemination, Archives & Slide Expenses, Lecture & Seminar, Camps & Workshops H.Q. Grants to SA & Arts Organization , HQ Art Gallery & AC Expenses, Outgoing Exhibition, Special Exhibition, Survey of Folk, Tribal & traditional Art, conservation & Restoration , Art Festival other than North East Programmes , XIX Commonwealth Games, Programmes & Infrastructural Facilities , 150th Anniversary of Rabindranath Tagore- programme, Fellowships & Scholarships Publication & Documentations Regional Centres North East Prog. Establishment of New Regional Centres Kolkata, Grahi. |  |  |  | Lectures& Seminars-9 Exhibition in LKA Gallery- 250 Grant-in-aid to art organizations-25 Conservation/ Restoration art works- 150 12th Triennial India-1 XIX Commonwealth Games Pro. & Infrastructural Facilities Exhibition of SAARC Countries -1 Catalogue-1 Book on “Krida”-1 150th Birth Anniversary of Rabindranath Tagore –Pro. Exhibition of Tagore’s works-1 Publication of Tagore’s Essays-1 |  |  |  |  |
| 5. | Sahitya Akademi | To undertake publishing & promoting Indian literature in 24 languages. | 6.30 | 10.50 | Normally, non plan grant is used for administrative and establishment expenses. |  | 6.28 | 13.87 |  |
| (i) | Upgradation of Libraries and Information Services | To provide readers/ intellectuals the complete range of books and update basic information about writers and literary activities in India at one place, make documentary films on eminent writers and scholars in the field of literature with modern archive unit of visuals. |  |  | Purchase of books in 24 languages will continue. The retro-conversion of bibliographic data in respect of different language sections is proposed. Upgradation of the Akademi’s English web site and the Hindi web site will be launched. Development of Archive Unit by adding modern equipments will continue. Ten Documentary films on writers will be made. Initial work of cataloguing of audio tapes of various* | Purchase of books in 24 languages including foreign publications continued. The retro-conversion of bibliographic data in different languages taken up in order to their priority. Efforts have been made to create more and more catalogues. The catalogues already made, have been added to Akademi’s Hindi and English websites. And will be digitized 10 documentary films already started. |  |  | *programmes/seminars is in the process. 10 documentary films on writers will be made. The work on revised version of Who’s Who of Indian Writer has already been started. |
| (ii) | ### Publication Schemes | The scheme to full fill the basic objective of the Akademi dissemination of Indian Literature and making available to multilingual societies of Indian Literary masterpieces from other language into their own language, histories of literature, monographs on Indian Writers, translation of important Indian and foreign classics, anthologies of poetry, short-stories, one-act plays, literary essays etc. |  |  | To publish around 400 books in all the 24 languages recognized by the Akademi. The publication of bi-monthly journals Samkaleen Bharatiya Sahitya (Hindi) and Indian Literature (English) and a half yearly journal Sanskrit Pratibha (Sanskrit) to continue. Publication of revised editions of Encyclopedia of Indian literature, new series of National Bibliography of Indian literature 1954-2000 to be completed. The other programmes under publication scheme will continue.* | A mew publication series named ‘Katha Bharati’ in collaboration with Central Institute of Indian languages has been launched. The second series of National Bibliography of Indian Literature (1954-2000) covering all books of literary merit and abiding values of Bengali, Dogri, Kannada, Maithil, Malayalam, Manipur, Nepali, Oriya, Rajasthani, Tamil and Telugu have already submitted their entries. |  |  | * The entries in the remaining languages are expected by the end of this financial year. It is proposed to take up the printing work in four phases. The authors/writers paid royalty on the basis of actual sale of books. |
| (iii) | Literary functions and programme Modernization and improvement of administrative functioning | To celebrate centenaries of great writers, hold regional, national and international seminars, writers camps, workshops, symposiums etc., provide writers a forum for their periodical gathering by organizing meet the author, men and books etc. |  |  | The Akademi will organize literary programmes in various fields. The programmes will include writers’ workshops, centenary celebrations, symposiums, Memorial meets, seminars etc.. Akademi would hold more than 400 programmes in the above categories throughout the country. | Akademi hold various Literary Forum Meetings, Men & Books, Asmita, Kavi Sandhi, Kavya Sandhya, Mulakat, Kath Sandhi, Celebration of centenaries of important writers, organizing of seminars at regional, national and international levels, writers camps and workshops at national and international levels organized* |  |  | *Computerization of the Akademi as a whole upgraded with latest technology, specifically in the areas of library services, database bibliography, cataloguing, indexing and accessioning. |
| (iv) | Awards to writers 150th Birth Anniversary of Rabindranath Tagore | To enable young and old writers in Indian language to visit other parts than their own, send Indian writers and host foreign writer delegation under Cultural Exchange Programmes, to give award to literary works which merit appreciation and encouragement in all 24 Indian languages recognized by the Akademi, give honorary fellowships to eminent writers in recognition of their contribution to Indian Literature. |  |  | Young writers will be given Travel Grant under the scheme of the Akademi to visit other parts of the country than their own. The Akademi will participate in different Cultural Exchange Programmes. The Annual Awards will be given to writers in 24 Indian languages recognized by the Akademi. The payment of Royalty and remunerations to authors/ copyright holders will be made. Grant under the scheme for writers in Residence will continue. The living fellows, eminent writers etc. will be offered financial aid under the scheme. | The scheme provides grant to 100 young writers to enable them to visit their counterparts in different parts of the country. The foreign writers/delegations will be hosted under Cultural Exchange Programme with whom India has bilateral relations. The Indian writers/delegation shall also visit the foreign countries on reciprocal basis. It is expected to host nearly four writers’ delegation and around four Indian writers delegation shall visit foreign countries. Akademi also will actively participate in various Indian Festivals, collaboration and Books Fairs at various countries. * |  |  | * The annual Sahitya Akademi awards in 24 Indian languages will continue. Akademi’s assistance to other literary institutions and the State Akademi shall be continued on the basis of Akademi’s programmes and activities. It conducted various literary programmes including seminars, exhibition, etc. as a part of 150th Birth Anniversary of Guru Raabindranath Tagore. |
| (v) | Promotion of Akademi Publications\ Book Exhibitions | To advertise Akademi publications through literary journals, organize and participate in book exhibitions at regional, national and international level. |  |  | To achieve a sell target of Rs.3.00 cr., the Akademi will participate in various book exhibitions at National/ Regional / International levels. A part from this, it will also participate in provisional city/town book exhibitions. Also to organize book exhibitions during seminars/literary functions. | The Akademi has participated book exhibitions, book fairs/melas at district/city/town level. The book exhibitions are also the part of centenary celebrations/seminars/literary functions held by the Akademi. Akademi shall participated in around 90 books exhibitions at different levels.* |  |  | *Akademi also likely to take participate in the International Book Fair where India is a Guest of Honour Country. |
| (vi) | ##### Translation schemes, ##### Regional Literature Studies Projects, ##### Development of Languages, Fellowship: Coomara Swamy and Premchand, ##### National Bibliography of Translation in Indian Languages, ##### Encyclopedia of Indian Poetics, Great Books of India etc. | Translation is the basic activity of the Akademi. Translation centre “SABDANA” to make arrangements for training of translators and train the practicing translators by conducting workshops, to do the inter-lingual research and translation, prepare a register of translators and identify titles for translations and their publications into other Indian languages and into foreign languages. |  |  | The Translation Prizes in 24 languages recognized by the Akademi will continue. The work on the scheme” Katha Bharati” launched with Central Institute of Indian Languages (CIIL), Mysore will continue. More data will be provided to CIIL, Hyderabad for incorporation on their web site. . The Centers will conduct Translation Workshops in languages recognized by the Akademi as well as un-recognized languages .New Translation centers will be launched in Western and Northern regions. | The Translation Centre “SABDANA” is source of encouragement and training to the practicing translator to undertake inter-lingual research, translation of foreign classics into Indian. Bangalore Centre has already published quiet a few medieval texts in translation in English and South Indian Languages. The translation prizes to best translation in 24 languages shall continue. * |  |  | *It is estimated to translate and publish around 30 books. The translation of Children literature from one language to another shall also continue to make available the works of one language to the readers of another language. |
| 6. | Festival of India | To organize major cultural festivals in selected foreign countries for achieving better understanding and cooperation | 4.10 | -- | By holding art/museums exhibitions, literary seminars, theatre / performances / seminars / workshops. | It was decided to organize a good number of Festivals/ Days of India’s etc. in foreign countries and vice-versa to be taken place under CEPs. - Festival of India in Kazakhstan. - Payment to SNA in connection with shared history festival. | 1.32 | 0.00 |  |
| 7. | Indira Gandhi National Centre for the Arts (IGNCA) | IGNCA was established to commemorate the memory of the Former Prime Minister Late Smt. Indira Gandhi. It is envisioned as a centre for research, academic pursuit and dissemination in the field of the arts. | -- | 25.00 |  |  | 0.00 | 24.55 |  |
| (i) | Promotion of Multidisciplinary Research and Critical Dialogue among diverse Arts. | Enlarge its programme of research and publication of fundamental texts, reference works, glossaries, dictionaries, encyclopedia, comparative history of Indian arts, thesaurus of fundamental terms, inter-dialect and inter-disciplinary glossaries and dictionaries, explore relationships of arts and science, dimensions and explore relationship between arts of India and the world. Special focus on the North-East and its cultural dimensions. |  |  | Studies on the following dimensions: (a) Multiple levels of Identity and their manifestation in Arts (b) Language and Cultural Diversity (c) Wisdom Tradition, Ecology, Resource Management and Sustainable Development (d) Religious Identities, Confluence of Traditions and Composite Cultures (e)Inter-cultural Dialogue (f)Contribution of Women to Indian Art and Culture | (a)Publication of critical editions of fundamental texts, monographs on tribal and folk culture, republication of texts by eminent scholars (b) Research and Field studies (c) Audio-video documentation (d) Conference, seminars and workshops (e) Exhibition and multi-media events. (f) Production of films, CDs, audio-video recordings. |  |  |  |
| (ii) | Resource augmentation and modernization | Augment the repository of primary source material - written, oral, auditory, audio-visual and pictorial of the IGNCA, to serve as the national centre for the arts and culture and support research and publication activities of its other in-house divisions, Upgrade and install modern management and technological tools and systems, Enhance reproduction of source materials in different regional centers under IGNCA, Upgrade technology and set-up permanent galleries for display and exhibition. |  |  | # (a) Purchase of # (i) Books (ii) Journals (iii) Rare books (iv) Personal collections (b) Collection of slides through in-house digital photography. and Purchase of slides (c) Microfilming of Manuscripts (d) Acquisition of Cultural archival material (e) Modernization of (i) Digital Library Information System (ii) Annonated Bibliography Index (iii) Reprographic unit (iv) Audio-visual equipments (f) Cultural Informatics (g) Creation of Galleries | (i) Addition of books, periodicals, journals in the Library (ii) Modernization of the Library services State-of-art equipments in Reprography, Computer centre and media production (iii) Setting up of three galleries for display of arts and crafts (iv) Digitization of manuscripts, internal repository etc. (v) Operationalising e-governance in the cultural field (vi) Collection of archival material from the North-East. |  |  |  |
| (iii) | Cultural Cartography & Modernization of equipments in IGNCA | Map ecological and cultural profile of diverse communities of India along with specific aspects of art and crafts traditions prevalent among them. |  |  | (i) Creation of a cell (ii) Research and field study (iii) Preparation of Atlas Procure photocopiers, fax machines, tables, almirahs, establish workstations, and provide Information Technology tools and equipments. | Installation of modern equipments Enhancement of work output and better working conditions. (i) Training and capacity building (ii) Publication (iii) Seminars, conferences and workshops |  |  | Ongoing programme and will be completed before 31st March, 2011 |
| 8. | National School of Drama, New Delhi | Promote Theatre and to conduct theatre training programme | 6.80 | 13.00 | Normally non- plan grant is used for administrative and establishment expenses. |  | 7.30 | 28.65 |  |
| (i) | Theatre workshop and part time courses in regions and locally and other training courses for faculty and staff. | To benefit a vast majority of theatre enthusiasts in various states with diverse languages and cultural backgrounds and to create theatre awareness in them. |  |  | Intensive Theatre Workshop- 2, Collaborative Theatre Workshop- 40, Assistance to Theatre Workshop- 10, Part Time Course- 2, Refresher Course- 2, Short term Workshop- 8, Intensive Theatre Workshop- 12, * | 84 theatre workshops were conducted and 10 workshops/ training courses for children were conducted in Delhi and Outside. |  |  | * Acting Theatre Workshop-2 Technical Theatre Workshop- 2, Theatre Music Workshop- 2, Theatre Design Workshop-2 |
| (ii) | Organizing of training courses/ Children Theatre Workshops in Delhi and outside Delhi | To develop personality and give exposure to children in terms of their expressions and confidence. |  |  | Children theatre Workshops in Delhi/ Outside Delhi- 42, Production Oriented Children Theatre workshop- 36 , Theatre workshop with SC/ST Children-2, Short Term Theatre Workshop- 4 | 10 workshops in Delhi and Outside Delhi were held. |  |  |  |
| (iii) | Organizing of collaborative programme of traditional group in villages and theatre festival/ exhibition. | Providing 3-year Advanced Dramatic Training Course and to acquaint the students from theatre from existing in different regions of the country. |  |  | 2nd Year Students production – 4, 3rd Year students production – 4, Final year production – 5, 1st year & 2nd year students scene work Summer intensive workshop- 1, Winter workshop -1, Display Exhibition-8 & Theatre Performances-64 | 2nd Year students prod. 4 3rd year students’ production 4 Final year diploma production 6, 1st & 2nd year student’s scene work 5 Summer intensive workshop Winter intensive workshops Display exhibition Overseas prod. |  |  |  |
| (iv) | Promotion of Folk, Tribal Arts and Educational Tours | To familiarize the students with the existing folk and tribal art relating to theatrical and music forms. |  |  | Workshop with Traditional Group-1 & Educational tour for 1st 2nd 3rd years students-5 | Educational tour to Agra and Fatehpuri Sikri & Aurangabad were organized for the benefit of students of the School. Workshop with traditional artists was held at Mathura. |  |  |  |
| (v) | Formation of Repertory Company of Adults performing for children | Aim to promote theatrical performances for children. |  |  | Production of new/old plays for children-2, Summer Theatre workshop-2, Children workshop- 2, Sunday Club workshop performances-2, Workshop & Play in schools-40, Teacher’s workshop - 2 Other Festival Exhibition- 1 | School shows in Delhi/ NCR- 38; Summer theatre workshops -7; Summer workshop in 4 District of Assam and Meghalaya (1 District); Sunday club with children (550 children participated); new production (Adal Badal)- 13 shows; Sunday club festival – 12 shwos. |  |  |  |
| (vi) | Extension of Repertory Company National Theatre Festival & Parallel theatre Festival National children Theatre Festival and Bal Sangam/ Jashne-achpan | Dissemination of Indian plays in India and Outside the country. |  |  | Performances of play in Delhi-100, Outside Delhi-50, Shows of new productions-24, shows in summer festival-1, Shows in winter festival-1, Participation in BRM collaborative performance with groups- 25 | 1. Summer Theatre Festival 2010 –shows of 8 plays. 33 2.Performances staged in Delhi under sponsorship (plays) 8 3.Weekend Theatre programmes 3 4.Participation in BRM – 2011 shows of plays 3 5.Participation in Nandikar Theatre festival, Kolkata (Shows of plays) 2 6. New plays produced 4 7. Shows of old plays. 80. National theatre festival BRM 2010 with Indian and foreign theatre groups was held successfully in January 2011. 81 plays were performed out of which * |  |  | *23 were from foreign countries alongside APB Drama school festival was held. Exhibition on Actors titled “Abhi- Vyakti” and the exhibition on the “Footsbarn company”. |
| 9. | ### National Gallery of Modern Art (NGMA) | ### To create an understanding and sensitivity among the Indian public towards visual and plastic arts in general and to promote the development of contemporary art in particular. | ### 3.85 | ### 7.00 | Normally non- plan grant is used for administrative and establishment expenses. |  | ### 3.50 | ### 11.52 |  |
| i. | Up-gradation, Modernization and maintenance of museum | To promote development of contemporary art at par with international level. |  |  | ### Maintenance of a well organized museum of Modern Art with excellent display of art objects at par with International Standards at New Delhi, Mumbai and Bangaluru. | In addition to maintaining a well displayed gallery at New Delhi , Mumbai and Bangaluru, 16 Special exhibitions were held at Delhi, Mumbai & Bangaluru during the year both of Indian contemporary artists and also of foreign Artist under cultural exchange Programmes. Besides, from exhibitions regarding celebration of 150th birth anniversary were held in Berlin, New Your, Korea and London, according to press news, dated December,2011 from London’s weekly news, the Independent, the exhibition was awarded 4 Stars out of 5, which shows the importance given to the Tagore Exhibition in London. More than 650 Films shows on art were organized in NGMA for general public and students groups. Conducted tours were organized for 80 schools in an around Delhi for the benefit of school children. 150 Children attended the Art Sketch Club every Sunday at the museum premises.* |  |  | * 283 Children attended the Summer Art workshop organized in the month of May –June 2009 at new Delhi and awarded certificates. ### Conducted tours for various sponsored groups of Indian & foreign delegation. Press conferences, Press preview were organized. About 23,000 books on painting, sculpture, graphics etc. were collected, 32 important magazines and journals on Indian and Foreign were subscribed. |
| 10. | Asiatic Society Kolkata | Declared as an institution of national importance. To launch research projects on language, literature, culture and socio-economical aspects. | 7.70 | 8.00 | ### Normally, non plan grant is used for administrative and establishment expenses. |  | 9.22 | 5.13 |  |
| (i) | Development of Library System | To establish build, maintain institutions for promotion of research in humanities and sciences |  |  | Acquire books, journal etc. its preservation and maintenance to cater readers with books and references. Book Acquisition-2500 vol. Subscription to serials-300 titles* | The targets fixed for various activities have been continuing. 9955 male and female readers were served by providing library facilities including 165 foreign readers. |  |  | Cataloguing and documentation of - 4000 Books and 6000 journals Binding/Mending- 2600 books & Journals to be undertaken |
| (ii) | Development of Museum & User facility | To preserve manuscripts which has a rich collection of archival records, coins inscriptions and very valuable lithographs. |  |  | Cataloguing of MSS -4000 books & journals, Documentation of MSS, archival Material etc.– 6000 books and journals. | 544 Indian and 194 foreign visitors/research scholars visited in the library. |  |  | In depth study for development of NE Cultural activities were taken up. Strengthened and maintain preservation of books/ MMS artifacts. |
| (iii) | Conservation & Preservation of rare books, MSS & Other document | To take effective measure for the preservation of brittle and fragile manuscripts, rare books and other ancient objects kept in the Museum and Library of Society. |  |  | Restoration of 30000 sheets of Manuscript in forms of film, plate etc., and 2500 Lithographic prints/sheets to be restored. | Preservation of rare-books, MSS, paintings, etc. was taken up and documentation of rare books/ MSS carried out. |  |  |  |
| (iv) | Publication Programme | To bring out the publication of high academic standard for which the society is known to the world of scholars. Particular emphasis is made on the publication of books under the Bibliotheca Indica series. |  |  | Publication of 15 Books, 4 Journals, 10 M. bulletins & 4 Booklets to be brought out during the year. | Publication of 7 books, 7 re-print of books, 4 journals, 8 booklets and 10 monthly bulletins were taken up during the year. |  |  |  |
| (v) | Augmentation of Research | Research work in different areas, imparting training, conduction seminars, lectures, workshops etc. |  |  | Research in work in different areas, imparting training and conducting seminars and workshops – 50 project, 15 seminars, 35 lectures 5 exhibitions/workshops | 36 projects, 14 external projects on various subjects, 5 seminars, 32 lectures & 3 exhibition/ workshop were conducted/ taken up. |  |  | 2 Workshops on NE were conducted. |
| 11. | Centre for Cultural Resources and Training, New Delhi | Aims to improve the quality of life through the medium of Academies working in the field of linking education with culture. | 3.13 | 10.00 | Normally, non plan grant is used for administrative and establishment expenses. |  | 3.42 | 15.99 |  |
| (i) | Propagation of Culture among school students | To conduct a variety of in-service Teacher Training Programmes such as Orientation Training Programmes, workshops, Seminars, Refresher course etc. in different parts of the country for school teachers, teacher educators etc.organisation of educational activities for school students and children belonging to governmental and non-governmental organizations. Workshops for children of resettlement and basti colonies and for physically challenged students. |  |  | 4000 Teachers/ Teacher Educators to be trained in various training Programmes. 4000 Teachers to be trained through Trainers. 30000 Students to be trained under Community and Extension Programmes. 200 Cultural Clubs to be setup in various states in the country.* | 3747 Teachers/Teacher Educators have been trained in various Training Programmes. 4160 Teachers trained through Trainers. 49603 Students have been trained. 194 Cultural Clubs have been setup in various states in the country. 40 Lectures on Indian Art and Culture to be organized. 32 Publications including reprints have been published. 954 Educational kits produced. |  |  |  |
| (ii) | Cultural Talent Search Scholarship Scheme (CTSS) | Aims at providing facilities by awarding scholarship to study the performing and other arts to outstanding young children in the age group of 10-14 years. |  |  | 500 Scholarships to be awarded under Cultural Talent Search Scholarships Scheme 4 Cultural festival to be organized for scholarship holders. | 500 Scholarships have been awarded covering all parts of country including the north-east. 4 Cultural festivals have been organized for scholarship holders. |  |  | The awardees are selected on the recommendations of Central Selection Committee and Regional Selection Committees. |
| 12. | Financial Assistance for Professional Groups and Individuals for specified performing art projects. (Dance, Drama and Theatre Ensembles) | To promote the Guru Sishya Parampara and support organizations / individuals working in the field of Performing Arts. | 1.55 | 25.00 | There are no fixed targets individuals/organizations involved in Cultural activities and are assisted on the basis of receipt of proposals and recommendations of the Expert Committee. | 775 individuals /organizations have been assisted. Ceiling of production grant was increased from Rs. 1 lakh to Rs. 5 lakh. | 0.73 | 30.16 | Includes 30% provision towards pro-women, and 20% provision for ST population |
| 13. | Gandhi Peace Prize | Government of India announced institution of an annual international Gandhi Peace Prize for social, economic and political transformation through non-violence and other Gandhian methods as a part of celebration of 125th birth anniversary of Mahatma Gandhi. | 1.55 | -- | The recipient of this prize is selected by the Jury headed by Hon’ble Prime Minister in accordance with the prescribed code of procedure. | The nomination for GPP was made for declaration during the year but no candidate could be selected at the last stage. Synopsis on each nominee were prepared and compiled in a booklet, which was then put up to the Jury for selection of awardees. | 0.01 | 0.00 |  |
| 14. | National Culture Fund (NCF) | NCF objective is to develop Public Private Partnerships for the protection, conservation and development of heritage. | -- | 0.01 | Various proposals have been received for seeking financial assistance through different organizations/individuals including BharatBala Productions Pvt. Ltd., OSIAN’s Art Society, M/s. Darpana, Prasiddha Foundation, ONGC, INTACH etc. for holding various festivals celebration, film productions and many others categories of events under Tangible and Intangible Cultural Heritage. | - Replacement of plastic case around the chariot at the entrance of National Museum with reinforced glass- project sponsored by ONGC, NSC and National Museum. - Conservation of Ancient Shiv Mandir (Amber nath)- by Nagrik Seva Mandal (Ambernath)- (work in progress). - Renovation and maintenance of Ahom monuments by ASI and M/s ONGC- (work in progress). - Adoption of Haazardurai Palace (West Bengal) - by ASI & SBI (Kolkata). - Completed project with M/s Saarth- a film on Kishori Amonkar Classical singer by Shri. Amol Palekar- by ONGC and MEA. - Film on Smt. Mirinalini Sarabhai Classical Dancer- by M/s DARPANA (Ahmadabad). - Conservation of photo archives of post independence period- M/s India Photo Archive* | 0.00 | 0.01 | *Foundation (work in progress). - Organizing Virasat Festival (Dehradun) by ONGC & REACH Foundation. - Construction of Toilets at Shore Temple (Mahabali puram)- (Work in progress). - Preparation of detailed projects reports on Sri. Ranganath Venugopal Mandir (old) (Pushkar) by Sri. Ranganath Venugopal Mandir and NCF. Apart from these projects, some ICH projects are in pipeline. |
| 15. | Centenaries/ Anniversaries Celebration | To celebrate the Centenary/Anniversary of important personalities and events |  |  |  |  |  |  |  |
| 15.1 | Celebration of 2550th Anniversary of Mahaparinirvana of Lord Buddha | Construction of school Block by Buddha Cultural Foundation Monastic School, Tawang, Arunachal Pradesh. | 0.45 | -- | Construction work of building school block undertaken. | Out of approved amount of Rs. 1.50 crore, second installment of grant of Rs. 0.45 crore was released. | 0.45 | 0.00 |  |
| 15.2 | Celebration of Birth Centenary of Lal Bahadur Shastri | In order to create a Chair in the Institute of Defence Studies and Analysis, N.Delhi in the name of Shri Lal Bahadur Shastri. | 0.05 | 2.00 | Opening of two new technical institutes at Indore and Manda for men & women separately will be taken up during the period. Maintenance grant to LBSMT. | An amount of Rs.2.00 cr. was released for the said purpose. The chair has been set up during 2007-08. | 0.05 | 2.00 |  |
| 15.3 | Celebration of 150th anniversary of 1st war of independence, 1857 | Undertaking the residual work as approved by the NIC. | 1.00 | 10.00 | The residual item of work/ programmes as approved by NIC for establishment of Chair are to be undertaken. | Funds released for the establishment of five commemorative Chairs to the respective Universities and projects undertaken by Punjab Govt. and ITDC. | 0.97 | 9.00 | Completion of the projects depends upon the availability of funds. |
| 15.4 | Financial support to Khalsa Heritage Project | To highlight salient aspects of the important events relating to Khalsa Heritage in order to infuse in the public, particularly the young, the spirit of these great events. | -- | 8.00 | Funds for Khalsa Heritage Project are released to Punjab Govt. as 1/3rd share of Central Govt. (Plan) as reimbursement of the amount spent on the project on quarterly basis. | The matching grant of Rs. 3.53 crore was released to the Govt. of Punjab as a share of Central Govt. | 0.00 | 3.53 |  |
| 15.5 | Ter-Centenary of Guru-ta-Gaddi | Infrastructural development of Anand Pur Sahib and Talwandi Sabo, as a part of commemoration. | 0.01 | -- | Infrastructural development of Anand Pur Sahib and Talwandi Sabo, as a part of commemoration. | Infrastructural development of Anandpur Sahib and Talwandi Sabo as a part of commemoration is being undertaken. | 63.20 | 0.00 | Rs.83.20 cr. as a ‘cash outgo’ was approved in the 1st Supplementary 2010 |
| 16. | Other Schemes/ Institutions |  |  |  |  |  |  |  |  |
| a) | Central Institute of Higher Tibetan Studies, Sarnath | Established with a view to educating the youth of Tibet and Himalayan border areas of India | 6.90 | 5.80 | Normally non plan grant is used for administrative and establishment expenses |  | 9.36 | 6.28 |  |
| (i) | Development of Library | ## 1. To Preserve Tibetan culture and tradition. ## 2. To restore ancient Indian sciences and literature preserved in the Tibetan languages. |  |  | Purchase of 1500 books, and computer/ equipments will be purchased. | Purchased 2646 books & Journals, e-documents and some equipments purchased etc. |  |  |  |
| (ii) | Publication and Printing. | To provide printed material on Tibetan culture for scholars and others |  |  | 12 books to be published. | 12 books & Journals, E-documents and some equip purchased published. |  |  |  |
| (iii) | Rare Buddhist Text Research, Establishment of Language & Laboratory, Promotion of Intellectual contact, exchange of scholar conferences and seminars | To offer the alternative educational facilities to the students of Indian border area who formerly availed the opportunity of receiving higher education in Tibet |  |  | 1st and 2nd Bi-annual journal to be published and 2 sites to be visited for research purposes. Various other programmes will be carried out for promotion of Buddhist/Tibetan languages and culture. | One annual journal was published and one workshop organized, 26 chapters of rare Buddhist text were edited and survey of manuscript conducted. Translated and restored Grantha’s 1140 pages. Ayurveda Kosha- 5700 words entry, Nama Kosha- 2500, Vinaya Kosha- 3000 words and other Sanskrit Tibetan or Sanskrit Jyotish words were added in the encyclopedia. |  |  | Re-editing work of MBSST Darbhanga Institute under process. International/ National seminars/ symposium organized. |
| (b) | Central Institute of Buddhist Studies, Leh. | To develop multifaceted personality of the students through inculcation of the wisdom of Buddhist literature as well as to familiarize them with modern subjects to acquaint them with collection,conservation, translation, publication of rare manuscripts and research works relevant to Buddhist Studies etc. | 4.20 | 8.50 |  |  | 5.21 | 7.30 | Normally, non plan grant is used for administrative and establishment expenses. |
| i. | Construction of Building | Construction of auditorium, Guest House, 20 Residential Quarters and Building for DPS, Zanskar. |  |  | Construction of physical infrastructure for CIBS and DPS Zanskar. | Construction of physical infrastructure for CIBS and DPS Zanskar is under progress. |  |  | Construction is going through CPWD and State PWD in a phased manner |
| ii. | Provision for existing Gonpa/ Nunnery school. Publication of rare books/manuscripts, preservation of traditional Ladakhi arts and culture. Compilation of Encyclopedia of Himalayan Buddhist Culture. | To support educational activities in the number of Gonpas by providing teachers and stipend to the students. |  |  | Plan activities for 50 feeder schools in different monasteries of Ladakh and a branch at Zanskar Kargil to preserve and promote monastic system of education. These works will be undertaken during the year. | 767 students provided cultural education along with modern education. 594 books and 55 type of journals/ magazines acquired and added to library collection. Plan activities for these feeder schools have been continuing. Conferment of Deemed to be University status to CIBS. Provided fellowships for research scholars. |  |  | Acharaya equitant to M.A., Shastri equitant to B.A., Madhyama equitant to 10+2, Ph.d. 6 year diploma/ degree Bhot Medical science, traditional Culture, painting and wood carving. |
| (c) | Gandhi Smriti and Darshan Samiti | To propagate the life, mission and thoughts of Mahatma Gandhi by organizing various socio – educational and cultural programmes. | 4.20 | 10.00 | Normally, non plan grant is used for administrative and establishment expenses. |  | 3.82 | 8.85 |  |
|  | Promotional Activities 1. Regular programme with educational institutions a) Taking Gandhi to Schools b)Gandhi Summer School 2.Programmes for youth 3.Programmes for Women 4.Commemorative programmes 5.Regular Programmes in GSDS | To plan and carry on activities for the promotion of Mahatma Gandhi’s ideals and of national causes identified by him. |  |  | a)Children programms with educational institutions to reach out more than 20,000 students in India and abroad. b)Gandhi Summer School in Delhi and other states as well as for disadvantaged children. Youth to reach out more than 10000 youths. Programmes for women to cover about 5000 women. Programme for awareness to reach out 10000 people. About 2000 underprivileged children to be trained. | Various programmes for students/youth including children’s and women were organized in different parts of the States/ UTs of the country for constructive works and taking forward the message of Mahatma Gandhi including empowerment of women and fight against violence on women. Two publications i.e. Annual Report and Anasakti Darshan were brought out. Publication of messages of Mahatma Gandhi & its Social issues. |  |  | 10,000 youths and 5000 women across the country participated in reaching out programmes. More than 10,000 people were read out under commemorative progarammes. 2,000 under privileged people attended the programmes. |
|  | Dissemination, Infrastructure, Programmes in NE | To undertake such activities as will lead to greater understanding of Mahatma Gandhi’s life, work and thoughts. |  |  | The following publication will be brought out – 1.Annual Report 2.The Yamuna, GSDS Children’s newspaper 3. Anasakti Darshan New books, equipments to be procured to strengthen Smiti infrastructure. | Through these publications the message of Mahatma Gandhi and other social issues were taken up reaching nearly 20,000 children/youth and other cross section of the society both directly and indirectly. |  |  | The Samiti read out to all states of the NE States on women empowerment, occasional training and constructive work. |
| (d) | Nava Nalanda Mahavihara, Nalanda, Bihar | To revive past glories of the ancient university of Nalanda and to give post graduate studies and research in Pali language and literature and Buddhology. | 1.58 | 3.20 | Normally, non plan grant is used for administrative and establishment expenses. |  | 2.48 | 2.20 |  |
| i. | Improvement & Development of Library Service | Developing the library with purchase of new books on Pali, Buddhism Philosophy, Ancient History, Culture and Architect, Hindi, English, Sanskrit etc. |  |  | Over 1000 of books are expected to be purchased on Pali, Buddhist Philosophy, Ancient History etc. | Around 1000 number of books were purchased for developing the library collection. |  |  |  |
| ii. | Development of Xuan Zang Memorial Hall | To provide creative works, as paintings, murals inside and outside the XZM and on landscaping etc. |  |  | Regular maintenance and development works to be taken up besides there is a proposal to construct a separate building for housing and preserving Xuan Zang relics. | Various paintings and morals connected with the life of Xuan Zang were added to the Memorial. |  |  |  |
| iii. | Cultural Exchange programme, workshops seminars & conferences | Promotion and dissemination of Buddhist thoughts by organizing seminars, workshop etc. on inter-institution exchange basis. |  |  | Academic and cultural material collected from workshops, seminars etc. is printed and is made available to scholars and researchers. | Apart from several workshops and National Seminars on relation in Linguistic, Social and Philosophical Perspective was organized. |  |  | Proceedings of Living Buddhism in North East India will also come in 2010-11. |
| iv. | (i) Annual foundation day & ceremony & special convocation (ii) Award of scholarship to the meritorious students of Mahavihara | To commemorate the foundation day of the NNM on the 20th Nov. each year and special convocation. To support the meritorious students |  |  | This is a regular feature of the Mahavihara to commemorate the foundation day. Indian and foreign students are to be benefited. | Erudite scholars from inter-state area, high official dignitaries, cultural programmes to grace the occasion. Indian and foreign students are to benefited. |  |  |  |
| v. | Printing of old and new publication and documentation exhibition | Main objective is to print and reprint of the proceedings of the earlier seminars and other research oriented materials and to promote & dissemination of Lord Buddha’s teachings by holding exhibition & its documentation |  |  | Printing of Annual & Audit Repot, proceeding of the seminar & re-print of old books will be taken up. A exhibition on the theme of Nalanda & Buddhism will be exhibited. | Printing of proceeding of National Seminars, Commemorative volume and Annual Report etc. A Bihar’s Indic Spiritual, Cultural Festival was organized. |  |  |  |
| vi. | Pali Hindi Dictionary Project | Scheme aims at preparing an exclusive Pali-Hindi Dictionary |  |  | Vol.II of Pali Hindi Dictionary is expected to come out in 2010-11. | With approval of BOM three reputed scholars on fixed remuneration are employed. To assist them three more assistants are employed. |  |  |  |
| (e) | Maulana Abul Kalam Azad Institute of Asian Studies, Kolkata | To conduct research and training of life and works of Maulana Abul Kalam Azad with the study of social culture, political and economic movement in Asia from the middle of the 19th century. | 1.05 | 6.50 |  |  | 0.80 | 5.25 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Research project including North East/ fellowship and other promotional activities. | To carryout research activities and revelation of political, social & economic changes in India and other Asian countries. |  |  | 24 Fellows undertook research on various areas including North-East India. Basic services were available at the Salt Lake campus of MAKAIAS. Foreign Visits & seminars at National & International level were planned on wide scale. 14 members of regular staff did the establishment work of this Institute | Regular submission of research reports & research papers from 24 fellows who were working on projects. The Library of the Institute is functions from the Salt Lake campus of MAKAIAS, where there is ample space. The Maulana Azad Library is located in the Heritage The Institute organized 3 national building and 8 international Seminars* |  |  | */ Symposium exhibitions. The Institute also collaborated with other Universities/ Institutions/ Organizations in organizing Seminars/ Conferences both national and international |
| (ii) | Publications \Acquisitions of Book | To publish the research work of the scholars in different subject fields. |  |  | Publication of 10 Books & one journal. 1 journal in press. | Contribution to the areas of research in the Institute’s competence. |  |  |  |
| (iii) | Maulana Azad Museum Up gradation of Office building & Hostel | The Museum has made an impact on the people of Kolkata. Contributions of Maulana Azad to the Indian Independence movement along with a collection of memorabilia are on display for the visitors. |  |  | Maintenance of photographs with captions and about a hundred memorabilia including the highest National award – the Bharat- Ratna are displayed. Maintenance of an LCD T.V., which shows Film footage on Maulana Azad. Acquisition of films & documents on Maulana Azad & his work. Acquisition of rare books concerning life and times of Maulana Azad. Maintenance of 3 stories building for better functioning. | Increased awareness of Maulana Azad’s life, work, knowledge of Indian national movement & nation building. Making of an audio Visual on the Institute to promote the Institute within India and abroad by running the same in Seminars and Conferences and presenting to other Institutions both national and international.* The targeted work completed. |  |  | *Further, spreading awareness about the Museum and Library via visual Media – Doordarshan. |
| (e) | Kalakshetra Foundation, Chennai | A Cultural institution of International repute established for preservation of traditional values in Indian Art especially in the field of dance and museum. | 4.10 | 3.00 |  |  | 4.10 | 4.46 |  |
| i. | Theatre Upgradation and Museum | To provide an upgraded audio and lighting equipment at par with the international standard for Indian/ International audience. |  |  | Theatre upgradton and theatre sound equipment to be completed in Feb. 2011. And work on sound proofing will be taken up. | Work Committee constituted for supervising and approving major civil works inside Kalakshetra Campus* |  |  | *has being monitoring be renovation programme and up-gradation. |
| ii. | Festival and Craft Bazar. 58th Annual Art Festival, Kathakali Festival and crart Bazar. | To preserve, promote and development of performing art traditions in Bharatanatyam, Carmautic Music Kathakali. |  |  | 58th Annual Art Festival, which includes Smt. Rukmini Devi’s Dance- Dramas performance by the repertory company and 4 day Kathakali Festival are to organize. | In Dec. 2010, organized a Craft Bazaar in collaboration with Datakaari Haat Samiti, New Delhi. Smt. Rukmini Devi’s Dance- Dramas performance by the repertory company was organized and also 4- days Kathakali Festival organized. |  |  | During 2010-11, 48 new students were admitted to the departments of Bharatnatyam, carnatic music and painting. |
| iii. | Documentation of Dance Dramas. | To documentation of dance dramas on the theme of Krishna to be documented for Archival purposes. |  |  | Remaining 3 pats of Ramanayan series is being brought out. | Remaining 3 pats of Ramanayan series have been completed. |  |  |  |
| iv. | Research & Documentation | To proceed further in furtherance of the activities in traditional Art form and also to train young generation to keep abreast of the development in this field. |  |  | As a part research work on Smt. Rukmini Devi’s dance drama and other contemporary music/dance art forms, collection of rare and precious books from various sources will be collected, training session including field trips of students. | The work is continuing. The current activities will continue under research and development being by proper administering the library and research work. |  |  |  |
| (g) | Namgyal Research Institute of Tibetology, Sikkim | The Institute is an autonomous organization under the state govt. of Sikkim and gets regular grant- in- aid from this Ministry. The main objective of this institute is to spread the knowledge of Chhos(Doctrine of Buddha). | 0.42 | -- | The Institute has ongoing programmes of translating and publishing the seminal texts preserved in its archives. | The institutes continued its ongoing programmes relating to publication maintenance and repair works of the institute, salaries of 21 regular employees. | 0.42 | 0.00 |  |
| (h) | a) Fellowship to outstanding artists in the field of performing, literary and visual arts | ## This scheme provides financial support to outstanding artists in the fields of music, dance, theatre, visual art, literature and traditional art forms of folk and indigenous art. | 1.35 | 7.00 | 125 junior and 125 senior fellowships to be awarded. | 125 senior and 125 junior fellowships were awarded. | 1.78 | 7.16 |  |
|  | b)Scholarship to young workers | This scheme seeks to give financial assistance to young artists of outstanding promise for advanced training within India. | 0.78 | -- | 400 scholarships to be awarded. | 354 scholarships were awarded. |  |  |  |
| (i) | - Financial Assistance to distinguished art persons - Setting up a National Welfare Artist’s Fund | To provide financial assistance to artists whose contribution in the field of art has been of great significance and who have attained an age of 58 years and above and are in indigent circumstances. To provide medical aid to artist in indigent circumstances. | 2.20 -- | 4.50 5.00 | About 2600 old artists to be provided assistance under this pension scheme. Financial assistance will be given to renowned artists for their medical/health and other purposes. | 2876 old artistes provided financial assistance during the entire period of 2010-11. This scheme is still to be implemented. | 2.00 0.00 | 10.73 0.00 |  |
| (j) | Delegation under Cultural Exchange Programme | Promotion of Cultural relations with other countries of the world on the reciprocal basis. | 0.80 | -- | The main purpose of this fund is to host cultural visits by foreign dignitaries organize meetings/ conferences under the cultural agreements. During the year 2010-11, new CEPs will be signed/executed under the Cultural Agreement with various countries. | - Miscellaneous expenditure for 16th Joint Working Group meeting India Finance. - Visit of South Africa Culture Minister of India. - Visit of Polish delegation to India. - Russian delegation to India. - Russian delegation. | 0.05 | 0.00 |  |
| (k) | Financial Assistance for Tribal/Folk Art | ## To promote and disseminate tribal art and culture. The scheme aims at creating awareness of richness of tribal /folk art through documentation and organizing cultural activities including festivals. | -- | 0.25 | There are no fixed targets individuals/organizations involved in Cultural activities and are assisted on the basis of receipt of proposals and recommendations of the Expert Committee. | The scheme was discontinued in 2008-09. However, in ongoing cases, 13 individuals/ organization were granted assistance. | 0.00 | 0.03 |  |
| (l) | Financial Assistance for the Preservation & Development of Cultural Heritage of the Himalayas | To promote, project and preserve the cultural heritage of Himalayas. | -- | 0.75 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 25 NGOs / individuals were given grant-in-aid under this scheme. | 0.00 | 0.40 | The number of proposals to be approved by the Expert Committee will depend upon the quality of the project and capability of the organization |
| (m) | Financial Assistance for the Preservation and Development of Buddhist/ Tibetan Organizations | To promote and propagate the scientific development of Buddhist/ Tibetan culture and tradition and also research in the relative fields. | -- | 3.50 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 97 NGOs / monasteries were given financial assistance under this scheme. | 0.00 | 3.59 |  |
| (n) | Scheme of Centenaries & Celebrations | To provide financial assistance to cultural organizations/NGOs for celebration of centenaries of renowned personalities of India. | 1.80 | -- | Financial assistance to be given to eligible applicants/NGOs for celebration of Centenary/ Anniversary | 8 NGOs/ Organization were sanctioned grant-in-aid of Rs. 1.61 crore during the year.. | 1.60 | 26.27 |  |
|  | - 150th Birth Celebration of Guru Rabindranath Tagore - 150th Birth Celebration of Swami Vivekananada | To commemorate 150th Birth Anniversary of Guru Rabindranath Tagore in a befitting manner and to spread his works to the people. To disseminate art and culture including literary and religious contributions made by Swami Vivekananda among the masses as a part of 150th Birth Celebration. | 0.00 0.00 | 22.00 8.00 | The programmes as approved by NIC for Chitravali, NFDC, TCGS online electronics variorum of Tagore works, Marg publication etc. All the proposals approved by the National Implementation Committee (NIC) will be taken up for their implementation, including intangible culture for character building of youth and in awakening them* | Funds released for Chitravali, NFDC, TCGS online electronics variorum of Tagore works, Marg publication projects etc. NIC approved 2 proposals on 03.09.2010. First installment of funds released for the purposes mentioned in Column 5. | 0.00 0.00 | 13.87 12.40 | Projects completed/ expected to be completed as per schedule. *towards nation building and also propagating the teachings and his messages. |
| (o) | Maintenance of National Memorials | To commemorate the role of eminent National Personalities who have contributed to and played a historic role in the history of the country. | 1.70 | 0.00 | Financial assistance is given to the voluntary organizations for maintenance of National Memorials | 2 NGOs were given assistance for development and maintenance of National Memorials. | 0.00 | 0.00 |  |
|  | Development of Sardar Vallabh Bhai Patel Memorials & Development & upkeep of Dr. Rajendra Prasad Memorial. |  | 0.00 | 15.00 | Grant to be released to the Trust for undertaking developmental works on Sardar Vallabh Bhai Patel Memorials. For upkeep of Dr. Rajendra Prasad Memorial, grant will be released to the Trust. | Grant of Rs.10.00 cr. was released to the Trust for undertaking the said works. Still to be taken up. | 0.00 | 10.00 |  |
| (p) | Scheme of Building Grants including Studio Theatres | To give grants to voluntary cultural organizations working in the field of dance, music, fine arts, indology and literature for construction of building and purchase of material. | -- | 5.00 | There are no fixed targets individuals/organizations involved in Cultural activities and are assisted on the basis of receipt of proposals and recommendations of the Expert Committee. | 44 organizations have been granted assistance. The scheme has been modified and reintroduced as Building Grants, including Studio Theatres w.e.f. 07.01.11 | 0.00 | 1.28 |  |
| (q) | Financial assistance to Cultural Organizations with a national presence | To provide assistance Institutions/Organizations engaged in cultural activity at the National level. | 3.00 | 5.00 | The grant will be given to the prominent institutions like R.K. Mission. INTACH and SPICMACAY etc. | R.K. Mission was Institute of Culture Kolkata and others including INTACH, SPIC MACAY and NCPA, Mumbai were given grants. | 2.75 | 4.99 | Non-Plan funds were given to R. K. Mission for their administrative activities. |
| (r) | Development of Cultural Organizations (Cultural Functions Grant Scheme) | To give grants to voluntary organizations of national fame engaged in cultural activities for holding conference, seminars and symposia on important cultural matters. | -- | 3.00 | Organizations to be awarded grants, as per the recommendations of the Expert Committee. | Releases were made in the existing cases sanction in the earlier years and 400 fresh cases for the year 2010-11. | 0.00 | 9.04 | The amount of grant has been enhanced from Rs.3.00 lakh to Rs.5.00 lakh per project. |
| (s) | Twang Monastery (Center for Buddhist and Cultural Studies) | To educate the monks and also act as a centre for Buddhist Cultural Studies for preservation the traditional Buddhist art & culture. | -- | 0.01 | Monastery will continue its ongoing programmes including maintenance of their museum. Dying arts of sand Mandala and Butter sculpture will be revived by providing training to the monks students. | The monastery continued it ongoing activities / programmes on Buddhist studies. | 0.00 | 1.01 | The activities of this monastery are financed from the funds allocated for NE region. |
| (t) | Tibet House, New Delhi | The main aims and objectives of the Tibet house are to promote, preserve and protect the Tibetan culture, encourage the exchange the ideas and techniques between Tibetan and non-Tibetan artists and craftsmen. | -- | 0.50 | Tibet House will continue to implement their ongoing programmes including maintenance of Museum | It implemented its activities relating to programme coordination for awareness on Tibetan Studies and Culture and also maintained its museum during the period under review. | 0.00 | 0.50 |  |
| (u) | Central Institute of Himalayan Culture Studies, Dahung, Arunachal Pradesh | To preserve and promote the Buddhist cultural heritage of India. | -- | 0.01 | Under graduate, post graduate and doctoral programmes relating to Buddhist/Tibetan culture to be organized. The infrastructural and building related facilities are to be undertaken. | The academic programmes of the institutions continued in the period under report and funds to the tune of Rs.2.00 cr. were released for their building construction. | 0.00 | 2.00 |  |
| (v) | #### Development of Jallianwala Bagh Memorial | ## In order to take up a comprehensive development of this Memorial, refitting its status and importance in the history of India freedom struggle. | 0.50 | 0.50 | Developmental programmes will be taken up to upgrade the Memorial. | Grant of Rs. 0.25 crore for development/ maintenance of memorial was given under Non-Plan Head. | 0.25 | 0.00 |  |
| (w) | #### Scheme for safeguarding and other protective measures in the area of Intangible Heritage and Cultural Diversity (arising out of UNESCO Convention) | ## In order to meet the obligations arising from the UNESCO conventions on the safeguarding of intangible cultural heritage and cultural diversity. | -- | 0.50 | There are no fixed targets individuals/organizations involved in Cultural activities and are assisted on the basis of receipt of proposals and recommendations of the Expert Committee. | An amount of Rs. 0.50 crore was released for safeguarding and other protective measures in the area of ICH and Cultural diversity. | 0.00 | 0.50 |  |
| (x) | #### Plan scheme for promotion and dissemination of Awareness about Indian Culture and Heritage | ## To take up activities relating to promotion of cultural and heritage through performing arts and theatres. | -- | 0.01 | This scheme will be implemented through CCRT, after modifying this scheme. | The scheme will be implemented through Library Section of the Ministry in 2011-12. | 0.00 | 0.00 |  |
| (y) | #### Cultural Heritage Volunteers (CHV) Schemes/ Cultural Heritage Young Leadership Programme. | ## To protect the young people from marginalization and neglect by ensuring their social inclusion and involvement in civic and cultural programmes. | -- | 0.01 | This scheme will be implemented through CCRT. The scheme is being modified. | The scheme is still to be implemented. | 0.00 | 0.00 |  |
| (z) | #### Pilot scheme for Cultural Industries | ## In order to convert wide variety of creative expressions, traditional designs and endless variety of crafts into cultural industries products. | -- | 0.50 | The financial assistance will be given to ZCCs for carrying out pilot survey for cultural industries located in their zones. Other facilities for implementation of this scheme will also be provided. | Due to non receipt of UCs from 2 ZCCs, the further release of fund has been withheld. | 0.00 | 0.00 |  |
| (aa) | #### Financial Assistance for setting up of Multipurpose Cultural Complex including those for children | ## Creation of cultural complexes in States/ UTs. | -- | 3.00 | Releases were made for earlier cases. | Releases were made for ongoing projects only. The scheme was discontinued from 01.04.2007. However in ongoing cases, 2 organizations were granted assistance. | 0.00 | 2.52 | This scheme is being reintroduced with certain modification, as per MTA exercises. |
| (bb) | #### Flexible Engagements in Knowledge Institutions #### (scheme of Tagore National Fellowship for Cultural Research) | ## It envisages lateral movement of scholars/academicians into the institutions to take up projects and research work related to main objective of the institutions and enrich them with a new creative edge. | -- | 1.50 | 15 Tagore National Fellowships to be awarded. | 13 Tagore National Fellowships were awarded. | 0.00 | 0.39 |  |
| (cc) | #### Institutions & Individuals engaged in Literary Activities | ## To assist the organization of all Indian Characters engaged in the development of literary activities. | 0.10 | -- | Assistance will be provided to Institute/Individuals. | 2 institutions were given grant during the year i.e. Institute of Historical Studies & Numismatics Society of India. | 0.15 | 0.00 |  |
| (dd) | #### International Cultural activities and grants to Indo-Foreign Friendship Societies | ## To foster closer friendship and cultural contacts between India and foreign country concerned, and strengthen goodwill for Indian culture through friendship societies. | 0.70 | -- | Grants are sanctioned on the specific recommendations for the Indian Mission concerned. The grants cover expenses of grantees on cultural activities. | 56 missions have been sanctioned grant under the scheme during 2010-11. | 2.07 | 0.00 |  |
| (ee) | #### Indian Literature Abroad | ## To promote Indian languages to six UNO languages | -- | 1.00 | To promote Indian languages to six UNO languages | This scheme still to be implemented. | 0.00 | 0.00 |  |
| (ff) | #### Setting up National Centre for Performing Arts | ## To host cultural shows for performing art | -- | 1.00 | A token provision has been kept to initiate the new scheme. | This scheme could not be implemented in 2010-11. | 0.00 | 0.00 |  |
| (gg) | #### National Gandhi Heritage Site Mission | ## Development of Gandhi Heritage Sites and Establishment of Gandhi Heritage Sites Portal in Sabarmati Ashram Ahmedabad for restoration, maintenance, conservation and development and also for preservation of writings/publications etc. of Gandhi ji. | -- | 5.00 | The identification, collation and assessment of information on Gandhi Heritage material for its management and development and determination of conservation methodology etc. Construction of national memorial at Dandi. | Rs. 4 crore Corpus fund released for the establishment of Gandhi Heritage Sites Portal. Heritage sites related to Gandhi ji are being developed. Relevant information on Gandhi ji will be preserved in the portal which will be available for public. For implementation of announcement* | 0.00 | 4.00 | *made by Hon’ble P.M. on the 75th Anniversary of Dandi Salt Satyagraha. A national dandi memorial will be constructed. |
| (hh) | #### International Federation of Arts Councils and Culture Agencies (IFACCA) | ## Ministries of Culture & Art Councils from over 60 countries are members of IFACCA. | 0.05 | -- | Annual contribution has to be given to join the IFACCA. | Contribution of Rs. 4.13 crore has been given to the federation. | 0.04 | 0.00 |  |
| Archaeology, Archives and Museums |  |  |  |  |  |  |  |  |  |
| 17. | Archaeological Survey of India | This organization is mainly involved in conservation, preservation and maintenance environmental developments of ancient monuments and sites. | 260.00 | 121.00 |  |  | 267.71 | 154.24 | Normally, non plan grant is used for administrative and establishment expenses. |
| i. | Conservation & Preservation of Ancient Monuments: its up keep and maintenance including environmental development. | For conservation, preservation and maintenance of centrally protected ancient monuments and sites. |  |  | ASI has undertaken about 1600 schemes (works) for structural conservation, chemical preservation and horticulture operations based on priorities, commitments and financial resources. The work relating to structural conservation, environmental* | Better preservation and conservation of monuments have enhanced cultural tourism. Scientific conservation has arrested further deterioration monuments. |  |  | *improvement and scientific preservation of these 46 monuments identified for the Commonwealth Games taken up. |
| ii. | Providing basic amenities tourists | Development of basic amenities in Ancient monuments including provision of toilets, drinking water facilities etc. |  |  | Better visitor facilities and other amenities in World Heritage Monuments and Sites and ticketed monuments. | Better tourist satisfaction increase in the number of cultural tourists. |  |  |  |
| iii. | Excavation and Exploration. | ## Excavation of Archaeological Sites and Exploration of antiquarian Remains, under Village to Village Survey and Problem Oriented survey |  |  | 1. 3 Excavation of Archaeological Sites and exploration of antiquarian remains. 2. Problem oriented Survey. 3. Purchase of Machinery and Equipments, tools and plants. 4. Temple Survey Project. 5. Financial assistance for excavation for Universities and Research Institutions. 6. Financial assistance for publication. 7. Epigraphically Survey. | Ongoing process. Self explanatory. |  |  |  |
| iv. | Development of the Archaeological Site Museums. | Maintenance/Development of Archaeological Museums |  |  | 1. Maintenance of 44 Site museums. 2. Phased Museum Reforms. 3. Opening of the site museums at Piprahawa (U.P.), Lalitgiri (Orissa), Shivpuri (M.P.) and Sannati (Karnataka). 4. Re-organization of the galleries as per 14 Point Museum Reform. 5. Upgradation of Public amenities. 6. Publication of brochures/popular literature. 7. Capacity building and outreach programme. | Ongoing process. Self-explanatory. |  |  |  |
| v. | (i) Publication (ii) Cultural Awareness | - Publications under Academic and Informative Series. - Dissemination of knowledge and awareness generation regarding heritage. Celebration of World Heritage and other important days by Circle & Branche offices of ASI for dissemination of knowledge and creating awareness among the masses on our rich heritage |  |  | Academic - Indian Archaeology – A Review – 2003-04 and issues for 2004-05 and 2005-06 are in press. - Memoirs – Excavation at Antichak published. Kalibangan and Udayagiri are in press. Informative 1. Guide Books on Taj Mahal, Sarnath (Hindi). 2. Special publication on Geoscietific Studies for Conservation of Ajanta published. 3. Coffee Table publication>: Monuments of Delhi in English published and Hindi version in the Press. 4. Circle and Branches have brought out brochures/folders on archaeological discoveries, explorations, excavations, conservation and preservation of centrally protected monuments for free distribution at ticketed monuments. Celebration of World Heritage and other important days by Circle & Branch Offices of ASI through holding photo exhibition, Quiz/essay, painting competitions, workshops and other cultural events for school/ college students. | Increased research base on Indian archaeology and greater awareness about India’s heritage. Greater interest in and awareness of heritage. |  |  | Non-receipt of complete manuscripts along with illustrations. |
| vi. | National Mission for Ancient Monuments and Antiquities | a)Mission aims to undertake major activities like documentation of antiquities spread over site Museum of ASI, museums under the control of State Govts. and Universities b) Compilation of data on unprotected monuments and sites c) Digitization of archival drawings of various architectural institutions/organizations and organizing training programmes etc. |  |  | 1. Documentation of antiquities that are lodged in 42 site museums of ASI covering nearly 1 lakh antiquities 2. Documentation of antiquities that are lodged in sculpture sheds of 24 Circles of ASI covering nearly 50,000 antiquities 3. Documentation of antiquities that are lodged in Central Antiquity Collection of ASI covering more than 1 lakh antiquities 4. Documentation of antiquities that are lodged in 251 archaeological museums under the control of 29 States and 6 UTs 5. Compilation of data on unprotected built heritage and sites in 35 States and UTs from secondary sources i.e. both published and unpublished 6. Digitization and creation of data base of more than 4 lakh registered antiquities as lodged with data bank of ASI 7. Digitization of archival drawings that are available with 24 Circles, 6 Branches, 2 Temple Survey Projects and 1 Building Survey Project of ASI 8. Creation of data base of 3675 centrally protected monuments and sites* | National Mission has documented 3, 50,000 Antiquities and 80,000 Built Heritage & Sites in the prescribed template developed by NMMA for creation of National Database. The work of documentation of Antiquities lodged at Central Antiquity Collection, Purana Qila is under process. |  |  | *9. Workshops of museum personnel under the control of States and UTs will be organized at 10 different cities of the Country 10. Out reach programmes on heritage awareness for school children will be organized in all the 29 State capitals and 6 UTs 11. Training programmes on heritage conservation and management will be organized for NGOs and concerned State officials in all the 29 States as part of capacity building programme. |
| 18. | National Archives of India | The custodian of non-current records of enduring value of Central Government Ministries / Departments / Offices and their predecessor bodies. The nodal agency for record management activities and their permanent preservation and use by the posterity. | 14.50 | 5.00 |  |  | 14.18 | 4.88 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Expansion of records Management Programme | i. Acquisition of Public Records ii. Appraisal of files iii. Survey and Inspection of Public Records iv. Vetting of Records Retention Schedule. v. Holding of Meeting of Archival Advisory Board vi. Compilation of 9th and 10th Report of DGA on Implementation of Public Records Act 1993. vii Organizing Orientation course in RM for DROs. viii. Inspection of DRR’s of Ministry/ Departments/ Offices. |  |  | Acquisition of 15,000 files\records. Appraisal of 15000 files of the records. 80,000 appraised records of various Ministries/ Departments transferred Vetting of 10 records retention schedule 1meeting to be held annually & follow up actions to be taken. Compilation of 11th & 12th DGA Report to be completed. 7 orientation courses to be conducted 16 DRRs to be inspected. | 6865 files acquired, 6861 records appraised, 28 Archival Assistants engaged in several Ministries for record appraisal. Appraisal of 2, 68,519 records, 1, 37,738 files transferred by 31.03.2011. Subject listed in AIMS package online 1, 56,138 files. Processing and arrangement of records received in NAI (w.e.f April 2010)- Physical checking 84,026 files Arrangement of files 25,131 files Records in process having been received in NAI-1, 33,099 files. Two Records Retention Schedule vetted..* |  |  | * 10th, 11th and 12th meeting on the archival advisory board has been held and various recommendation circulated to all concern. 85 Ministries of GOI were asked to furnish 80 hrs. on implementation on public record Act. 7 orientation courses were held. |
| (ii) | Expansion of repair and reprography | Repair of records, binding of books/ volumes/ preparation of security Microfilming, Preparation of Security Microfiche films, Positive printing of microfilms, Supply of copies (Xerox/ Photo/ Reader/ Microfilm to scholars as per their demand). Out sourcing of negative and positive microfilming/ out sourcing of positing microfilming of negative microfilm rolls available in NAI. |  |  | 1,10,000 sheets to be repaired, 80 books, 200 volumes and 1000 misc. items to be bound, 720 rolls to be microfilmed, preservation of 100 bundles of each Palm, Terat and Tulat leaf 60,000 exposoures to be completed, 28,000 meters printing to be done. 50,000 copies to be supplied to scholars. Scanning of 396000 images by Microfilm scanner. Digitalization of Manuscripts – 300 images. | 1, 05,700 sheets repaired, binding of 240 vols., 291 books, 2854 misc. items taken up. Stitching of 215vols. 250 books and 2763 misc. items were taken up. For Conservation and repair of records and rare books in NAI, procedural formalities are being taken to out source the work. Repair and lamination of 1,99,241 sheets, 2480 proceeding vols were stitched and bound under conservation/ preservation of public record. Repair and lamination of 1, 73,863 sheets * |  |  | *2414 vols were stitched and bound under repair and binding of library material of rare and important books and publications. Palm leaf MSS- 6778 bundles and curative conservation of 21, 627 sheets, 671 rows microfilm. |
| (iii) | Expansion of library and administration | Purchase of books Data Entry in to the computer Preparation of data input sheets. |  |  | Accessioning of books/periodicals-700 Preparation of data input sheets- 700 Classification of books/periodicals- 700 Books cards prepared- 1500 | 1258 books acquired, 1482 books/periodicals accessioned, 1369 books classified, 4633 books card prepared. 1546 data entries made, 1036 books bound/laminated. |  |  |  |
| (iv) | Expansion of National Register or Private Records (NRPR) | Publication of NRPR volumes |  |  | Volume of 24 & 25 to be compiled & completed | Listing of performers was made which were so far received. Work of compilation and editing of vol. 24 of NRPR is in progress. |  |  | Subject to receipt of adequate no. of properly filled in proformas from States/UT Archives/RRSCs |
| (v) | Expansion of Activities of School of Archival Studies | - One Year Diploma Course in Archives and Record Management - Short Term Courses in Archival Management and allied disciplines. - Monthly Talks, Workshop/Seminars on Conservation, Records Management, Expansion of School Library |  |  | (a) One year diploma course in Archives and Records Management 2009-10 to be completed and diploma course 2010-11 to be started (b) a. Short Term Course in Record Management-two courses to be conducted. b. Reprography – 2 courses c. Servicing & Repair of Records – 2 courses d. Care & Conservation of Books/MMS/Archives – 2 courses e .Archives Management – 1 courses * | Two courses each under short term courses on records management, reprography and servicing and repairing of records, care and conservation of book/ MSS/ archives were conducted. One course on archives management was also conducted. 2 day workshop was held at port Blair on record management and RTI. 3 day workshop on record management and conservation and microfilming digitization was conducted at Port Blair and LKA, New Delhi* |  |  | *One week workshop on recorded management, conservation and microfilming/ digitization was conducted at Shilong in collaboration with department on Art & Culture, Meghalaya Govt. |
| (vi) | Setting up of a Record Centre in Eastern Zone | - Survey and Accession of non current records - Appraisal of Records - Vetting of records retention schedule. - Repair and preservation of records by INTACH, Bhubaneswar |  |  | Survey and acquisition of non-current records of Central Govt. Office in North Eastern Zone. 2000 files to be appraised Vetting of 2 record retention schedule 30 sheets per working day. | Acquisition of Public and oriental records-384 records were acquired from Andrew Yule Company, Kolkata. 9 vol. of Mayurbhanj Gazettes acquired. 4317 files acquired from An.SI, Kolkata. 306 appraised files acquired from Iron Steel Kolkata. 33 Palm leaf MSS were acquired from Gopinath Mohanty Memorial Trust. |  |  | De-acidification double sided lining, gardening, flattening and stitching 25642 sheets were stitched made by INTACH, 1413 sheet digitized. Appraisal of 10000 non current files. |
| (vii) | Scheme of financial assistance for preservation of manuscripts/ rare books to NGOs. | To financially assist individuals\ NGOs in the State \UTs in securing the valuable documents |  |  | Grants Committee Meeting to be held and the amount recommended by the Committee to be released to the recommended Institutions. | An amount of Rs.5.80 lakh was released as Ist and 2nd installments to 18 NGOs. Besides, Rs.10.42 lakh was also released to 15 NGOs. |  |  |  |
| 19. | National Museum | A premiere institution in the field of art and culture in India and involved in important work of acquisition, conservation, exhibition and educational activities | 7.75 | 10.00 |  |  | 7.81 | 9.67 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Photo-documentation of art objects and events | Colored photo documentation of Museum’s collection, exhibits for exhibitions and publication purposes and events for publicity purposes, done as per demands. - Miniature paintings - Central Asian antiquities - Manuscripts |  |  | Colored photo documentation of Museum’s collection, exhibits for exhibitions and publication purposes and events for publicity purpose, to be done as per demand. - Miniature paintings - Central Asian Antiquities - Manuscripts | - Passage to Asia Brussels exhibition – 1364 color prints prepared. - China Exhibition-13 CD prepared - All VIP visits, functioned covered – 445 color prints prepared - All Departments Object Photography – 640 color prints prepared - B&W prints – 1837 colour prints prepared - Color negatives 950 prints prepared * |  |  | - *Digital Photography (still) of arts objects – 1332 Negative prepared - Supply of Digital/Image (CD) – 60 CD prepared Old B&W negative (physical verified – 7000 negative is prepared. |
| (ii) | Display & modernization of Museum - reorganization of existing galleries. | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | - Jewellery Gallery - Central Asian Wall painting Gallery - Manuscripts Gallery - Bronze Gallery - Pre-Columbian and Western Art Gallery - Maritime Heritage Gallery - Anthropology - Pre-Columbian & Western Art * | - ”Sharan Rani Backliwal Musical Instruments gallery” is reorganized and opened for public. - Work of re-organization of the decorative arts gallery no-1 was taken up. - Temple Chariot The case of temple chariot, displayed near the entrance of the Museum, was reconstructed. Now toughen glass covering is provided to the temple chariot in place of plastic covering. Existed labels of temple chariot in Hindi and English were revised and edited. Work of glass covering and labels in Hindi and English is completed. - Work of Costume Gallery is under progress - New metallic signages were provided for sculptures displayed outside, Ground Floor Rotunda & Corridor - Refurbishing of 32 pedestals to the sculptures displayed in the ground floor corridor and rotunda. - After darning costumes were displayed in showcases. Plaster cast of the Ashokan Edict in Hindi & English is displayed in the National Museum lawns. |  |  | - *Decorative Art - Special storage for wooden door collection - Modular Storage System for Textiles |
| (iii) | Re-modeling of the object in Plaster Casts Acquisition of Books for Museum Library & Educational Activities and Outreach Prog. | To make the artifacts more attractive and colorful. |  |  | Preparation of rubber moulds, raw cast of replicas in Plaster of Paris and raw finished and coloured as per approved list for the sale and gift purpose. | Preparation of rubber moulds, raw cast of replicas in plaster of paris and raw finished and coloured as per approved list for the sale and gift purpose.* |  |  | *Casting of 850 moulds and its coloring etc. |
| (iv) | Restoration and Conservation of art objects. Restoration of Oil Paintings / Conservation of antiquities / art objects / training course in conservation, Acquisition of equipments for conservation / binding of manuscripts. | - To protect the antiquities and art objects from decay. - To train the Museum staff of National Museum and other museums/Institutions in latest technology in conservation. - To keep laboratory well equipped with the latest equipments. |  |  | Conservation : - Chemical Treatment/Conservation of 1000 objects from Museum collection - Restoration / conservation and bindings of 50 manuscripts - Chemical Analysis of 200 Harappan/ Anthropology Metallic Objects - Conservation work of objects from outside institutions such as Parliament Houses, Rashtrapati Bhawan etc. as per demand. Teaching and Training - 3 months training course in conservation of manuscripts/ metal objects. - Programmes on Preventive Conservation for Curators of different Museum/Art Galleries (4days) on Metal and Wooden objects. Survey of National Museum Objects - Examination of Artifacts of different sections to fix priority of conservation of about 1000 objects in a year and also preventive conservation* | Cleaning and preservation of about 560 objects in the laboratory, galleries, storage, museum garden, and rotunda of National Museum. , Survey and preventive conservation of 237 objects in reserve storage, Conservation of 59 panel painting in Parliament House, Conservation of 3 objects of Goa Museum, Conservation of Buddha Stone Sculpture in Darbar Hall Rashtrapati Bhawan, 286 objects were examined / prepared condition report in connection with the Exhibition Maharaja, Divine & Cosmos, and Passage to Asia., Organized workshop on conservation of illustrated manuscripts in collaboration with IGNCA and Manuscripts Mission, Museum artifacts photo documented for before and after conservation treatment 680 negatives were prepared. |  |  | * Workshops & Conference Workshop on Conservation Artifacts at Lahaul Spiti. - Workshop on conservation of artifacts at Leh. - Workshop in North East Re-organization of laboratory - Procurement of equipments for Laboratory as per requirement Condition Reports Examination and preparation of conditions report of Artifacts selected for various exhibitions in India and abroad. |
| (v) | Exhibition Publications Strengthening of Museum Security | - To popularize the ancient Indian Art & Culture. - To organize thematic exhibitions. - To organize exhibitions under Cultural Exchange Programme - To bring out catalogue bulletins, guide books, art publication etc. To strengthen the security arrangements of the Museum |  |  | Special photographs display of Museum objects. Exhibition to be organized subject to the finalization of bilateral Agreement by the MoC Printing of invitation card, brochures. Reprinting of out of stock publication & galleries catalogues etc. Electronic surveillance and maintenance of CCTV system, security equipments AMC awarded to M/s ECIL. | - Special exhibition titled “Sanaugavut: Inuit Art from Canadian Arctic” was organized. - Exhibition titled “Games & Sports in India” was organized on the occasion of CWG – 2010. A. Printing of Invitation cards, brochures, folders, publicity materials, etc. for modernized – reorganized galleries and forthcoming exhibitions. National Museum Brochure is published in Hindi & English., News letter of National Museum is published during the period under report. |  |  |  |
| 20. | National Council of Science Museum | To popularize Science and Technology by organizing exhibition, seminars, training programmes for Science Teachers, students, young entrepreneurs, technicians etc. | 24.25 | 21.00 |  |  | 34.46 | 30.96 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | - Setting up of new galleries, - Upgradation and updation of exhibits, - New circulating exhibitions, - Educational programmes, - New mobile science exhibition units, new training facilities, - Strengthening of infrastructure and existing facilities of 25 science centers located at various parts of the country including Major Civil works - MS Course in Science Communication - to get professionally qualified personnel for popularization of Science. | To modernize, upgrade and popularize the science and technology in the country. |  |  | New galleries will be set at NBSC, Siliguri; DSC, Purulia; RSC, Bhubaneswar; RSC, Jaipur; VITM, Bangalore; RSC, Coimbatore. Additional galleries on ‘Image’ at SSC, Patna; ‘Fun Science’ at DSC, Dhenkanal; ‘Communication’ at BITM, Kolkata; ‘Hall of Mirrors’ at NSC, Delhi; ‘Fun Science’ at Science Centre, Burdwan. Major renovation of gallery works at various Regional Science Centres, DSC, will also be taken up during the year. Two new Travelling Exhibitions will be developed also popular science exhibit for Mobile Science Exhibition will be taken up apart from others travelling exhibitions continued to be circulated. Various major educational activities including Science Fair, Seminars, Festivals, Multi-media Show, Lectures, Science Quiz, Creative Ability Programmes etc. will also be held/developed. Various civil works including renovation, installation of lift, toilets, bore wall, ACs, artifact storage facility, etc. will be taken up. M.S. course in Science Communication will continue. | New Galleries & Renovation of Galleries: ‘Electrotechnic’ at VITM, Bangalore and ‘Mathematics’ at BITM, Kolkata completed and inaugurated, ‘Reflections’ will be set up at DSC, Digha; Renovation of galleries on ‘Fun Science’ at DSC, Digha; Nehru Planetarium project including designing and developing an exhibition on ‘Astronomy’ at NSC, Delhi and ‘Children’s Science’ gallery at RSC, Lucknow was completed during the year; Development of temporary exhibitions on the theme ‘From the Archives – ‘International Sporting events in Delhi in the past’ completed at NSC, Delhi and displayed during the Commonwealth Games; Fabrication of 34 exhibits on ‘Water and Water Management’ for Delhi Jal Board completed at NSC, Delhi. New galleries on ‘Nuclear Power’ at NSC, Mumbai; ‘Popular Science’ at DSC, Dhenkanal; Images’ at SSC, Patna; ‘Children’ in BITM, Kolkata; 3D Theatre’ at DSC, Purulia and other new galleries at RSC, Bhubaneswar; Science center, Burdwan; NASI, Allahabad; RSC, Tirupati; RSC, Coimbatore; RSC, Pilikula; NSC, Mumbai were set up during the year; Another new gallery on ‘Nanotechnology’ at VITM, Bangalore was also added during the year. |  |  | Exhibitions of mobile science at VTM, Bangalore (2 Units); NSE (22 Units) continued their exhibitions in ruler as well as urban areas of the country. Travelling exhibitions on various subjects were completed at CRTL, NITM, RSC, Nagpur. The Council continued undertaking various major educational programmes at their science centers all over the country including laser shows, science fairs, engineer fairs, seminars, science drams, lectures, etc. Major civil works including face lifting of science center building, up-gradation of substation, construction of storage facilities, etc. were taken up at various science centers all over the country. |
| (ii) | Major Equipment Procurement. | To modernize and provide latest equipment to various RSCs. |  |  | New film for 3D Projection System and Large Format Projection System (LFPS), Spark Theatre, digital planetarium and Immersive Visualization System for various centres will be procured. | Van-de-Graff generator (Spark Theatre) (2 sets) and Large Video Wall LCD Screen, Chassis (5 nos.) for construction of MSE bus, equipments for 3D Theatre (5 sets), CPC Telescopes 8 inch (8 sets) and have already been procured. |  |  | Other items indicated in column 3, will be procured by March, 2012. |
| (iii) | Science Centres at NE a) RSC, Guwahati (Existing Centre) b) SRSC, Jorhat (On going project) c) SRSC, Gangtok (Upgradation) and Sukanta Academy, Tripura (Catalytic Support). d) Development of 3D Theatre for SC Aizawl, Mizoram | To inculcate scientific temper in public at large and students in particularly of that area. |  |  | Strengthening of infrastructure and existing facilities by fabrication of new Exhibits etc. To set up new Science Centre along with Digital Dome Planetarium in the state of Assam. Work of expansion of SRSC, Gangtok alongwith a Planetarium. Development of exhibits (30 nos.) for the gallery on ‘Wealth of Tripura’ for Sukanta Academy, Tripura. To provide catalytic support to Aizwal, Mizoram by the development of 3D Theatres. | Work for exhibit development of the Biomachine gallery was continued. The work for SRSC, Jorhat has already been started and is expected to be completed by January 2012. Layout for construction of the up-gradation of SRSC, Gangtok has given and construction work will start very soon. Work of fabrication of cabinets for exhibits was complete. Action had been taken for development of 3D Theatre at SC, Mizoram. |  |  | SRSC, Mizoram, Tripura, Jorhat, Meghalaya and Gangtok will continue in 2011-12. |
| 21. | Science Cities | To popularize Science and Technology at selected centers in the country. | -- | 12.00 | Normally, non plan grant is used for administrative and establishment expenses. |  | 0.00 | 12.80 |  |
| (i) | On Going Projects- RSC Raipur , RSC Dharwad; RSC Ranchi; and SRSC, Solapur, RSC, Coimbatore; RSC, Jaipur; RSC, Pilikula, Mangalore; PCMC, Pune; Regional Science city, Guwahati and 2nd Phase of RGSC, Mauritius. | To set up new Science Centres/Sc. Cities in the state of Karnataka, Chhattisgarh, Jharkhand, Tamilnadu, Maharashtra, Uttarakhand Rajasthan, Puducherry (U.T.) and West Bengal. |  |  | To popularize science and to spread science message and to create a scientific temper and awareness among the people of the region. | RSC, Ranchi was inaugurated on November 29, 2010. RSC, Raipur will be inaugurated shortly. The works of Dharwad, Coimbatore, Jaipur, Pilikula (Mangalore), PCMC, Pune are in progress. The civil works for Dehradun, Jodhpur, Puducherry have been started* |  |  | *The new Centers will be completed in 33 months from the date of commencement of construction. RSC, Ranchi and Raipur completed. |
| (ii) | New RSCs at, Pune, Assam (upgradation) and Mauritius (outside India) | To inculcate scientific temper in public at large and students in particular. |  |  | These new projects will be taken up during the year subject to fulfillment of conditions under Science Cities norms\guidelines. | Work of Science Learning Centre, Nepal and RGSC, Mauritius shall be taken up in 2011-12 & 2012-13 |  |  | RSC, Coimbatore, Pilikula and Jaipur under progress. |
| 22. | Anthropological Survey of India | Committed to research activities on human population from bio-culture perspectives. Its activities include collection, preservation, maintenance, documentation and study of ethnographic materials as well as of ancient human skeletal remains. | 16.25 | 10.50 |  |  | 17.26 | 9.54 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Documentation and Dissemination Activity I – Special drive initiative for procurement of Hindi Language Publications. To maintain coordination between libraries of all regional centres. Activity II – Outsourcing libraries services in a planned way. Activity III – Maintenance of existing galleries. Museums | To maintain Anthropological Libraries in 7 Regional Centres and Central National Library at Kolkata and also maintenance of museum along with its strengthening and zonal fabrications. . |  |  | Scholars of this survey located at the regional centres and the Head Office: To maintain the resource in the form of library materials. Upgradation of the website of the Survey. Survey would be selling books of worth about Rs.1 lakh. The exhibition is likely to be visited by about 3-4 lakh visitors. Work of transferring 25 16mm visual documentary films into Beta-cam format and more than 1000 audiocassettes to continue. Strengthening museum collections with ethnography artifacts to continue. Various exhibitions will be mounted by the museum in NER and in any state. | Modernization of libraries in the survey continued, work of retro-conversion and digitization of all the libraries continued. New books national and international journals, papers procured. Collection, Conservation and documentation of museums specimens continued and maintenance of zonal museums, to touch screen kiosk informative system installed in Zonal Anthro. Museum at Port Blair. Survey arranged thematic display of artifacts and photographs at Shirapunji, Chakdah (WB), etc. Zonal Anthro. Museum of the survey Jagdalpur prepared a thorough plan for plantation of Bastar in their Museum* |  |  | *Regional Centers of the survey celebrated 50th year golden jubilee celebration including national seminar. Exhibition on Human Origin Genome and People Of India, Bio Cultural Diversity in India, Damodar Mela were hosted at a number of Regional’s Centers. |
| (ii) | Fellowship programme | At present the Survey has the strength of 47 fellows which has purpose to enhance total fellowship to 67. As these are important component of man power development of resource in the country. |  |  | At present the survey has 47 fellows. It is proposed to enhance total fellowships to 67 and also increase the stipend. | The survey conducted a written test among the applicants for deploying vacant post of JRD and SRF. Deployed research fellows continued their engagement in field work for various national plan projects/scheme* |  |  | *under the supervision of respective principle investigators. |
| (iii) | Manpower Training /Meetings of Advisory/Executive Committees/Experts Collaborative Schemes Information & Technology Publication | Implementation of various research projects requires meeting and training programmes involving outside experts. Besides internal meetings of the Executive council. |  |  | Implementation of various research projects requires meetings and training programmes involving outside experts. National Advisory Committee of the Survey meeting also need to be held at least twice during the current financial year. Training of administrative and supportive staff. Scholars/fellows of this survey to participate in training programme in various disciplines. | Many officers from Regional and HQs of An.SI participated in National/ International seminars/ training programmes/ conferences/ committee/ workshops on different topics relating to Anthro. Socio Cultural, Positive Cytology and Health, Gender & changing world of Work and Health, Palapo Anthropology was deputed/ participated during the year. The survey participated or provided collaborative academic assistance* |  |  | *To different universities/ institutions for hosting national/ international seminars/ conference during the period under report. Survey’s website upgradation continuous. Lab data management continued with procuring computers, peripheral accessories. |
| (iv) | Induction of DNA technology System & Soft ware: High/Ultra High through put DNA/RNA analysis system. Bead based suspension array system for proteins and nucleic acids and other activities are taken up by the Survey. DNA Banking. Community Genetics & Health | Maintenance of Infrastructure already developed at Kolkata, Mysore, Nagpur, Shillong and Port Blair. Development of laboratory facilities with DNA technology up to PCR level and DNA Banking at Dehradun and Udaipur. |  |  | Induction of DNA technology in Survey as a part of modernization of physical anthropology laboratories is a continuous scheme. Survey has taken programme of creating state-of-the-art advanced facilities, survey is poised to implement national programs concerning genetics and health integrated with cultural practices of communities. | Annual maintenance of all DNA labs was undertaken. Awareness prog. on haemeoglobino-pathic among local students and Ashram Boarders organized by ANRC, Port Blair. DNA lab at Dehradun has been established..UV spectrophotometer is installed at DNA lab Udaipur. Ultra flow freezer- 86 Degree celcius water purification system for DNAs and RNAs and pyroxene free water, auto clave, electrophoresis system. * |  |  | *DNA banking programme continued. The survey is poised to implement national programmes concerning Genetic and Health Integrated with cultural practices of communities. |
| (v) | DNA Polymorphism of the Contemporary Indian Populations & Ancient Skeletal Material | Study and DNA analysis of the contemporary DNA samples. Human Genome Diversity Analysis. Workshops, Outsourcing manpower. |  |  | Baseline information that is being generated on Indian populations in terms of human genome diversity will be useful in medical applications. | Mitochondrial Genome Variations in Type II Diabetes: Lab work completed. Final report writing is in progress by the deployed researcher. Genome Wide Linkage analysis of Handigodu syndrome in Karnataka, South India: PCR & Sequencing of DNA samples of Handigodu syndrome affected patients are in progress. |  |  | Procurement of consumables continued for Lab analytical studies. In scientific research of this kind, risk factors can not be predicted |
| (vi) | Physical Growth & Development of Children in N.E India – A Public Health issue | To generate information about the health status of the children of the North East India in Particular. |  |  | Growth of children as public health issue is a mission mode project in North-East Area. Research team to undertake extensive field investigation. | Computerization and analyses of data collected from field investigations continued. Deployed research scholars initiated for next phase of fieldwork among the scheduled communities in the different parts of the North East region. |  |  | Engagement of manpower on contract is under process. |
| (vii) | Narmada Valley Excavation | The extensive excavation in Narmada Valley in search of Palaeo-anthropological materials, before submergence. |  |  | Field exploration and excavation work to continue in Narmada Valley and its adjacent areas. To collaborate with European and African groups with extra mural funding to be pursued. Analysis of collected specimens to continue. | Analytical research of the collected fossils from the Narmada river-bed continues in Head Office, Kolkata. Setting up of a field camp is undertaken for Field explorations in Shivalik area. |  |  | First phase of field work has been started by the scholars of this survey in Shivalik area. |
| (viii) | NEW SCHEMES People of India: Cultural Diversity (Five components) a)Intangible & Tangible Cultural Heritage: Oral Traditions, Folk Taxonomies, Social Structure & Bio-cultural Adaptations with Gender Perspectives. b) Establishing a National Centre for Community Knowledge at the new building at Udaipur. c) National Centre for Visual Anthropology: Kolkata d) Man & Environment e) Bio-cultural Linkages with border area countries. | To scientifically documented and projected cultural diversity of the people of India for greater harmony among the communities Aims to highlighting the intangible cultural heritage of Western India Aims to provide methodological tool in anthropological research This project is earmarked for SC/ST which requires extensive findings to frame the all India scheduled for extending required field works. Reconnoiter tour for collection of first hand information for executing the project will be conducted |  |  | Reconnoiter survey, field investigations, data collection, report writing, editing in publishable form, publication of paper, and presentation in academic Seminars/ conferences to exchange views. To Disseminate the intangible cultural heritage of Western Indian through establishing a national centre for community knowledge. To establish a national centre for visual anthropological documentation and making of films. Procurement of equipment, production of 10 traditional knowledge situation and production of 4 documentaries. Reconnoiter survey, field investigations, data collection report writing editing in publishable form, and publication of paper, and presentation in academic seminars/ conferences to exchange views through extensive research in scheduled biosphere reserves. Reconnoiter survey, field investigations, data collection report writing editing in publishable form and publication of paper. Village studies in NE including photograph documentation and mapping. Workshops to be organized. | a) Field investigations carried out by the deployed scholars in different scheduled locations/communities Genealogical Records and Traditional Knowledge system in the sacred centers of India, under this project, first phase fieldwork completed on Kamakhya temple, Haridwar, Puri and report writing is under process. b) Senior officers deployed under this project is finalizing a brief report to his tour different Ang Habitats in middle and south Andaman. c) To Sr. officers attended the meeting at Mon, Nagaland to discuss possibilities of documentation of traditional way of life of Konyak Nagas. d) Analysis of data collected from 24 villages from the core area is in progress. Deployed research personnel completed second phase of field investigation in Tamil Nadu.for Gulf of Mannar Biosphere Reserve. e) Senior research scholar from NER centre conducted a pilot survey before extensive field investigation. |  |  | Engagement of manpower on contract. Deployed researchers from regional centres of the survey completed field works in Assam, Bastar , Narayanur, and South Andaman. Workshops were organized at Udaipur, Vidyasagar University, W.B. |
| (ix) | # People of India: Bio-cultural Adaptations (Two components) a.)Community Genetics and Health in North – East India b)Genetics & Health: Family Study | To address an important public health issue in the communities of North East and creating an institutional mechanism. Aim to study Bio-cultural risk factor for life style diseases |  |  | To Initiate a collaborative program in North-East on the issue of G6PD deficiency and hemoglobinopathies. To initiate field studies at Mysore and Walatair, which will be implemented with a consortium of specialties and will be known as ‘Mysore Family Study’. Standardization of protocols, through workshops and training. | Field investigation carried out under the research project. The Study of village Darang entitled “Community Genetics and Health in North East India: A Study on the War-Jaintias of Darang”. b) Collection of samples under MYFADS has been undertaken. 800 blood and urine samples and other data on Gangadikara Vokkaliga population have been collected. DNA extraction, quantification, biochemical analysis and sample preservation to continue. |  |  | Lanuched in XII Plan from 2007-08 A.P. which needs induction of manpower from outsourcing under the approval of GOI to implement the research studies. In scientific research of this kind risk factors can not be predicted. |
| 23. | Nehru Memorial Museum and Library | Responsible for collection of books, newspapers, unpublished references, private papers/ photographs film takes, and also translation of important papers relating to Pundit Jawaharlal Nehru. | 9.30 | 5.26 |  |  | 9.30 | 8.60 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Research & Publication - Award of Fellowships - Publications Programmes - Seminars and Lectures | To offer three levels of fellowships namely Senior Fellowship, Fellowships and Junior Fellowships and to institute, award scholarships and monitory assistance. To undertake publication of books monographs etc. To organize lectures, seminars, symposia and conferences to promote and encourage the study of Modern Indian History. |  |  | It is a regular ongoing research scheme namely “ Promotion of Research in Modern Indian History and Cotemporary Studies”, “ Perspectives in Indian Development (Social, Economic & cultural)” and “India and Changing Trends in World Economy and Polity”. Publication of basic research documents is a continuous process. Organization of seminars/ lectures is an ongoing programme. | The fellows were working on the different research projects under the 3 ongoing schemes. It published research projects/documents for the benefit of scholarly community. The project for publication of selected works of late Sh. C. RajaGopalachari is also continued. Tuesday seminars and other lectures were organized 4 seminars, two at national level. |  |  |  |
| (ii) | Development of Library Acquisition of books, Periodicals/ Resource Material Multimedia Library | To maintain a Library of books, pamphlets, newspapers, periodicals, microfilms, still photographs, motions pictures, sound recording and other materials bearing on the History of Modern India with special reference to the Freedom Movement. |  |  | The Library will continue to acquire books, with a focus on Modern Indian History and related Social Sciences in addition to material on microfilm and photographs. | The library continued to acquire new books in addition to material on microfilm and photographs. Regular activities like mounting new exhibition were undertaken. Celebrating the Indian nation, 6 events were organized. |  |  |  |
| (iii) | Development of Museum | To maintain and upkeep of the Museum of Jawaharlal Nehru Personalia, memorabilia, mementos and other objects pertaining to his life and the Indian freedom movement. |  |  | Regular activities like mounting new exhibitions, cultural events, the thematic film shows will be undertaken. On the occasion of Historical Milestone of Indian nation, various events will be organized in and around Commonwealth Games-2010. | General maintenance and upkeep of the museum was undertaken. Regular activities on new exhibitions to attract public were also under taken the glories legacy of the modern India, its maker and builders, besides it different phase. |  |  |  |
| (iv) | Nehru Planetarium Activities Oral History and Manuscripts Division, Reprography Services, Children Resource Centres | Nehru Planetarium of NMM&L is the only planetarium in the Capital and its programmes stimulate scientific interest among the children. |  |  | For meeting the expenditure on Planetarium, the development and maintenance on day to day bases will be undertaken. The institution will continue to implement the ongoing works on these acts. | It undertook minor repairs besides regular maintenance work. The exhibition areas renovated and civil structure of the planetarium which needed major repair including installing a new A.C. plant was under ken. Microfilming of newspaper and private papers acquired by the library continued. The Library continues acquire books on modern history and related social sciences. |  |  | The library provided state of art facilities like digital membership, wireless, LAN, high and computer storage facilities for digital material. It continues to require personal papers of eminent people. |
| 24. | Indian Museum, Kolkata | Engaged in reorganization and renovation of galleries housing unique treasures of Indian and foreign art representing centuries of cultural ethos and tradition. | ###### 5.95 | ###### 12.00 |  |  | 9.59 | 7.89 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Modernization and upkeep of galleries: Archaeology section, Anthropology Art section Numismatic & Epigraphy Wing | The objectives include refurbishing, modernization & renovation of different galleries and reserve collections with updated arrangements and techniques. |  |  | i) Reconstruction, renovation of 18 galleries ii) Setting up of 2 new galleries ( residual work) iii) Electrification of go-down – 1 iv) Air conditioning of gallery - 1 v)Equipment purchase – 1 vi) Showcase redesigning-1 vii) Fire proof arrangement-1 viii) Documentary film - 1 ix) Field collection - 200 x) Catalogue préparation - 1 | Renovation work is in-progress. Updating Arch., Art, Anth. Gallery. Maintenance and upkeep of Long Arch. Gallery, Coin gallery, Decorative Art gallery, Painting gallery, Anthropology gallery. Physically verified - (i) Archaeological objects – 1333 nos.; (ii)Coins – 1168 nos.; (iii) Art objects-283 nos. (iv) Anth. Objects – 534 nos. |  |  | Execution of the programme has been depended on allocation of available fund. |
| (ii) | Strengthening and modernization of security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. | To strengthen the security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. |  |  | i) Engagement of Security Agency & State Armed Police throughout the year. ii) Replacement of existing fittings, fixtures etc. iii) Maintenance & purchase of upgraded & sophisticated security gadgets iv) Illumination development of total campus area v) Upkeep of different electronic devices/fire/ burglary alarm, door frame and hand set metal detectors, CCTV etc. vi) Purchase of computer vii) Organization of training viii) Construction of water tank ix) Intermittent test of security system - x) purchase of vehicle | i) Engagement of State Armed Police guards; ii) Engagement of Private security agency; iii) Maintenance of CCTV; iv) Upkeep and maintenance of different electronic devices. |  |  |  |
| (iii) | Strengthening and modernization of Conservation Unit (Conservation Laboratory) | Scientific preservation of antiquities and restoration of art objects. |  |  | i) Conservation of sensitive materials – Textile, ivory, wood carvings, paintings, metal, stone, delicate artifacts etc. ii) Reorganization of mobile conservation Laboratory & its workshop; iii) Purchase of sophisticated instruments and equipments-X ray flurosence portable machine; (b) Thermo-hygro graph (Barigo); (c) UV Monitor; (d) Xerox machine. (e) D-70/80 Camera with accessories. iv) Reorganization of different laboratories (organic/ inorganic) v) Computerized documentation of conservation work; vi) Organization of refresher training courses on conservation, orientation course for museology students; vii) Organization of a Special long term project of laser conservation. | i) This unit rendered chemical treatment of 961 objects. ii) Installed a Xerox machine. iii) Conducted insecticide operations in different galleries and other part of Indian Museum campus. iv) Undertook both preventive and curative conservation of the artifacts placed either in the gallery or in the reserve. v) Organised workshop on 'Sculpture Conservation' at Museum & Art gallery, University of Burdwan. |  |  | Rs. 20 lakh as Technical fees for consultant and project management for implementing the development work under upgradation of the Indian Museum. |
| (iv) | a) Programme of Education, Mass Communication and Cultural Activities, b)Publication & printing of Annual Report/ New Publication c) Development of Photography unit and photo documentation of collections d) Project for the Development of Audio Video studio | Organization of education activities and training programmes holding of temporary/ special & inter-state, in-house exhibitions, outreach programme through Museum on wheels (Museo Bus), organization of National/ International seminar and workshop. |  |  | i) National / International seminars and workshop; ii) Mobile exhibition, temporary exhibition; iii) Mass Communication Cultural programme; iv) Annual and memorial lecture series; v) Training programmes – In-service training course and short course in museum studies, practical aspects of Museum methods; vi) Development of Auditorium & Exhibition Hall; vii) Preparation of leaflets, exhibition folders, invitation cards, handout etc. viii) Purchase of computer, wheel chairs for physically handicapped; ix) Reorganization & refurbishing of lecture room. Reprint of old publications-4, printing of new publications-4, Training to officials in advanced printing technology Printing of Annual Report 2005-06 both in English & Hindi Versions and reprinting of picture post card. Purchase photo sensitive materials with accessories, setting up of image bank of photo achieves and maintenance of equipment. A preparation of documentary films on Archaeology, Art, Anthropology, Specimen etc. | - Organized cultural events mentioned in column 5. i) Printing of Annual Report of 2005-06. ii) Printing of Colored picture post card. - Participation in different book fairs including Kolkata Book fair. i) Restoration of old valuable documented negatives of antiquities; ii) Photographs taken (color, B&W, Digital – 7021), (iii) Printing of photographs-2413; (iv) Photo documentation of antiquities – 1945; v) Digital photo documentation of antiquities – 7965; vi) Color photo - 2143. i) Annual maintenance & repairing of Audio video equipments. Produced Plaster cast replicas 475 nos.; Plaster cast finish –* |  |  | * 533 nos.; Plaster cast color finish 9 nos.; Loan kits supplied-40. Complete color finish replica – 50 pieces. Replica color inishing 451, Replica under color process 136. Library acquired 876 books, prepared 3100 data-sheets, 3100 catalogues and 500 books entered into data-sheet. 3100 books classified, 7500 xerox copies supplied, services rendered to 6000 readers, 500 journals binded. Physical verification of books 7000, Books and journals imputed in computers 5000. Books classified 3100. |
| (v) | Development/ Re-organization of Galleries under scientific surveys | To raise the standard of display and presentation of the scientific galleries and to bring them at level with that of the cultural galleries museum proposes to renovate and update the scientific galleries also with the expertise of the respective Surveys. |  |  | i) Extensive renovation of the Mammal Gallery ii) Reorganization of the Insect Gallery iii) Reorganization of showcase of Siwalk gallery iv) Introduction of intercom facility v) Maintenance of galleries under scientific survey | NID Ahmadabad is proposed to undertake the said work for which administrative clearance is being sought. This issue is still pending. |  |  |  |
| (vi) | Special repairs and maintenance of Museum buildings (heritage) | To develop and structural conservation of Museum buildings and other infrastructural developments |  |  | a)Main Museum building renovation of Damage and sewerage system including pipe lines thoroughly to be taken up of southern side of the building, repairing of doors & windows on 1st floor, de-plastering & re-plastering of ground floor and ceiling and construction a modernized ticket counter | Main Museum Building – 1. Work on the renovation of the entrance of the Main Museum building is in progress. 2. Renovation of Siwalik gallery is in-progress. |  |  |  |
| (vii) | Development of museums in Eastern & North-Eastern states of the country | To bring about greater and deeper understanding and appreciation of the country’s rich cultural heritage as a whole. |  |  | Formulation of the infrastructural development of the museums of the North-East region during 2008-09 are being re-assessed by a team of technicians, experts, Directors and other Sr. Officers of the Museum including members of the trustees of the Board of the organization. | Student from North-Eastern states have visited Indian Museum under Heritage tour. |  |  | The estimate in this respect was not mentioned earlier. The estimate cost 10% of Rs.20.56 cr. of the BE for 2009-10 |
| (viii) | Art purchase and procurement of art objects and artifacts Exhibitions (Mobile, Special and museum workshops) | Collection in a museum is a life line of its growth. Over the years the museum aims to enrich its collection. To grow awareness amongst the people for those who are not in a position to reach the Museum. |  |  | Acquisition of antiquities, art objects and ethnological specimens to be collected under the jurisdiction of authorities. Different exhibitions including museum bus and mobile conservation laboratory are proposed to the taken up. | Acquisition of art objects is being taken up in the last quarter of the year. Various exhibitions including mobile exhibitions were organized by Museum. |  |  |  |
| 25. | Salar Jung Museum, Hyderabad | A museum of national importance houses rare and varied art collection from all over the globe acquired by Salar Jung I, II and III. | ###### 8.45 | ###### 10.00 | Normally, non plan grant is used for administrative and establishment expenses. |  | 10.89 | 10.00 |  |
| (i) | Project Building | Aims to provide additional space for the museum especially for expansion of galleries. |  |  | Construction of additional floor over western and eastern block for expansion of galleries. | The work is under progress. To provide additional space for exhibiting objects in modernized and improved manner. |  |  |  |
| (ii) | Developmental works (Existing Building) | Under taking various developmental works of the existing building including reorganization of Galleries, modernization of stores, conservation of manuscripts, library etc. |  |  | Developmental works of the existing building and reorganizations of galleries. | 1. Construction of one more floor over CISF barracks. 2.Miscellaneous works 3.Carrried forward works of Galleries 4.Jade Room 5.Childrens section |  |  |  |
| (iii) | Up-gradation of security | The security in the Museum is being upgraded by providing CCTV cameras, fire alarm system and fire hydrant system. |  |  | The security in the Museum is being upgraded by providing CCTV, cameras, fire alarm system and fire hydrant system. | Reimbursement of CISF security for 12 months fulfilled. As a part of security arrangements for the Museums. |  |  |  |
| (iv) | Conservation of library books, Artifacts, MSS etc. Other Cultural and Educational Activities | Conservation of art objects /manuscripts available in the Museum Library |  |  | Usual exercise is taken up for conservation and preservation of the artifacts being displayed and also kept in store. Educational activities like summer art camp, museum week, special exhibition, seminars, workshops etc. to be organized. | The work has been completed as per target fixed under various misc. activities/ programmes. Special exhibitions and digitization work also attended to. Educational activities like summer art camp, Children week, museum week, 15 special exhibition, seminars, workshops, special lecturers, mobile photo exhibition etc.,* |  |  | * Digitalization of all the objects and the networking to the reserved collection. |
| 26. | Indira Gandhi Rashtriya Manav Sangrahalaya, Bhopal | A museum conceived as a growing movement to depict the story of human kind in time and space highlighting human biological and cultural evolution. | ###### 2.90 | ###### 9.50 |  |  | 2.90 | 7.47 | Normally, non- plan grant is used for administrative and establishment expenses. |
| (i) | Infrastructure Development and Education & Outreach programmes | Develop infrastructure facilities for achieving the objectives of documentation, display and dissemination of rich and diverse cultural patterns of India through Education and Outreach activities and Operation salvage. |  |  | Museum Site Development (Works): (i) construction of dormitory accommodation for tribal artists and students group, Construction of Documentation Centre building, Construction of Indoor Museum Building: Settlement of bills, Construction of boundary wall, Development of Visitor friendly facilities and construction of presentation spaces/auditorium/ upgradation Open air exhibition: The museum will incorporate new house types as exhibits, develop exhibits from Mahanadi River velly, create an open air display space for presentation, construction of indoor presentation/performance space auditorium, upgradation of visitors facilities in all existing open air exhibitions etc. Organization Setup: The existing units will be strengthened with adequate manpower. Development of Exhibition Galleries in Indoor Museum: Development of facilities at regional centre Mysore: Children Festival: Do and Learn Education Programme: Temporary and traveling exhibitions: Interactive-disciplinary training course on Museum and Heritage Management: Seminars/Symposia, museum talks etc. will be undertaken on the themes relevant to the scopes of the museum. | Construction of boundary wall of 500 mt. in 2nd phase, construction work of a fountain near parking and a car parking near office is continuing. Maintenance and upkeep of the open air exhibitions of the museum is carried out. 5 Traditional fifesies houses of Kom of Manipur, Deori, Rabha, Hajong and Moran Tribe of Assam were added as exhibit in the open air exhibitions. New exhibition Nearbadaji was also added in the Traditional Technology open air exhibition. 14 special periodical exhibitions were mounted. 9 “Do and Learn” museum education programme, 3 heritage corners were mounted, 22 programmes of performing art presentations, 10 seminars including a national workshops on Anthropology and museums, 6 museum popular lectures to Annual IGRMS lectures and 4 artist workshop were organized at Bhopal and various other places in India. International Day of World Indigenous People were organized. A five day art and craft workshop, cultural programme, and artist workshop, Anant Yatre and a national seminar at SRC, Mysore was conducted. Training course on conservation of wood, textile and other ethnographic objects for trainees from North East states and a national level capacity building training programme for professionals of ethnographic museums at Bhubaneswar were organized. Sangrahalaya has mounted nearly 13 temporary and travelling exhibitions at Bhopal. Museum has organized nearly 10 do and learn museum education programmes, National Balrang-2010, nearly 5 workshops and camp and nearly 31 programme of performing art presentations and several other programmes at Bhopal. 6 museum popular lectures and a annual IGRMS lecture, 9 seminar/ symposium were organized. Published 3 books, 1 journal, 1 annual report 2008-09, 3 quarterly newsletters and several brochures, folders, booklets, posters etc. |  |  | Maintenance and upkeep of indoor exhibitions road network, building, archival units like library, photography, conservation, graphic arts, etc. was undertaken from the Non- Plan Budget. |
| (ii) | Operation Salvage | Systematic action for Salvage and vanishing aspects of traditional material culture is a need because as a result of accelerated rate of change and rapid urbanization, traditional material culture, folk and tribal art objects as well as age old customs and traditions in many parts of India are fast disappearing. A systematic programme of Salvage of such material is being carried out by collection and documentation. |  |  | i)Documentation of Intangible Cultural Heritage in the village around Bhimbetka World Heritage Site ii) Documentation of various aspects of oral traditions in ethno-musicaloges and performing arts iii) Identification and Salvage of rare objects iv)Collection of material culture objects v)conservation of specimens vi)Rock Art research | Staff of the museums conducted field work in different remote corners of India to collect and document cultural heritage of India. A programme for documentation of performing arts of Tripura was organized at Tripura. Although 1389 objects have been received and accessioned in the specimen store of museum belonging to various communities of India. Project for documentation of the Intangible * |  |  | *Heritage Culture around the Bimbetka World Heritage site is continue and two projects for translation of old manuscripts were also completed in Assam. |
| 27. | Other Programmes (Museums) |  |  |  |  |  |  |  |  |
| (a) | National Research Laboratory for Conservation of Cultural Property, Lucknow | To develop the capabilities of different cultural institutions in the country in the conservation of cultural property and provide conservation services to Museum, Archives, Archaeology departments and other similar institutions. | 3.14 | 2.20 |  |  | 3.01 | 2.05 | Normally, non- plan grant is used for administrative and establishment expenses. |
| i. | Research and Development Field projects Training Information Resources and communications Up-gradation of laboratory facilities | To develop sustainable, conservation solutions. To conserve collections. Works of heart, architecture, etc. and to generate internships, assistantships for NRLC’s trainees. To develop conservators and restorers. Dissemination of conservation information To cope up with the latest advancements |  |  | Conservation solutions (10) Conservation of 1040 sft wall painting ,25 oil paintings 4 Thankas, 2 Bronzes , 1500 revenue maps, manuscripts. Generate (15) internships Train (15) conservators/ restorers. Training service to (5) universities / cultural institutions. Organize (5) national level seminar/workshops. Acquisition of Information resources (100 Publish (10) Technical note/report /articles. Acquisition of Portable X ray diffraction spectrometer and 3 D laser scanner. | Solutions found (7) Conserved 1040sq ft wall painting, 20 oils, 4 thanka, 2 bronze, 1300 maps and manuscripts. Generated (10) internships. Trained (8) conservators/ restorers. Provided trainings to the students from (4) institutions. Organized (3) seminars/workshops Acquired (70) resources Published ( 7) Acquired both the equipments as mentioned in column 5 |  |  |  |
| (b) | Victoria Memorial Hall, Kolkata | Museum of contemporary art involved in collecting material and data relevant to a period depicting art history during the freedom struggle. | 3.30 | 11.00 |  |  | 3.30 | 5.85 | Normally, non- plan grant is used for administrative and establishment expenses. |
|  | Special repair and renovation work to be undertaken by CPWD/ASI Garden development Construction of an annexe building for auditorium-cum-administrative block | To undertake the repair works of the memorial building, roof and chemical cleaning of both external and internal portion. To proper upkeepment, garden and beautification of lawns. To provide additional space for mounting exhibitions for international standard and seminars libraries facility etc. |  |  | CPWD and ASI will continue the repair work on the basis of estimates. Repair to interior surface of the dumb, de-plastering or re-plastering of the galleries. Construction of ticket sell counters etc. CPWD has completed 50% of the work of landscaping and beautification of gardens. The remaining works will be taken up during the year. Construction of annexe building at the memorial complex including exhibition hall for hosting international/ national level exhibitions etc. | Work of electrical transformer room done by CPWD. Regular maintenance is going on. Fund released but work has not taken up yet. 25 nos. of Garden Benches has been installed. Estimate received from CPWD. Fund released. Work is in progress. Estimate received from CPWD. Fund released. Work is in progress. The work has been outsourced & work is in progress. Work is in progress. Fund released to KMC. Work is yet to be taken up by KMC. Construction work for annexe building is still to be taken up. |  |  | The process for construction of Annexe building at the memorial complex is in progress for its administrative approval. |
|  | Domestic Exhibition | To familiarize the public at large about the richness of the collections and to communicate our past history, culture and aesthetics and atleast one traveling exhibition in any one of the Metropolitan cities in India. |  |  | Curating 3 temporary exhibitions out of the reserve collection. 2 other exhibitions will be held in collaboration with other organizations and abroad. | Mounted exhibition on Social Harmony for public view. Exhibition on achievement and activities of VMH “Striving towards the glories India “. Exhibition of scroll painting by MF Hussain and Sunita Kumar mounted.* |  |  | *Another exhibition on making of VMH and on heritage houses in Chitporre Road neighborhood. |
|  | Publication | To bring out high quality publication and some authentic catalogue on our unique collections of works of European artists. |  |  | A catalogue on Busts and Statues of Victoria Memorial Hall. | A catalogue on India: Land and Landscape published. |  |  |  |
|  | Strengthening of Security | To safeguard the artifacts and the monument from vandalism and theft and to protect the cultural property |  |  | Installation of fire alarm and fighting system as per recommendation of CISF including smoking detector, installation of surveillance system (CCTV) Installation of 12ft. height’ barbed wire fencing on the perimeter wall. Deployment of 131 CISF/ personals | Security system upgraded, purchased of 1 multi zone DFMD and installed, 2 battery operated pollution free charts. Fire Fighting devices for emergency use. Deployment of CISF personnel is under consideration. Deployment of Kolkata Police is continuing. Existing * |  |  | *CCTV cameras and system are repaired & is working properly. Hiring of 13 walky Talky on rental basis continuing. |
|  | Setting up/ Modernization of galleries and storage of art objects and installation lighting, climate control, visitors facilities etc. | To restructures, remodel all the galleries of the Memorial with proper display, lighting system and climate control. |  |  | Development of Infrastructural support system and Modernization of galleries and stores as per the Master Plan by NID, Ahmedabad. Installation of LED Screens near north and south gates for virtual tour of museum beyond museum hours by NCSM, Science City. Installation of centralised Air Conditioning system in exhibition hall at Portrait Gallery by M/s. Voltas Ltd. | Work to be started this month. Proposal dropped by Board of Trustees because of high cost. Four ACs are installed. |  |  |  |
| (c) | Allahabad Museum, Allahabad | The main activities of the museum include acquisition of art objects, reorganization of galleries and reserves enriching the library and photography unit and publication | 1.98 | 2.50 |  |  | 1.74 | 1.41 | Normally, non- plan grant is used for administrative and establishment expenses. |
| i. | Renovation of Building | Aim to provide additional space required for staff and visitors in a proper manner. |  |  | Renovation of the sitting rooms of the Asstt. Keepers etc. including mainly paintings of walls and roofs. Plastering at various point in the museum building. Construction of toilet on the first floor. Other repairing and cleaning works. | Certain portions of existing building were got a new look and required space and facilities for staff and visitors also increased. |  |  | Progress dependent on timely availability of funds |
| ii. | Library Photography, documentation and strengthening thereof. | To strengthen the library collection and also to acquire number of journals and volumes of sets possessed by the museum, to microfilm certain books and journals which are not available by sending a team consisting of Museum personnel and to acquire books and journals of importance to enrich the Museum library. |  |  | Routine work of classification, cataloguing and computerized book inventory; binding of books, cataloguing of Persian manuscripts by engaging an expert, purchase of Library Software; purchase of Library books. | 50 books on different subjects acquired, 600 books classified and catalogued, 15 issue of journals subscribed. 2301 readers attended the library and 190 books were consultant by the scholars, 3991 zerox copies were taken out. * |  |  | * Photo coverage of all activities like seminars, lectures, workshops, exhibition, etc. undertaken. |
| iii. | Modernization of galleries | The objectives include wood paneling, fabrication of new showcases\wooden blocks, modernization\reorganization work in various existing galleries of the museum. |  |  | Wood paneling in Minor Archaeological and Sculpture galleries. Fabrication of wooden blocks for partition in Coomaraswamy Hall and new showcases and renovation of old ones departmentally. Framing and mounting of more than 500 paintings in miniature and modern paintings gallery. Modernization of Nehru gallery and other important works will be attended. | Modernization work was carried out to provide better knowledge of our ancient cultural heritage to the visitors. Diesel for generator procured for keeping galleries lightened during the power failure, modernization of 3 galleries: i. Miniature painting, ii. Modern painting and iii. Nehru gallery is under process. Captions, showcase and gallery sheets of * |  |  | *arms gallery, natural history gallery archaeology galleries were renovated and changed. |
| iv. | Acquisition of Art Objects | To acquire art objects for the Museum through Art Purchase Committee in its meeting to be held at suitable intervals. |  |  | First & Second meetings of Art Purchase Committee may be held in Oct. 10 & Feb.11 respectively. | AS per recommendation of the Art Purchase Committee, art objects and antiquities worth Rs. 8.24 lakh were purchased. |  |  |  |
| v. | Exhibition and display Organization of reserve collection. Modelling Section. Educational and other cultural activities Research Fellowship & Exploration and Chemical Conservation Laboratory. | To encourage the budding artists of the country and to increase the knowledge of religion and culture of people of North Eastern Region |  |  | Reorganizing reserve collection of explored material, preparing showcases for Bronzes and Archaeological objects, exhibition of renowned sculpture artists Shri Gyan Singh and Shri Lallen Singh. Exhibition of prize wining paintings of renowned artists including sculpture artists to be held. To hold photography exhibitions of masterpieces in the museum at different educational institutions and museums. | 3 exhibitions were held including Banaras thought based on water colors exhibition, prize winning paintings/ clay modeling exhibition and exhibition on newly acquired art object. Held various memorial lectures, workshop, exhibition, painting workshop, clay modeling workshop, seminars children cultural programmes and national seminars on art & archaeology, astrological science, etc. were organized. |  |  | Conservation of a total number of 522 objects comprising 70 stone sculpture, 10 paintings, 300 MSS, 110 bronze metal and 25 archival documents were conserved. |
| (d) | National Museum Institute of History of Art, Conservation & Museology, New Delhi | To provide education and training in the specialized areas of art, history, conservation and restoration of artifacts and their display and upkeep in museum. | 0.25 | 4.00 |  |  | 0.17 | 3.00 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Academic Programme Noida Project | Dissemination and advancement of knowledge in the fields of History of Art, Conservation and Museology. To establish it own building over 3 acres of land at Sector 62, Noida. |  |  | Conducting of courses by admitting students to M.A. courses (55 seats) and Ph.d courses (12 seats) and 3 short terms courses – two in English and one in Hindi (about 250 participants). Construction work to be taken up during 2010-11. | Out of 42 students in M.A. Courses, 26 students passed out whereas 18 students admitted in Ph.D. Courses, 7 students passed out. In Short Term Courses, 199 students admitted and 124 students passed out. One international, 1 seminar, 5 national seminar were held* No meeting of SFC for sanction of grants/ approval could be held. |  |  | Duration for Ph.D is 5 years. The short term courses are for duration of 5 months. *6 special lectures were also conducted. |
| (e) | Scheme for financial assistance for ‘Promotion & Strengthening of Regional & Local Museums’ | To promote the strengthening and modernization of existing museums at the regional, state and local level. | -- | 14.50 | About 50 museums will be benefited for the grants under the scheme. The financial limit under this scheme has been revised. | 60 museums/ organizations were given grant for promotion & strengthening purposes. | 0.00 | 14.82 | Release of funds depends upon the number of complete/ proper proposals received from different museums |
| (f) | Scheme for Modernization of Museums in Metro Cities | In order to bring some of the Museums in the Country at par with the best in the World. | -- | 6.00 | Modernization of two museums one at Egmore Museum, Chennai and other at Chatrapati Shivaji Vastu Sangrahalaya, Mumbai is proposed apart from National Museum and Indian Museum. | Grant released to Chatrapati Shivaji Maharaja Vastu Sangrahalay (Mumbai) and Govt. Museum, Egmore (Chennai) for their modernization programme. | 0.00 | 7.20 |  |
| (g) | Vrindavan Research Institute, Vrindavan | To preserve cultural heritage of India | 0.17 | 0.43 | Various research, documentation activities on Braj culture and conservation of manuscript will be undertaken. | Publication 5 volume of Braj Culture encyclopedia’s word index of commentator, purchase of computers, furnishers* | 0.17 | 0.43 | *and other office equipment including cameras for documentation. |
| 28. | National Library, Kolkata | To serve as a repository of all reading and information materials produced in India as well as abroad concerning India | 21.50 | 15.00 |  |  | 22.54 | 12.40 | Normally Non Plan Grant is used for administrative and establishment expenses |
| (i) | Collection Building & Book Production Statistics | To collect books and other printed materials published in India, Acquisition of Foreign Books and Periodicals |  |  | Through D.B. Act/ purchase Foreign books- 3500 Titles-680 30,000 Indian publications have been targeted to acquire. | 37,400 Indian publications have been acquired 3205 foreign books have purchased and 720 titles of foreign journals have purchased. |  |  | Deposits under Delivery of Books and Newspapers Act, 1954 depend upon cooperation by publishers |
| (ii) | Retro-conversion Project & Digitization of old, Rare publications (Reader Service) | Retro-Conservation, Digitization and Modernization of Laboratory, Preservation Computer Units |  |  | Under Retro-conversion and digitization programme, it is targeted to create 4 lakh records of old and rare brittle reading materials. 14 lakh pages are to be digitized during the year. | It will preserve the old brittle reading books and upgrade the preservation, conservation and computer units of the Library for readers service. |  |  | Selection of firms, agencies to be done on the basis of open tender with subject to timely administrative approval. |
| (iii) | Strengthening of Administration | Furniture & interior decoration of Bhasha Bhavan etc. |  |  | Furniture for all the Division of Library in Bhasha Bhavan to be provided . | To improve the working environment for the staff and the visitors. |  |  | It is subject to timely administrative approval. |
| 29 | Delhi Public Library | To provide free library and information services to the people of NCT of Delhi and also to provide mobile library services in rural area of Delhi. | 10.70 | 5.00 |  | Normally Non Plan Grant is used for administrative and establishment expenses | 12.41 | 4.08 |  |
| (i) | Collection Developments | The basic objective of DPL is to provide free library and information services to people of Delhi. In order to achieve this objective, DPL proposes to strengthen its collection development in fall the service units. Besides this updating of Reference Collection of Central Library and Sarojini Nagar will also be taken up by acquiring new reading materials. |  |  | Around 4000 titles (60,000 Multiple Copies to be purchased for the DPL system in English, Hindi, Urdu, Punjabi, Besides audio & video cassettes and reference books etc. | Around 33,900 books and 468 DVD’s were purchased. |  |  |  |
| (ii) | Conservation and Preservation | Binding care and repair of books and other reading materials are continuous activity of DPL. Preservation of documents is a compulsion in a library for posterity purpose. |  |  | Around 20-25 thousand new books are to be bound through commercial bookbinders. | 5475 Books were got bound through the binders. |  |  |  |
| (iii) | Modernization and IT Development | Modernization of library activities is the continuous process of DPL. It is proposed to augment the computer system of library, which requires more computer, server, scanner, operating system, ISM etc. for creating of database in other Indian languages. |  |  | DPL has started free internet access services by installing 15 terminals at Patel Nager, these terminals each in Sarojini Nagar & Central Library. DVD corners have also been set up in 3 libraries – Patel Nagar, Sarojini Nagar & Central Library. This service is proposed to be extended in 5 branches this year. | Free internet service extended to another 6 units viz.,Karol Bagh, Vinobha Puri, Janak Puri, Narela, R.K. Puram Sec. 8 and Shahadra libraries. |  |  | Successfully conducted the exhibition and sports quiz competition as a part of common wealth games celebrations. |
| (iv) | Seminar/Lectures/ Training |  |  |  | Around 25 staff members to be trained during the year. | Officials were deputed to various trainings and seminars. AS per recommendation of 6th CPC, 64 group IV employees were given in house training. |  |  | Renovation of façade in the central library completed. |
|  | New Schemes a. Opening of New Libraries |  |  |  | It is also proposed to open new libraries in the areas inhabited by weaker section of the society. | No new library could be set up during the period under review. |  |  |  |
| 30. | Raja Rammohun Roy Library Foundation | To promote and support public library movements in the country. | 2.90 | 30.00 |  |  | 3.70 | 38.50 | Normally Non Plan Grant is used for administrative and establishment expenses |
|  | Matching Schemes: a) Assistance towards building up of adequate stock of books b) Assistance towards organization of mobile libraries and rural book deposit centers c) Assistance towards storage of books d) Assistance towards seminars, workshops and book exhibitions e) Assistance to public libraries towards increasing accommodation f) Assistance towards acquisition of TV-cum-VCP sets for educational purpose/Computer for library application Non-matching Schemes: a) Assistance to voluntary organizations providing public library services b) Assistance to children libraries of children section of general public libraries c) Assistance to state central libraries and district libraries through central selection of books d) Assistance to centrally sponsored libraries –affiliated libraries under Visva-Bharati e) Assistance towards organization of seminars, conferences etc. of an all India level Professional body like ILA, etc. f)Assistance to public libraries towards centenary celebrations g) Assistance towards establishment of Children's corner | Replenishment of book stock of libraries Providing library facility to remotest corners Providing storage materials Providing awareness, orientation to library professionals Construction of Library building Supply of audio-visual aid and supply of computers for automation To encourage voluntary zeal towards providing library service To promote reading habit amongst children Replenishment of book stock with recent costly books Replenishment of book stock with recent costly books To encourage National Professional Organizations To encourage old libraries To attract children users |  |  | 9000 Libraries to be assisted with 3 Crore Books Libraries – 10 Libraries – 3500 Organizations –50 Libraries – 140 Libraries – 70 Libraries-260 Libraries-175 Libraries-479 Books – 15 Million Libraries-37 Organizations –5 Libraries-35 Libraries-100 | 12516 Libraries 9 Libraries Libraries-4472 Libraries-40 Libraries- 183 Libraries- 301 Libraries-144 Libraries- 139 Libraries-387 Organizations-37 Libraries- 18 Libraries-25 Libraries- 39 |  |  | State Govts. sometime failed to release contribution in time As a result finalization of proposals may be delayed State Govts. sometimes failed to send applications in time. As a result finalization of proposals may be delayed depends on the meeting of the Book Selection Committee. |
| 31. | Other Libraries |  |  |  |  |  |  |  |  |
| (a) | Central Reference Library, Kolkata | To implement (a) Compilation and publication of the Indian National Bibliography (in Roman script and respective language scripts) * | 2.02 | 0.60 | *which is a bibliography of current Indian Publications in Indian languages recognized by the Indian Constitution and in English and (b) Compilation and Publication of Index Indiana. |  | 1.98 | 0.57 | Normally, non plan grant is used for administrative and establishment expenses. |
|  | Indian National Bibliography & Index Indiana Other activities | - Publication of INB Annual volume 2007 - Compilation of INB Annual volumes 2008 - Monthly issues of INB 2009 January to December. - Compilation & Publication of Index Indiana - Apprenticeship Training programme - North East Region development programme - Data collection centers at 5 state capitals at Chennai, Bangalore, Hyderabad, Pondichery & Thiruvananthpuram |  |  | a) 250 copies of Annual Volume of INB 2007. b) Manuscript of 2008 INB vol. to be ready. c) Monthly issues of INB 2009. d) Manuscript of 2009 INB vol. ready. 100 copies of index Indiana-2004-2009 6 batches of 30 students to be trained in Librarianship, 2 Training/ Workshop/Seminar/ Programme Putting the INB database on the net. 3 book fairs. | a)Achieved 250 copies of the publications brought out. b) Achieved c) Achieved Achieved 8 Batches of 40 Students trained. 3 training programmes in NE conducting. 1 seminar conducted at Imphal, Manipur Upgraded LibSys. Software installed. Organized sale and exhibitions of CRL publications. |  |  | Malayalam bibliography published. Successfully conducted seminars and workshops in Manipur and Silchar. Not Achieved. |
| (b) | Khuda Baksh Oriental Public Library, Patna | This Library has been evolved out of a personal collection of Maulvi Mohd. Bakhsh who was a man of letters with a great passion of books. It houses over 20000 manuscripts and some rare printed books. | 2.02 | 1.50 |  |  | 2.29 | 0.00 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Acquisition: Purchase of Books, manuscripts, microfilms, Video & Audio Cassettes | To acquire books, manuscripts, microfilms, Audio & Video CDs for use of readers |  |  | Purchase of 5000 printed books, 50 manuscripts and 120 titles of periodicals. | Purchased 5536 printed books and 89 periodicals, 28 newspapers, 10 MSS, 112 audio visual cassettes. |  |  |  |
| (ii) | Research & Publication: Publication of rare material , Printing of Catalogue, Research seminars, Lectures & Cultural programmes, Khuda Bakhsh Research Fellowships and Publication of Quarterly Journal. | To bring out critical editions of manuscripts, publish books of rare value, lectures by distinguished scholars. To acquaint the outsiders with the hidden treasure descriptive catalogue. Organization of seminars, lectures of distinguished personalities. Fellowship and Scholarships to renowned scholars. |  |  | Publication of English translation of 3, Hindi translation of 1 and facsimile of 2 rare manuscripts Publication of 20 books. Printing of 2 volumes of catalogue , organize National Seminar 2, Annual Lectures 1, Extension Lectures 4, Popular Lectures 12, Cultural Programmes, Senior Fellowship – 3 Junior Fellowship – 7 Assigning research projects to scholars Publication of 4 issues of Quarterly Journals. | 9 books published 5 National Seminar, 1 Annual Lecture, 8 Extension Lectures, 3 Popular Lectures, 3 Exhibitions, 1 Mushaira and a few other cultural programmes were organized. 7 Senior Fellows and 5 Junior Fellows and 1 Tagore National Fellow were working. Four issues of journal brought out. |  |  |  |
| (iii) | Conservation & Preservation : Preservation Laboratory and development of books preservation & reprographic facilities. Modernization and automation. Organization of events and exhibitions. | Preservation Lab. For routine maintenance, curative as well as preventive and preservation. To keep the books in the good condition. |  |  | Routine activities for preventive and curative preservation of books and manuscripts. Getting printed books and manuscripts bound on contract basis. Rescanning work of manuscripts will be taken up. | Routine activities for preventive and purantive preservation of books and manuscripts were undertaken including 323 books and MSS got bound on contract basis. Digitization of 10 lakh pages of MSS* |  |  | *was completed through NICSI. Re scanning of such MSS whose images have been rejected was done. |
| (c) | Thanjavur Maharajas Serfoji’s Saraswati Mahal Library, Thanjavur | A priceless of repository of culture and knowledge, it was conceived as the Royal Palace Library in the 16th century. | -- | 1.10 |  |  | 0.00 | 0.44 |  |
| (i) | Publication of books from the manuscripts in Sanskrit, Tamil, Marathi etc. | To translate, transliterate the manuscripts and to bring out books. |  |  | 14 New Books and 10 Reprints will be taken up during the year. | The work is under progress. |  |  |  |
| (ii) | Conservation | To apply citronella Oil to Palm leaves and to preserve the Paper manuscripts/ Valuable Old books etc. |  |  | 110000 leaves of manuscripts to be cleaned 2000 books are to be mended and preserved | A number of MSS have been chemically treated and conserved. |  |  |  |
| (iii) | Reprography | Microfilm of Manuscripts and rare books for preservation. |  |  | 1000 new Tamil manuscripts are to be microfilmed cleaned | The work is under progress. |  |  |  |
| (d) | Library for Tibetan works and Archives, Dharamshala, H.P. | Aim to acquire and conserve Tibetan books and manuscripts and to provide intensified reference service as well as Centre for Tibetan manuscripts, paintings and object of Arts. | 1.20 | -- | The institute was set up with a view to preserve and promote the rich heritage of Tibetan civilization and Indo- Tibetan learning. | Preservation of ancient Buddhist manuscripts, artifacts research publication education promotion, development, etc. | 1.20 | 0.00 |  |
| (e) | Rampur Raza Library, Rampur | The main objective of the library to acquire and conserve Indo-Islamic manuscripts, miniatures, books and other objects of arts and science in the library and to serve as a centre of reference and research and also act as a centre of Arts for International importance. | 1.18 | 4.05 |  |  | 1.17 | 1.24 | Normally, non plan grant is used for administrative and establishment expenses. |
| (i) | Publication & Printing | Publication of books of text of Arabic, Persian and Sanskrit manuscripts. |  |  | Publication of books, journals, technical reports and painting – includes publication of books on history and culture, catalogue, journals text of MSS monograph of painting, technical reports, Annual report, colour picture postcards preparation of coloured and slides * | 5 books have been published. |  |  | *, printings of various performas and certificates, requisition slips for books and MSS invitation cards. |
| (ii) | Preservation and Renovation of two Heritage Buildings. | Two historical palaces of Raza Library viz Hamid Manzil and Rangmahal are monuments of archaeological importance, in need immediate repairs which was approved 37th meeting of Rampur Raza Library Board. |  |  | Most of the ornamental ceilings of the rooms of Hamid Manzil have been restored within last 8 years and rest will be restored in the financial year 2010-11. | This is continuing project. Minors repairs have been done during the year. |  |  |  |
| (iii) | Acquisition of Books, MSS Scholarships and awards Seminars/workshops/ exhibitions Preservation and conservation of the collections, Computerization and application of IT, Deployment of CISF, Training Programmes and Modernization of Darbal Hall Museum. | Acquisition of rare MSS books and art objects for meeting the demands of research scholars Organizing Akademic and cultural activities for interaction of scholars, Academicians To protect prices less collection of the library |  |  | 12 rare MSS 6 printed books, 177 books and 9 art objects 5 scholarships and 3 awards 3 seminars, 2 workshops, 2 exhibitions and 2 lectures Mushiara and Kavi Sammelon about 6000 pages of rear MSS art objects, books, paintings etc. | 460 printed books and 20 manuscripts and 3 art objects have been purchased. 11 scholarships and 2 awards were given. Exhibitions, 2 Mushaira, Kavi Sammelon, two seminars and lectures have been organized. 2640 pages of MSS 1230 pages of printed books, 09 miniature painting, 08 map, 09 calligraphy,* |  |  | *92 fumigation (books and Mss) of Library collections have been scientifically restored. About 2,00,000 pages have been digitized up to 31st March 2011. |
| (f) | National Mission for Preservation of Manuscripts | Aims at cataloguing, conserving and collecting the invaluable manuscripts from all over the country and to strengthen manuscript resource centers, manuscript conservation centers and digitization of catalogues and prestigious manuscripts. | -- | 7.50 |  |  | 0.00 | 8.50 |  |
| (i) | National Manuscript Library | To create National Manuscript Library |  |  | The entire digitize Manuscripts and other important as well as rare documents will be housed in the Library. | 93 lakh images were digitized and work is still in progress. |  |  |  |
| (ii) | Networking through MRCs- | Documenting the available manuscripts in MPCs. |  |  | 48 MRCs to be given grant for executing the work of documentation and other identified works. | 67 installments were release and 1.54 lakh documents were documented. |  |  |  |
| (iii) | Networking through Manuscripts (MCCs) | Aims to provide training in conservation and allied fields |  |  | To run the existing 33 MCCs and to release grant @ Rs. 5.00 lakh for each centre | 59 installments were released. Preventive is done for 10.5 lakh folios. Curative conservation work done for 2.5 lakh folio. |  |  |  |
| (iv) | Conservation workshops and Training | To conduct preventive, rare support, curative workshop etc. on demand basis |  |  | To conduct zone wise workshops | 22 workshops were conducted & 390 candidates trained on conservation of manuscripts. |  |  |  |
| (v) | Research and Publication | To edit and publish the printed books |  |  | About 50 books/MSS to be edited and published along with Samiksika, Samrakshika and Tattvabodha | 3 books were released and 2 newsletters, Kirti Rakshana was published. |  |  |  |
| (vi) | Digitization | To digitize important Manuscripts |  |  | This is continuing scheme to digitize MSS through the selected parties | 20 lakh images were digitized. |  |  |  |
| (vii) | National Survey and Post Survey | To carryout National Survey to identify the manuscripts |  |  | To cover 5 states for identifying and documenting MSS located in the survey | One state covered 5.4 lakh manuscripts were identifies. Post Survey conducted in two status 60000 manuscripts were documented. |  |  |  |
| (viii) | Manuscript logy and Paleography workshops and training | To promote the manuscript logy through Universities. |  |  | To conduct zone wise for level I/ II/ III workshops and training | 480 scholars trained in 16 workshops conducted. |  |  |  |
| (g) | Setting up of a National Mission on Libraries, leading to the formation of a Commission. | To pointedly address the problems of Public Libraries and to upgrade the infrastructure and technological environment of the Public Libraries within a time frame | -- | 10.10 | Token provision has been made to initiate the spade work for National Commission on Libraries. | The scheme of National Mission on Libraries could not be implemented on account of similar objective of RRRLF. | 0.00 | 0.00 |  |
| (h) | Asiatic Society, Mumbai | A premier research institution in the realm of philosophy, language, arts and social sciences in relation to Asia in general and India in particular. To maintain and enhance its role the Society maintains a library and a heritage museum of rare manuscripts and artifacts. | -- | 1.00 | Purchase of 600 printed books microfilming of 650 pages daily, digitization of 600 pages daily of rare books, conservation/ chemical treatment to 1200 books to be fumigated, 5800 pages de-acidified, 57900 pages tissued and 1800 maps to be fumigated. | Purchase of 64 printed periodical and 753 books of pre-modern & 387 books of modern subjects. Microfilming of 54 books containing 15456 pages and 47 files of Bombay gazette containing 27170 pages. 784 maps were cleaned, fumigated and flattened & 559 maps mounted on cloth. | 0.00 | 1.62 | Conservation of 1229 books by fumigation, 49321 pages de-acidify, 48790 pages tissued and 100 maps de-acidified. |
| (i) | National Archives for Audio Visual Materials | This will act as central data bank on intangible cultural heritage and Nodal Agency for integrated knowledge and actual documented material. | -- | 1.00 | This is the new scheme and preliminary work for formulation of scheme and other related issues will be taken up during the year. | The detail of the scheme is still to be worked out and likely to be implemented in 2011-12. |  |  |  |
| (j) | State Central Library, Mumbai | To acquire books and periodicals under the provision of press and registration of Books Act, 1867 and the delivery of Books Act, 1954 and preserve them for posterity. | 0.30 | 0.20 |  |  | 0.00 | 0.00 |  |
|  | Modernization/ computerization/Digitisation /Up gradation of state central library | To digitize rare books and manuscripts: Computerisation/ Retro-conversion of DBA books |  |  | 18000 books, 500 periodicals, 250 newspapers receivable in DBA section to be technically processed and provided to the 2 lakh readers. | The library collected books/ reading material under D.B. Act for the readers, researchers and scholars. |  |  |  |
| (k) | Connemara Public Library, Chennai | It is one of four Depositories of Indian Publications under the Provisions of the Delivery of Books and Newspapers (Public Libraries) Act of 1954, as amended. To receive all materials published in India free of cost. It serves as a UNESCO information center and receives all the publications of UNESCO. It is also a depository for Asian Development Bank Publications. | 0.35 | 0.60 | Upgradation of library and to render Right Information to the Right User at right time. | 18676 books were received under DB Act. 16378 standard works were processed. | 0.35 | 0.42 |  |
| 32. | Provision for Project/ schemes of N.E. Region and Sikkim |  |  |  |  |  |  |  |  |
| 32.1 | Project/ Schemes for promotion of Art and Culture | To promote, disseminate and protect unique art and culture of NER. | -- | 53.24 | Organizing various programmes/ schemes in the field of promotion of art and culture in the North Eastern States and also benefiting NGOs /individuals through departmental schemes. | Preserved the rare and old documents for posterity. | 0.00 | 0.00 | ** exp. for 2010-11 for the activities of NER has been included in the respective Plan Heads /Schemes. |
| 32.2 | Archaeology, Archives and Museums | To promote cultural activities in the fields of Archaeology, Archives and Museums | -- | 15.66 | Development of Museums in North East Region and providing financial support to NGOs in NER in the field of Archival activities. Conservation and protection of various ancient monuments/sites located in NER. | Creating awareness of ancient culture of India in NER. | 0.00 | 0.00 |  |
| 32.3 | Libraries | To promote Library activities in the NER | -- | 4.60 | Development of Library activities in North East Region. | Inculcate reading habits through library movement. | 0.00 | 0.00 |  |
|  | Total ( provision for NER) |  | -- | 73.50 |  |  | 0.00 | ** |  |
|  | Total (Revenue) |  | 503.00 | 692.00 |  |  | 594.34 | 694.14 |  |
| 33 | Building projects of attached / subordinate offices |  |  |  |  |  |  |  |  |
| 1. | National Museum, New Delhi | Civil & electrical works in National Museum | -- | 2.00 | Civil & electrical works in National Museum | To provide better facilities in the galleries and official wing of National Museum. | -- | 7.81 | Includes exp. for the projects for NGMA & NRLC. |
| 2. | National Archives of India |  | -- | 6.45 |  |  | -- | 4.18 |  |
|  | (i) | Replacement of A/C plant for NAI Building. |  |  | Replacement of A/C plant for NAI Building. | Providing better facilities in disposing of voluminous work and also protecting the valuable records available in the Archives |  |  |  |
|  | (ii) | Import of 4 Impregnator Laminators |  |  | Import of 4 Impregnator Laminators |  |  |  |  |
|  | (iii) | Construction of functional building of record center, Bhubaneswar |  |  | Construction of functional building of record center, Bhubaneswar |  |  |  |  |
|  | (iv) | Addition and alteration of works of NAI Main/ Annexe building, Record Centre Jaipur and Pondicherry and Regional Office Bhopal. |  |  | Addition and alteration of works of NAI Main/ Annexe building, Record Centre Jaipur and Pondicherry and Regional Office Bhopal. |  |  |  |  |
| 3. | Anthropological Survey of India | -- | 4.00 |  |  | -- | -- | 0.74 |  |
|  | (i) | Construction of Office building at Salt Lake, Kolkata |  |  | Preliminary estimates for construction of building has been intimated by CPWD for taking up these projects. | Creation of additional office accommodation |  |  |  |
|  | (ii) | Procurement of land and construction of Museum at Central Regional Centre, Nagpur. |  |  |  |  |  |  |  |
|  | (iii) | Construction of residential quarters guest house and Museum of International Standard etc. at Udaipur |  |  |  |  |  |  |  |
|  | (iv) | Procurement of additional land & construction of Guest House Library, Museum and Conference Hall of North East Regional Centre at Shillong. |  |  |  |  |  |  |  |
|  | (v) | Construction of residential quarters and guest house of North West Regional Centre, Dehra Dun. |  |  |  |  |  |  |  |
|  | (vi) | Procurement of additional land and construction of an International standard guest house DNA lab. At the SRC, Mysore. |  |  | Work is under progress |  |  |  |  |
|  | (vii) | Construction of Office Building and museum at SRC, Jagdalpur |  |  |  |  |  |  |  |
| 4. | National Research Laboratory for Conservation of Cultural Property, (NRLC) Lucknow | Construction of Training Institute/auditorium in the campus of NRLC Guest House | -- | 2.50 | Work is under progress | For important activities of Laboratory, Training Instt.-cum-Hostel/Guest House at NRLCCP, Lucknow. | -- | @ | @included under exp. shown against National Museum. |
| 5. | National Gallery of Modern Art (NGMA) | Furnishing of new Annexe buildings of NGMA at Delhi and Bangalore. | -- | 4.00 | Work is under progress |  | -- | @ | @included under exp. shown against National Museum. |
| 6. | Archaeological Survey of India | Purchase of land for construction of office building for ASI at Nagpur , construction of Institute of Archaeology at Greater NOIDA,, Construction of composite office building on own land of ASI at Samantarapur, Bhubaneswar, Construction of building at 24, Tilak Marg, New Delhi, construction of new museum building at Lothal, Halebidu, Sanchi and at Surya Pahal (North East). | -- | 24.00 | Work is under progress | Accommodation problem of ASI staff shall be solved. | -- | 22.44 |  |
| 7. | Public Libraries | Central Reference Library The work relating to installation of A/C facilities in their office | -- | 0.05 | This work will be completed in 2010-11 | Providing working facilities in the office for efficiency in the official work. | -- | 0.00 |  |
|  | Total (Building Projects) |  | -- | 43.00 |  |  | -- | 35.17 |  |
|  | Grand Total (Art and Culture) |  | 503.00 | 735.00 |  |  | 594.35 | 729.31 |  |

Note: Plan Exp. indicated in Col. 8 includes Exp. on North East Activities.